## Sheet1
FileSystemObjectType | Id | ServerRedirectedEmbedUri | ServerRedirectedEmbedUrl | ID | ContentTypeId | Title | Modified | Created | AuthorId | EditorId | OData__UIVersionString | Attachments | GUID | ComplianceAssetId | NPIProject | Pattern | PLN | CustomerCode | CustomerName | Country | Region | Plant | Quantity | Priority | Status | DrawingImage | Comments | RFQDate | PODate | ToolDate | ManufacturingDate | ShipmentDate | PiecesonSiteDate | TrialStartDate | CompletionDate | NextRemainderDate | RFQtoPOBlocker | POtoToolRMBlocker | ToolRMtoMfgBlocker | MfgtoOnSiteBlocker | OnSitetoTrialBlocker | OData__ColorTag | FirstUniqueAncestorSecurableObject | RoleAssignments | AttachmentFiles | ContentType | GetDlpPolicyTip | FieldValuesAsHtml | FieldValuesAsText | FieldValuesForEdit | File | Folder | LikedByInformation | ParentList | Properties | Versions | Author | Editor
0 | 91 | null |  | 91 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-02-28 11:43 | 2023-01-16 09:55 | 16 | 12 | 64 | FALSE | 7448c007-2de9-4f53-ba1f-8c9d48dbd5d1 | null | FCVI-DURAFLEX5M | BC48175 | Viso | 113315 | CELSA BARCELONA | Spain | Europe | SR | 10 | β – Beta | Manufacturing | {"type":"thumbnail","fileName":"7d4f8584-f4cc-413a-bbc6-833009c90f96.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/7d4f8584-f4cc-413a-bbc6-833009c90f96.jpeg","id":"a77a405a-c849-4c82-9136-1dc6f225aea1"} | 26.02.2024 packed | 2022-08-08 22:00 | 2022-09-07 22:00 | 2023-11-12 23:00 | 2024-02-25 23:00 | null | null | null | null | 2023-07-22 22:00 | null | 6. Components delay (e.g., cans delay) | 2.4. Properties Out of Spec | 1. Internal shipment delays | null | null
01.12.2023 new expectation will be WK48 ex SR
13.11.2023 3 tons rejuvenated in GH (blend 9015046166, batches F05C0970, F05C0971, F05C0972) arrived in SR
06.11.2023 Fired properties shared, proceed to shipment as per R&D approval
24.10.2023 - HOLD mixes 1301 back GH due to bad properties
21.09.2023 - pcs after x-ray, 1301 from OS delivered wait on testpot
14.09.2023 - pending 6 pcs (whole 1301) glaze/firing / X-RAY
08.09.2023 - pressing check
07.09.2023 - mixes blended
31.08 - pending confirmation wk36
28.08.2023 - ON HOLD DECISION FROM PIOTR SPERKA
25.08.2023 - new delivery mix 1301 from GH - next week will be blending
1204 - after blending
1048 - waiting on blending and properites will be next week
7.08.2023 - 2 pcs pressed, after X-Ray small lamination on pcs
03.08.2023 - pending mix from CH - Custom clearance in GH, mfg in 2 weeks
28.07.2023 pressed one piece with whole mix 1301, is going to firing
19.07.2023 tooling arrived to SR
17.07.2023 tooling ETA - invoice issues for airfr...
0 | 92 | null |  | 92 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-02-28 11:43 | 2023-01-16 13:52 | 16 | 12 | 52 | FALSE | 541fd2f9-832e-4d1f-a0e5-71f70fa72657 | null | FCVI-DURAFLEX5M | BC48183 | Viso | 113315 | CELSA BARCELONA | Spain | Europe | SR | 10 | β – Beta | Manufacturing | {"type":"thumbnail","fileName":"10a58fa5-8c99-4d2a-80ff-cbd207362fc4.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/10a58fa5-8c99-4d2a-80ff-cbd207362fc4.jpeg","id":"0ef6e72d-a6ac-4202-bb21-70a93d036ed6"} | 26.02.2024 packed | 2022-08-08 22:00 | 2022-09-07 22:00 | 2023-11-12 23:00 | 2024-02-25 23:00 | null | null | null | null | 2023-07-22 22:00 | null | 6. Components delay (e.g., cans delay) | 2.4. Properties Out of Spec | null | 2. Problems with Standard Product Currently Running /CCAR | null
13.11.2023 3 tons rejuvenated in GH (blend 9015046166, batches F05C0970, F05C0971, F05C0972) arrived in SR
06.11.2023 Fired properties shared, proceed to shipment as per R&D approval
24.10.2023 - HOLD mixes 1301 back GH due to bad properties
21.09.2023 - pcs after x-ray, 1301 from OS delivered wait on testpot
14.09.2023 - pending 6 pcs (whole 1301) glaze/firing / X-RAY
08.09.2023 - pressing check
07.09.2023 - mixes blended
31.08 - pending confirmation wk36
28.08.2023 - ON HOLD DECISION FROM PIOTR SPERKA
25.08.2023 - new delivery mix 1301 from GH - next week will be blending
1204 - after blending
1048 - waiting on blending and properites will be next week
7.08.2023 - 2 pcs pressed, after X-Ray small lamination on pcs
03.08.2023 - pending mix from CH - Custom clearance in GH, mfg in 2 weeks
28.07.2023 pressed one piece with whole mix 1301, is going to firing
19.07.2023 tooling arrived to SR
17.07.2023 tooling ETA - invoice issues for airfreight procedure
16.05.2023 PO to SR
05.05.202...
0 | 127 | null |  | 127 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 11:17 | 2023-01-30 06:49 | 20 | 12 | 24 | FALSE | b8062209-88ea-4581-af65-9e886a439346 | null | FCSR-LTECH | KA74159040 | Slidegate Assy. | 147723 | ArcelorMittal Long Products Canada-Ouest | Canada | NAFTA | SR | 40 | α – Alpha | Complete | {"type":"thumbnail","fileName":"6f1ecc02-36d8-4168-aeee-b599954d5849.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/6f1ecc02-36d8-4168-aeee-b599954d5849.jpeg","id":"7c1e2277-71f8-4cca-8bbc-df94ab293db2"} | 13.11.2023 - Final report shared - follow-up industrial trial recommended with 3mo. consumption. First trial ended 5.1hts vs 4.1hts STD - it is believed life potential can be higher. | 2022-10-25 22:00 | 2022-12-04 23:00 | 2023-01-12 23:00 | 2023-03-12 23:00 | null | 2023-07-26 22:00 | 2023-08-31 22:00 | 2023-10-16 22:00 | null | null | null | null | null | null | null
17.10.2023 - Trial Report shared (Maritz)
07.09.2023 - restart, first 9 sets some plates going to 7 heats some out on 4 similar to current TS3214 plates
DVB0272000 - raw plate code (LV12/5)
13.03.2023 shipped (SR W200057)
13.01.2023 pressed
26.10.2022 PO Date
05.12.2022 dwg revision
16.11.2021 1st dwg
0 | 135 | null |  | 135 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-03-06 13:30 | 2023-01-30 12:00 | 20 | 259 | 58 | FALSE | 74abd843-ce27-4969-a96c-40762f96f0ce | null | FCVI-DURAFLEX5M | BD74609 | Viso | 118716 | ERDEMIR EREGLI | Turkey | Europe | SR | 40 | α – Alpha | Manufacturing | {"type":"thumbnail","fileName":"5fe301d0-4813-421f-8683-0ffc84d08d23.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/5fe301d0-4813-421f-8683-0ffc84d08d23.jpeg","id":"172e3685-7598-4d13-824e-8242660bf6e2"} | 06.03.2024 no pcs pressed yet will be done after BD74609 | 2023-04-26 22:00 | 2023-05-10 22:00 | 2023-11-12 23:00 | 2024-02-19 23:00 | null | null | null | null | 2023-07-22 22:00 | null | 6. Components delay (e.g., cans delay) | 2.4. Properties Out of Spec. | 1. Internal shipment delays | null | null
20.02.2024 - 1204 not possible from quality perspective. Alternative with 630 working solution (40 pcs made) - Julien
12.02.2024 last week achieved 30 pieces - 15 waits for 1301 TP [Adrian Kozak]
07.02.2024 results were negative but SR-PDL succeed to do 1 good piece
01.02.2024 crack after pressing
01.12.2023 new expectation will be WK48 ex SR
13.11.2023 3 tons rejuvenated in GH (blend 9015046166, batches F05C0970, F05C0971, F05C0972) arrived in SR
06.11.2023 Fired properties shared, proceed to shipment as per R&D approval
24.10.2023- HOLD mixes 1301 back GH due to bad properties
21.09.2023 - tooling validation
14.09.2023 - WK37 will be pressing 2 pcs (with good properties)
08.09.2023 - pressing check
07.09.2023 - mixes blended
28.08.2023 - ON HOLD DECISION FROM PIOTR SPERKA
25.08.2023 - new delivery mix 1301 from GH- next week will be blending
1204 - after blending
1048 - waiting on blending and properites will be next week
Next will be consider...
0 | 136 | null |  | 136 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-13 22:56 | 2023-01-30 12:39 | 20 | 12 | 21 | FALSE | cd051e48-dae0-4aa2-9919-55412feb838c | null | FCVI-DURAFLEX5M | BD73437 | Viso | 480048 | VOESTALPINE LINZ 18000900 | Austria | Europe | CH | 60 | β – Beta | Complete | {"type":"thumbnail","fileName":"911378f2-a83d-45a2-ae74-f3d1e13f66fe.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/911378f2-a83d-45a2-ae74-f3d1e13f66fe.jpeg","id":"aaaaa095-c5b4-4696-b76b-c2c70eb3575a"} | To add 'glazing' as a option !!! | 2022-04-27 22:00 | 2022-06-07 22:00 | 2022-06-29 22:00 | 2022-10-27 22:00 | null | 2022-12-04 23:00 | 2022-12-15 23:00 | 2022-12-19 23:00 | null | null | null | null | null | null | null
28.10.2022 packed
04.10.2022 pieces canned
30.06.2022 tooling delivered
02.05.2023 2nd dwg revision
28.04.2022 1st dwg
0 | 138 | null |  | 138 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-24 13:48 | 2023-01-30 12:45 | 20 | 12 | 24 | FALSE | d87dc4fc-188c-4cc6-9119-8e8f877dc7a5 | null | FCSR-LTECH | TKA70769070 | Slidegate Assy. | 143484 | ArcelorMittal SA Newcastle | South Africa Republic | Europe | SR | 72 | β – Beta | Complete | {"type":"thumbnail","fileName":"6b5fa322-6715-4435-80f6-a6f1d078b48d.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/6b5fa322-6715-4435-80f6-a6f1d078b48d.jpeg","id":"643d9424-369b-4fc1-bf24-32b45b84b1cc"} | 15.12.2021 RFQ Date ~ PO Date | 2021-12-07 23:00 | 2021-12-14 23:00 | 2022-03-14 23:00 | 2022-05-15 22:00 | null | 2022-08-24 22:00 | 2022-09-14 22:00 | 2022-10-03 22:00 | null | null | null | null | null | null | null
existing pattern
30.01.2020 1st dwg
(16.03.2023 KA70769XXX)
0 | 140 | null |  | 140 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-12-11 12:33 | 2023-01-30 14:20 | 20 | 40 | 26 | FALSE | 77acd79b-7e0e-47ad-853f-d29d49b54c21 | null | FCSR-LTECH | TKA70769055 | Slidegate Assy. | 101015 | Corporacion Aceros Arequipa S.A. | Peru | South America | SR | 50 | α – Alpha | Complete | {"type":"thumbnail","fileName":"70dcb46c-69e6-4e28-b932-d9fb1f9650f0.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/70dcb46c-69e6-4e28-b932-d9fb1f9650f0.jpeg","id":"8f38383d-412b-493b-ab15-363f9ebc79b5"} | DVB0254000 - raw plate | 2023-02-08 23:00 | 2023-02-15 23:00 | 2023-04-13 22:00 | 2023-06-04 22:00 | null | 2023-09-24 22:00 | 2023-09-26 22:00 | 2023-12-30 23:00 | null | null | null | null | null | null | null
Trial Date 27.09-03.10 >>20.10 Report - Vini
05.06.2023 - SR3175779
16.02.2023 PO Date ~ RFQ Date
30.01.2020 1st dwg
earlier same pattern for Columbus Stainess - 50 pcs (46 pcs) PO Date - 08.09.2022, shipped - 16.12.2022
checked by Joanna G.
0 | 142 | null |  | 142 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 11:41 | 2023-02-01 12:36 | 16 | 12 | 18 | FALSE | 2ee51c4c-6634-4ccf-a6bb-44d72b6c7fde | null | FCVI-DURAFLEX5M | BD71787 | Viso | 151482 | Asha | Russia | Europe | TC | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"a63ca4fc-b9c0-40be-9185-23cf3eaa728e.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/a63ca4fc-b9c0-40be-9185-23cf3eaa728e.jpeg","id":"5cb9108a-6a74-4cd7-a724-a310bdc4df4b"} | to add more than one !!! | 2021-08-18 22:00 | 2021-09-13 22:00 | 2021-11-25 23:00 | 2022-02-14 23:00 | null | 2022-03-06 23:00 | 2023-04-13 22:00 | 2023-05-03 22:00 | null | null | null | null | null | 3. Commercial issues/relationship | null
*war / capacity etc.
Tooling Date - to check
17.11.2021 2nd dwg revision
19.08.2021 1st dwg
0 | 143 | null |  | 143 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-24 13:46 | 2023-02-01 16:14 | 20 | 12 | 17 | FALSE | ae05f21f-c2c6-4f74-ab62-db911a488ee7 | null | FCSR-LTECH | TKA70769055 | Slidegate Assy. | 101146 | Columbus Stainless | South Africa Republic | Europe | SR | 46 | β – Beta | Complete | {"type":"thumbnail","fileName":"90ec07ac-54ce-413d-b3c1-f962e7ec5cb4.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/90ec07ac-54ce-413d-b3c1-f962e7ec5cb4.jpeg","id":"6dd899f0-47ad-43ba-94bb-8328683abee2"} | Trial Dates - to check (Martin) | 2022-08-31 22:00 | 2022-09-07 22:00 | 2022-10-26 22:00 | 2022-12-15 23:00 | null | 2023-03-27 22:00 | 2023-07-04 22:00 | 2023-09-17 22:00 | 2023-02-25 23:00 | null | null | null | null | null | null
DVB0254000 raw plate
16.12.2022 46 pcs / 50 pcs shipped
08.09.2022 RFQ Date ~ PO Date
30.01.2020 1st dwg
0 | 145 | null |  | 145 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-03-06 13:30 | 2023-02-02 20:04 | 16 | 259 | 49 | FALSE | f3f0c37d-970e-43f2-83fb-234ce89bded1 | null | FCVI-DURAFLEX5M | BD74591 | Viso | 118716 | ERDEMIR EREGLI | Turkey | Europe | SR | 60 | α – Alpha | Manufacturing | {"type":"thumbnail","fileName":"4ae9443e-6950-49b0-9667-0862d31acfd7.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/4ae9443e-6950-49b0-9667-0862d31acfd7.jpeg","id":"409b2fc4-54bd-4546-b971-5aceb3d01ffa"} | 06.03.24 29 pcs after firing, to be shipped. | 2022-11-07 23:00 | 2023-05-10 22:00 | 2023-11-12 23:00 | 2024-02-19 23:00 | null | null | null | null | 2023-07-22 22:00 | null | 6. Components delay (e.g., cans delay) | 2.4. Properties Out of Spec | 1. Internal shipment delays | null | null
20.02.2024 - 1204 not possible from quality perspective. Alternative with 630 working solution (40 pcs made) - Julien
07.02.2024 results were negative but SR-PDL succeed to do 1 good piece
01.02.2024 crack after pressing
01.12.2023 new expectation will be WK48 ex SR
13.11.2023 3 tons rejuvenated in GH (blend 9015046166, batches F05C0970, F05C0971, F05C0972) arrived in SR
06.11.2023 Fired properties shared, proceed to shipment as per R&D approval
24.10.2023 - HOLD mixes 1301 back GH due to bad properties
21.09.2023 - tooling validation
14.09.2023 - WK37 will be pressing 2 pcs (good properties)
08.09.2023 - pressing check
07.09.2023 - mixes blended
28.08.2023 - ON HOLD DECISION FROM PIOTR SPERKA
25.08.2023 - new delivery mix 1301 from GH - next week will be blending
1204 - after blending
1048 - waiting on blending and properites will be next week
Next will be consider bags
03.08.2023 - pending mix from CH - Custom clearance in GH, mfg in 2 weeks
19.07.2023 to...
0 | 146 | null |  | 146 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 11:45 | 2023-02-03 15:20 | 12 | 12 | 16 | FALSE | d2f00756-753b-4f78-9ac7-1635e7818714 | null | FCVI-DURAFLEX1000H | BD69286 | Viso | 100902 | ArcelorMittal Steel Vanderbijlpark | South Africa Republic | Europe | MY | 60 | α – Alpha | Complete | {"type":"thumbnail","fileName":"85c60c4b-2e3b-4d48-bf6b-0415ae151f92.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/85c60c4b-2e3b-4d48-bf6b-0415ae151f92.jpeg","id":"8808c545-7e1a-401c-8f3a-6c880fc91c30"} | 06.01.2021 delivery confirmation | 2020-11-11 23:00 | 2020-11-18 23:00 | 2021-01-05 23:00 | 2021-03-06 23:00 | null | 2021-06-27 22:00 | 2021-06-30 22:00 | 2021-08-17 22:00 | null | null | null | null | null | null | null
19.11.2020 PO Date
27.07.2021 2bd dwg revision
12.11.2020 1st dwg
0 | 147 | null |  | 147 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-16 12:15 | 2023-02-22 08:38 | 23 | 248 | 10 | FALSE | c300a450-6859-4b39-8dcb-8b55e59c716e | null | FCPS-OPTIFLOW+ | PS-OPTIFLOWP | Purge Plugs | 102205 | Nucor Yamato | USA | NAFTA | SR | 8 | α – Alpha | Complete | {"type":"thumbnail","fileName":"3d2b6a9d-42d8-46f1-9c88-ad945b56bad3.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/3d2b6a9d-42d8-46f1-9c88-ad945b56bad3.jpeg","id":"364e6ca6-a6f5-4f3f-9293-ed4e7c9a6dd2"} | PATTERN !!!! PH09080 (Launch Code: FCPS-HSC) | 2023-03-23 23:00 | 2023-07-23 22:00 | null | null | null | null | null | 2023-10-10 22:00 | null | 5. Quoted Price (Quoted Mfg. Cost) | null | null | null | null | null
11/10/23 - PACKED 7 PCS
10/10/23 - reduced order to 7pcs.
21/09/23 manufacturing not started
2nd dwg revision 24.03.2023
1st dwg 09.01.2023
0 | 149 | null |  | 149 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-30 07:28 | 2023-03-03 09:45 | 20 | 12 | 13 | FALSE | 9dc27f5b-0e44-4a38-8970-090531e0f9a3 | null | FCVI-DURAFLEX5M | BC46724 | Viso | 171656 | AQS | Algeria | Europe | SR | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"b8288c09-3107-48b2-953f-4660f1b4776d.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/b8288c09-3107-48b2-953f-4660f1b4776d.jpeg","id":"a0dbbb37-6759-4371-a2c4-8af21a4ec380"} | Tooling Date - to check | 2021-04-29 22:00 | 2021-08-09 22:00 | 2021-10-13 22:00 | 2022-02-07 23:00 | null | 2022-03-20 23:00 | 2022-05-11 22:00 | 2022-06-07 22:00 | null | null | null | null | null | null | null
27.08.2021 2nd dwg revision
30.04.2021 1st dwg
0 | 150 | null |  | 150 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 12:16 | 2023-03-28 09:22 | 16 | 12 | 27 | FALSE | e063ba90-77ab-4667-ad23-f60d48266f5b | null | FCVI-DURAFLEX1000H | BD74799 | Viso | 100902 | ArcelorMittal Steel Vanderbijlpark | South Africa Republic | Europe | MY | 60 | β – Beta | Manufacturing | {"type":"thumbnail","fileName":"f2bc0b8c-bef6-4b99-8230-d858040c4f65.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/f2bc0b8c-bef6-4b99-8230-d858040c4f65.jpeg","id":"64932a69-7264-4db7-bd7f-5922a1602189"} | 06.03.2024 expected mid-March on customer site | 2022-11-21 23:00 | 2023-02-01 23:00 | 2023-08-31 22:00 | 2023-11-29 23:00 | null | null | null | null | null | null | 6. Components delay (e.g., cans delay) | 2.3. XRAY Defects | null | null | null
14.11.2023 complete X-ray and pack ASAP
06.11.2023 xray of 20 pcs before the end of the week
27.10.2023 but put it on-line as soon as a spot is available
01.09.2023 30 pcs pressed. X-ray 14 rejects, 5 more pcs pressed: 3 with cracks, Testing done on changed filling process. 4 pcs pressed without cracks, cans: arrived
16.08.2023 only 4 pcs X-rayed with a crack, to send the results of the 30 pcs.
Skawina Cancel
04.08.2023 30 pcs fired, 5 pcs pending to machine
03.08.2023 5 pcs fired: glaze ok, packing crate
26.06.2023 Pending pressing 6 pieces trials and results X-rays, cans WK22
27.04.2023 mix rejected, tooling arrived
02.02.2023 gentlemen agreement, TRF
0 | 151 | null |  | 151 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 13:33 | 2023-04-06 13:34 | 12 | 12 | 14 | FALSE | 7c635d43-47d5-4b5e-96f2-6d51272abf5e | null | FCSR-LTECH | TKA70769040 | Slidegate Assy. | 104815 | Ternium Mexico, SA de DV (Norte) | Mexico | NAFTA | SR | 20 | α – Alpha | Complete | {"type":"thumbnail","fileName":"e9cbcf4b-2bd3-4ea7-bf68-fd522dcd8c56.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/e9cbcf4b-2bd3-4ea7-bf68-fd522dcd8c56.jpeg","id":"0ee51da3-ef90-4123-98f1-2e091ecbc95c"} | DVB0255000 20/40 pcs | 2022-06-26 22:00 | 2022-07-03 22:00 | 2022-08-04 22:00 | 2022-09-15 22:00 | null | 2022-12-06 23:00 | 2023-03-08 23:00 | 2023-03-29 22:00 | null | null | null | null | null | null | null
04.07.2022 PO Date ~RFQ Date
checked by Joanna G.
30.01.2020 1st dwg
0 | 200 | null |  | 200 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 13:35 | 2023-04-12 14:56 | 20 | 12 | 12 | FALSE | c3b4873f-10b5-42c5-a07e-d2a436ea24df | null | FCSR-LTECH | KA74175065 | Slidegate Assy. | 123483 | AMNSI | India | India | SR | 184 | α – Alpha | Complete | {"type":"thumbnail","fileName":"014a6c85-adf4-4c27-9bfc-4b4ae2da22e0.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/014a6c85-adf4-4c27-9bfc-4b4ae2da22e0.jpeg","id":"b5b7794d-7295-4e59-a7d7-45767ad17ede"} | to check report shared date - by Sudip | 2022-07-06 22:00 | 2022-07-13 22:00 | 2022-08-17 22:00 | 2022-08-30 22:00 | null | 2022-12-08 23:00 | 2023-01-09 23:00 | 2023-04-02 22:00 | null | 1. Wrong Customer Selection | Tool production issues | Mixing/Blending | Warehouse stock | Commercial issues/relationship | null
DVB0273000 - Raw Plate (100 pcs)
09.08.2022 packed
14.07.2022 PO Date ~ RFQ Date
17.11.2021 1st dwg
checked by Joanna G.
0 | 201 | null |  | 201 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 14:26 | 2023-04-12 15:33 | 20 | 12 | 21 | FALSE | f8e79060-703f-433a-b087-0f9eecf265d8 | null | FCSR-LTECH | TKA70769040 | Slidegate Assy. | 152515 | ARRENDADORA SIMEC, S.A. DE C.V. | Mexico | NAFTA | SR | 20 | α – Alpha | Complete | {"type":"thumbnail","fileName":"699208cd-04eb-4150-b294-a5db69b9a491.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/699208cd-04eb-4150-b294-a5db69b9a491.jpeg","id":"5672621e-b32b-4dfb-bd38-c775ff1fd680"} | DVB0255000 - 20/40 pcs | 2022-06-23 22:00 | 2022-06-30 22:00 | 2022-08-25 22:00 | 2022-10-17 22:00 | null | 2022-11-28 23:00 | 2023-01-24 23:00 | 2023-02-01 23:00 | null | null | null | null | null | null | null
01.07.2022 PO Date ~RFQ Date
30.01.2020 1st dwg
0 | 202 | null |  | 202 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-01-15 14:10 | 2023-04-13 02:46 | 20 | 12 | 20 | FALSE | 23f4bd1b-b4ca-4a35-8c6c-90525c424329 | null | FCPS-OPTIFLOW+ | PS-OPTIFLOWP | Purge Plugs | 126487 | Gerdau Jackson | USA | NAFTA | SR | 8 | α – Alpha | PO | {"type":"thumbnail","fileName":"4aa45382-422b-4c72-9d46-0dfde880d2d6.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/4aa45382-422b-4c72-9d46-0dfde880d2d6.jpeg","id":"0c3af55a-6580-44de-b6d0-22923d6e5df6"} | PATTERN !!! PH08801 (Launch Code: FCPS-HSC) | 2023-03-23 23:00 | 2023-11-19 23:00 | null | null | null | null | null | null | 2023-04-16 22:00 | 5. Quoted Price (Quoted Mfg. Cost) | 6. Components delay (e.g., cans delay) | 1.5. Impregnation | 2.2. Air freight priority | 5. Customer Operational Delays | null
PO Date - to check
2nd dwg revision 24.03.2023
1st dwg 10.02.2023
0 | 203 | null |  | 203 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 11:47 | 2023-04-13 15:02 | 16 | 12 | 16 | FALSE | aeedb492-872c-470c-aea1-68ff8ca8fd26 | null | FCVI-DURAFLEX5M | BD69245 | Viso | 151482 | Asha | Russia | Europe | TC | 10 | β – Beta | Complete | {"type":"thumbnail","fileName":"2731e4b2-243c-49db-bd64-c8ce32cc1256.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/2731e4b2-243c-49db-bd64-c8ce32cc1256.jpeg","id":"929c0fbc-cbe3-41c8-b986-e40e80f9d2e7"} | 22.12.2021 2nd dwg revision | 2021-12-21 23:00 | 2021-12-27 23:00 | 2022-01-13 23:00 | 2022-02-14 23:00 | null | 2022-03-06 23:00 | 2022-06-02 22:00 | 2022-08-17 22:00 | null | 4. Wrong application conditions specified | null | null | null | null | null
05.11.2020 1st dwg
0 | 204 | null |  | 204 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-30 15:48 | 2023-04-18 05:59 | 24 | 12 | 27 | FALSE | b707f54a-a54c-4a6e-acfb-e5fcc9ee2618 | null | FCPS-OPTIFLOW+ | PQ21259 | Purge Plugs | 101821 | JSW Ohio | USA | NAFTA | SR | 28 | α – Alpha | PO | {"type":"thumbnail","fileName":"426bb9c7-fc8c-4334-b576-491a0c6c0070.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/426bb9c7-fc8c-4334-b576-491a0c6c0070.jpeg","id":"cc1bc45d-2025-415f-8cc9-19b998fb8df4"} | 1st dwg 25.01.2023 | 2023-01-24 23:00 | 2023-02-26 23:00 | null | null | null | null | null | null | 2023-04-19 22:00 | Customer Loss of Interest or Push for Trial | Raw materials delay (e.g., mix delay) | null | 1.1. Warehouse stock | null | null
0 | 205 | null |  | 205 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-07-04 11:33 | 2023-05-02 16:31 | 40 | 12 | 30 | FALSE | 90301e5c-44fa-45a4-9793-e98532098122 | null | FCSR-LTECH | KA70769045 | Slidegate Assy. | 101497 | ArcelorMittal Juiz de Fora | Brazil | South America | SR | 157 | β – Beta | Trial | {"type":"thumbnail","fileName":"27c1255d-1660-4a8d-a895-33a41838c9f1.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/27c1255d-1660-4a8d-a895-33a41838c9f1.jpeg","id":"ac8890cb-6c75-4de3-8ad3-49d67bf57a19"} | Trial Date - to check | 2023-03-15 23:00 | 2023-03-29 22:00 | 2023-07-05 22:00 | 2023-09-21 22:00 | null | 2023-11-16 23:00 | 2024-01-31 23:00 | null | null | null | null | null | null | null | null
22.09.2023 157pcs shipped to customer
21.09.2023 order reduced from 160pcs to 157pcs
14.09.2023 transferred to Kokotow 37pcs
13.09.2023 37pcs packed SR3375696
13.09.2023 not fully 60pcs to be packed and shipped
07.09.2023 in total for Brazil 220pcs/280pcs produced
04.09.2023 transferred to Kokotow 100pcs
02.09.2023 100 pcs packed from regular order SR3356509
31.08.2023 transferred to Kokotow 20pcs
30.08.2023 20 pcs on alternative raw materials packed, marked on green label (SR3355750; SR3355751)
current kiln 5th - pressed WK28, fired WK29/30, impregnation WK31/32
DVB0254000 - raw plate
23.08.2023 pending assembly
16.03.2023 1st dwg
0 | 206 | null |  | 206 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-07-04 11:34 | 2023-05-02 16:38 | 40 | 12 | 24 | FALSE | a25c842a-e537-42d5-ac71-444936f4148b | null | FCSR-LTECH | KA70769045 | Slidegate Assy. | 156457 | AM RESENDE | Brazil | South America | SR | 100 | β – Beta | Trial | {"type":"thumbnail","fileName":"01f1c49a-86c8-480e-8119-f06c9a912177.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/01f1c49a-86c8-480e-8119-f06c9a912177.jpeg","id":"211670f8-1e36-4aea-adb7-51724182a4e3"} | Trial Date - to check | 2023-03-15 23:00 | 2023-03-19 23:00 | 2023-07-05 22:00 | 2023-09-21 22:00 | null | 2023-11-16 23:00 | 2024-01-10 23:00 | null | null | null | null | null | null | null | null
22.09.2023 100pcs shipped to customer
21.09.2023 in total for Brazil 257pcs/280 pcs produced (order reduced)
07.09.2023 in total for Brazil 220pcs/280 pcs produced
05.09.2023 transferred to Kokotow
04.09.2023 100 pcs packed from regular order SR3365140
01.09 packing mid of week 36
4800012911
current kiln 5th - pressed WK28, fired WK29/30, impregnation WK31/32
DVB0254000 - raw plate
23.08.2023 pending assembly
16.03.2023 1st dwg
0 | 207 | null |  | 207 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-14 15:12 | 2023-05-18 13:07 | 12 | 12 | 21 | FALSE | e840b43f-c630-4f00-9e69-bad1801c1eac | null | FCVI-DURAFLEX5M | BD73528 | Viso | 102563 | Trinecke Zelezarny | Czechia | Europe | MY | 10 | β – Beta | Complete | {"type":"thumbnail","fileName":"07ce2dd6-cda0-4411-822f-7e639bf1da83.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/07ce2dd6-cda0-4411-822f-7e639bf1da83.jpeg","id":"d08c9a49-32a9-4f45-a2db-469cff3285c6"} | 02.08.2023 Trial dates - Dima | 2022-05-23 22:00 | 2022-07-13 22:00 | 2023-04-26 22:00 | 2023-06-21 22:00 | null | 2023-07-09 22:00 | 2023-07-30 22:00 | 2023-08-10 22:00 | null | null | null | 2.4. Properties Out of Spec | 2.2. Air freight priority | null | null
04.07.2023 shipped
air freight cost approval (4-5 days) ETA TBC 05.06.2023
27.04.2023 pieces ok, waiting for the can
19.01.2023 mix with contamination
22.12.2022 mix 1301 rejected
14.07.2022 PO
24.05.2022 1st dwg
0 | 208 | null |  | 208 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-09-19 14:58 | 2023-05-25 12:17 | 12 | 12 | 11 | FALSE | 88d6d85d-0aef-4e85-be93-a6753bf62821 | null | FCPS-OPTIFLOW+ | PS-OPTIFLOWP | Purge Plugs | 172170 | ArcelorMittal Steelton LLC (CRPAS2) | USA | NAFTA | SR | 20 | α – Alpha | PO | {"type":"thumbnail","fileName":"5aea4b3f-8b18-4c7f-9e6d-24874363627f.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/5aea4b3f-8b18-4c7f-9e6d-24874363627f.jpeg","id":"77b8d96d-7df2-4c6e-b990-2676c35f6c1e"} | PATTERN !!! QF09430 | 2022-12-13 23:00 | 2023-01-15 23:00 | null | null | null | null | null | null | null | null | 6. Components delay (e.g., cans delay) | null | null | null | null
Launch Code FCPS-OPTIFLOW+ instead of FCPS-HSC
2x PO: 01.16.2023 & 17.05.2023
to move the delivery dates in the order:
From 22.09.2023 to 10.11.2023
From 06.10.2023 to 08.12.2023
14.12.2022 1st dwg
0 | 209 | null |  | 209 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-24 13:43 | 2023-05-25 22:02 | 12 | 12 | 11 | FALSE | 7b95090f-1e3c-406e-8ae4-a3f3d1036157 | null | FCSR-LTECH | KA74647045 | Slidegate Assy. | 113303 | QATAR STEEL COMPANY QSC | Qatar | Europe | SR | 72 | α – Alpha | Pieces on Site | {"type":"thumbnail","fileName":"80d9e451-6c92-4cc7-a634-33d19061d99d.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/80d9e451-6c92-4cc7-a634-33d19061d99d.jpeg","id":"0e43e1fd-3ace-4f9d-9334-1413d8f866d8"} | Trial Plan - ON-HOLD !!! (Martin) | 2022-03-02 23:00 | 2022-05-08 22:00 | 2022-07-13 22:00 | 2022-09-26 22:00 | null | 2023-01-11 23:00 | null | null | null | null | null | null | null | null | null
27.09.2022 packed - SR2395163
DBB0338000 - raw plate
09.05.2022 PO
03.03.2022 1st dwg
0 | 210 | null |  | 210 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 11:28 | 2023-05-25 22:06 | 12 | 12 | 10 | FALSE | dd80815d-e617-4d5a-9738-0368a50282f9 | null | FCSR-LTECH | KA70785058 | Slidegate Assy. | 114991 | KARDEMIR | Turkey | Europe | SR | 50 | α – Alpha | Complete | {"type":"thumbnail","fileName":"f144fe2c-43b6-4e66-b3f6-ff77568ca8f8.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/f144fe2c-43b6-4e66-b3f6-ff77568ca8f8.jpeg","id":"debb5758-1a04-4e9b-8438-a1c9c35ff437"} | Trial dates - to check - Dima !!! | 2022-10-13 22:00 | 2022-11-29 23:00 | 2023-01-25 23:00 | 2023-02-18 23:00 | null | 2023-03-23 23:00 | 2023-06-04 22:00 | 2023-06-14 22:00 | null | null | null | null | null | null | null
DVB0256000 - raw plate
24.03.2023 shipped
19.02.2023 manufactured
26.01.2023 (17.01.2023 RM confirmed)
30.11.2022 PO received
checked by Joanna G.
0 | 211 | null |  | 211 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 11:48 | 2023-05-26 05:45 | 12 | 12 | 9 | FALSE | 73b52a3a-a488-4bc9-b85c-439a98261188 | null | FCVI-DURASLEEVE-FLAT | BZ48909 | Viso | 480048 | VOESTALPINE LINZ 18000900 | Austria | Europe | TC | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"88f5f129-e213-4aea-a8a2-e094a8e30445.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/88f5f129-e213-4aea-a8a2-e094a8e30445.jpeg","id":"e676483e-01dd-4645-ba7e-c60805e49377"} | to check production Date | 2022-08-02 22:00 | 2022-09-25 22:00 | 2022-11-02 23:00 | 2022-11-30 23:00 | null | 2023-03-05 23:00 | 2023-04-02 22:00 | 2023-04-23 22:00 | null | null | null | null | null | null | null
to confirm Trial Date
0 | 212 | null |  | 212 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 15:15 | 2023-05-26 06:17 | 12 | 12 | 14 | FALSE | 08182303-01ca-4aa9-80a8-520c7e6c3968 | null | FCVI-DURASLEEVE-LONG | BK63143 | Viso | 102205 | Nucor Yamato | USA | NAFTA | MY | 10 | α – Alpha | Manufacturing | {"type":"thumbnail","fileName":"981d4030-bc3b-43a6-ba32-6a3c625f6ed1.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/981d4030-bc3b-43a6-ba32-6a3c625f6ed1.jpeg","id":"b9b40487-8eca-4c7f-88dc-18522b30ccec"} | MYV3230113 | 2022-07-11 22:00 | 2022-09-29 22:00 | 2023-04-26 22:00 | 2023-08-03 22:00 | null | null | null | null | null | null | null | null | null | null | null
WK31 Communicate with Santos\Paul to what can we do ? use anyway or remachining ?
Trial - Undersize flange - 9mm instead of 14mm at the holding area of the SES
12.07.2022 1st dwg
0 | 213 | null |  | 213 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 15:15 | 2023-05-26 06:26 | 12 | 12 | 9 | FALSE | ad7b11f4-d3f4-4034-b680-0a541dd2e579 | null | FCVI-DURASLEEVE-LONG | BK63150 | Viso | 102205 | Nucor Yamato | USA | NAFTA | MY | 10 | β – Beta | Manufacturing | {"type":"thumbnail","fileName":"8931cbed-f0f8-41e0-8632-eaf2dde7052d.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/8931cbed-f0f8-41e0-8632-eaf2dde7052d.jpeg","id":"1db8adba-3fd0-4c34-88e5-081489e091d8"} | MYV3230181 | 2022-07-11 22:00 | 2022-09-29 22:00 | 2023-04-26 22:00 | 2023-08-03 22:00 | null | null | null | null | null | null | null | null | null | null | null
WK31 Communicate with Santos\Paul to what can we do ? use anyway or remachining ?
Trial - Undersize flange, 9mm instead of 14mm at the holding area of the SES
12.07.2022 1st dwg
0 | 214 | null |  | 214 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 15:16 | 2023-05-26 06:29 | 12 | 12 | 12 | FALSE | 7c25103e-f44b-4dea-a3ce-13afed109c5f | null | FCVI-DURASLEEVE-LONG | BK63168 | Viso | 102205 | Nucor Yamato | USA | NAFTA | MY | 10 | β – Beta | Manufacturing | {"type":"thumbnail","fileName":"3c962a92-1014-4480-844e-d66eefaf5571.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/3c962a92-1014-4480-844e-d66eefaf5571.jpeg","id":"c1b3c438-cf25-4da8-b070-08ebe3cc3c80"} | WK31 Communicate with Santos\Paul to what can we do ? use anyway or remachining ? | 2022-07-11 22:00 | 2022-09-29 22:00 | 2023-04-26 22:00 | 2023-08-03 22:00 | null | null | null | null | null | null | null | null | null | null | null
Trial - Undersize flange, 9mm instead of 14mm at the holding area of the SES
12.07.2022 1st dwg
0 | 215 | null |  | 215 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 11:48 | 2023-05-26 06:38 | 12 | 12 | 10 | FALSE | 9908cd92-4662-4af9-a438-3cefb11af7e3 | null | FCSR-LTECH | KA75693065 | Slidegate Assy. | 150139 | ECHENG STEEL | China | China | SR | 40 | α – Alpha | Complete | {"type":"thumbnail","fileName":"919375b8-bfcf-419f-99f7-fae53a1d607e.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/919375b8-bfcf-419f-99f7-fae53a1d607e.jpeg","id":"e2a8a88b-1475-43a6-aec6-bb8a0d1f5d65"} | SK02059000 | 2022-07-21 22:00 | 2022-09-01 22:00 | 2022-09-29 22:00 | 2022-11-14 23:00 | null | 2023-01-15 23:00 | 2023-02-09 23:00 | 2023-03-30 22:00 | null | null | null | null | null | null | null
15.11.2022 SR2426015 packed
22.07.2022 1st dwg
0 | 216 | null |  | 216 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 14:09 | 2023-05-26 06:52 | 12 | 12 | 16 | FALSE | 6d7204c5-80c0-4f97-82d2-89fc25713203 | null | FCSR-LTECH | TKA70769045 | Slidegate Assy. | 169250 | Gerdau Corsa Sahagun | Mexico | NAFTA | SR | 80 | α – Alpha | Complete | {"type":"thumbnail","fileName":"83ad4962-052f-41cc-8bf7-e41bb48e9839.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/83ad4962-052f-41cc-8bf7-e41bb48e9839.jpeg","id":"b6c038a3-bddf-4bc9-8931-180420fe1bc9"} | DVB0255000 - 2 PO x 40 pcs (packed 80 pcs) - MFG / Pieces on site to be verified | 2022-11-09 23:00 | 2022-11-16 23:00 | 2023-01-05 23:00 | 2023-03-12 23:00 | null | 2023-05-14 22:00 | 2023-06-14 22:00 | 2023-07-06 22:00 | null | null | null | null | null | null | null
17.11.2022 PO Date ~RFQ Date
13.03.2023 shipment
19.02.2023 manufactured
17.11.2022 PO extra 40 pcs
26.09.2022 PO 20 to 40 pcs
10.08.2022 PO 20 pcs
30.01.2020 1st dwg
checked by Joanna G.
0 | 217 | null |  | 217 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 16:33 | 2023-05-26 06:57 | 12 | 12 | 15 | FALSE | 1d49c3eb-6481-4ae9-b1b3-af5c2683356a | null | FCSR-LTECH | KA74977050 | Slidegate Assy. | 142906 | Ternium Mexico, SA de DV (Puebla) | USA | NAFTA | SR | 50 | α – Alpha | Complete | {"type":"thumbnail","fileName":"d58f0828-22f3-416f-a8ea-71e2ecce0211.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/d58f0828-22f3-416f-a8ea-71e2ecce0211.jpeg","id":"b76060b2-4779-49af-b3c9-b6c70bd40837"} | to check with Francisco / Ken | 2023-01-24 23:00 | 2023-01-31 23:00 | 2023-03-02 23:00 | 2023-05-09 22:00 | null | 2023-07-31 22:00 | 2023-08-28 22:00 | 2023-09-13 22:00 | null | null | null | null | null | null | null
trial plan dates ??
1st dwg 27.04.2023
checked by Joanna G.
0 | 218 | null |  | 218 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-24 14:05 | 2023-05-26 07:03 | 12 | 12 | 13 | FALSE | 2c37e3f1-19b4-4a5c-bd99-e56a5644d02d | null | FCSR-LTECH | KA76188055 | Slidegate Assy. | 480062 | CELSA HUTA OSTROWIEC | Poland | Europe | SR | 47 | α – Alpha | Complete | {"type":"thumbnail","fileName":"aa48a549-6d6e-4a15-b734-a5ed53741e1d.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/aa48a549-6d6e-4a15-b734-a5ed53741e1d.jpeg","id":"b78010f1-5185-497a-8d72-fee025061381"} | Trial Date - to check (Radek) | 2022-08-30 22:00 | 2022-09-07 22:00 | 2022-10-04 22:00 | 2022-10-26 22:00 | null | 2022-11-30 23:00 | 2023-05-07 22:00 | 2023-06-06 22:00 | null | null | null | null | null | null | null
The general appearance and performance of Surface Layer
TS3182/3420 seem to be like Teardrop CDT, for the
performance as well as for the back side (TS3420)
The pattern of cracks of throttle path areas on teardrop,
SLCDT and Full Plate look very similar
SK02976000 raw plate
08.09.2022 PO
31.08.2022 1st dwg
0 | 219 | null |  | 219 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 15:17 | 2023-05-26 07:28 | 12 | 12 | 9 | FALSE | 1876df9b-ac17-490e-aedb-e2b4854126f9 | null | FCVI-DURASLEEVE-FLAT | BK63887 | Viso | 101821 | JSW Ohio | USA | NAFTA | MY | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"05aba865-cc9a-4717-8495-52d6ffcabafa.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/05aba865-cc9a-4717-8495-52d6ffcabafa.jpeg","id":"add6673b-68e2-4c1c-ac36-72a6eb6a65c5"} | MYS3260128 - crate number | 2023-01-04 23:00 | 2023-02-23 23:00 | 2023-04-13 22:00 | 2023-06-29 22:00 | null | 2023-07-04 22:00 | 2023-07-11 22:00 | 2023-08-01 22:00 | null | null | null | null | null | null | null
BW13768 / BK63887
Lost business due to payment issues.
Trying to regain business
Initial trial very succesful - DURASLEEVE TO BE ADDED
05.01.2023 1st dwg
0 | 220 | null |  | 220 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 12:25 | 2023-05-26 14:15 | 12 | 12 | 23 | FALSE | da7298c3-0075-4536-af1f-03cec0f4ea21 | null | FCVI-DURAFLEX20H | BD74401 | Viso | 200359 | TAMSA | Mexico | NAFTA | MY | 6 | α – Alpha | Pieces on Site | {"type":"thumbnail","fileName":"dcd3812c-2e25-4cfd-bb9e-e439a38d3bed.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/dcd3812c-2e25-4cfd-bb9e-e439a38d3bed.jpeg","id":"371ffe38-cdeb-43c3-8ae9-52b3c26ff33a"} | 18.09.2023 not shipped yet. Will be shipped when the trial of BD74252 starts | 2022-09-14 22:00 | 2022-10-02 22:00 | 2023-05-25 22:00 | 2023-06-25 22:00 | null | 2023-09-17 22:00 | null | null | null | null | null | 2.4. Properties Out of Spec | null | null | null
26.06.2023 packed MYV3250112
26.05.2023 start production with blend 31322 of mix 1301
11.05.2023 Waiting for mix to get the pieces repressed
05.05.2023 Re-pressed pieces had cracking in the seat
21.04.2023 re-press at least 3 pieces to have complete order
31.03.2023 pressing start
17.03.2023 share results of fired properties of blend
03.03.2023 preparation of thermites and test pots
19.01.2023 mix with contamination
22.12.2022 mix 1301 rejected
08.12.2022 pieces rejected
03.10.2022 PO (22507212)
15.09.2022 1st dwg
0 | 221 | null |  | 221 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 12:17 | 2023-05-26 20:46 | 12 | 12 | 21 | FALSE | 17a701b1-03f8-4a9b-8de9-d4c7ac5e3a9a | null | FCVI-DURAFLEX5M | BC47979 | Viso | 126487 | Gerdau Jackson | USA | NAFTA | MY | 25 | α – Alpha | Complete | {"type":"thumbnail","fileName":"48b1f5dc-7810-4b53-bf33-64d791673f44.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/48b1f5dc-7810-4b53-bf33-64d791673f44.jpeg","id":"8e41163d-17df-46e0-82b0-f17ed5ce791f"} | 19.08.2023 10Hr 40min (10heats) | 2022-06-26 22:00 | 2022-07-11 22:00 | 2023-05-10 22:00 | 2023-06-25 22:00 | null | 2023-07-06 22:00 | 2023-08-17 22:00 | 2023-09-19 22:00 | null | null | null | 2.4. Properties Out of Spec | null | null | null
We are shooting for 18.08:
. receiving the pallet on 16-17.08
. brief meeting with the customer on 18.08 in the morning
. running trial from 18.08 afternoon thru 8/23
26.06.2023 - MYV3250180 expedited. Exportation reference: E656
16.06.2023 after firing, process the pieces (X-ray and finishing and packing)
11.05.2023 mix rejuvenated
27.04.2023 mix rejected
19.01.2022 mix with contamination
22.12.2022 mix 1301 rejected
23.09.2022 tooling
08.12.2022 pieces rejected
27.06.2022 1st dwg
0 | 222 | null |  | 222 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-20 04:36 | 2023-05-26 21:14 | 12 | 12 | 9 | FALSE | 1a0047ba-6ab8-40ba-b54f-53a6561ac16c | null | FCVI-DURAFLEX1000L | BD73775 | Viso | 104816 | T A 2000 | Mexico | NAFTA | MY | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"dcfd968e-7ab9-4b2c-b66a-20f26d878fdc.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/dcfd968e-7ab9-4b2c-b66a-20f26d878fdc.jpeg","id":"6252cf0a-a7bc-4106-b59d-8178b5698493"} | Customer Name - TYASA 104816 | 2021-06-26 22:00 | 2022-02-09 23:00 | 2022-07-10 22:00 | 2022-07-25 22:00 | null | 2022-10-02 22:00 | 2022-11-03 23:00 | 2022-11-17 23:00 | null | null | null | null | null | null | null
11.07.2022 11 pcs pressed and cured, awaiting more production to glaze and fire
13.07/2022 2nd dwg
27.06.2021 1st dwg
0 | 223 | null |  | 223 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 15:18 | 2023-05-26 21:24 | 12 | 12 | 20 | FALSE | b3f2e3ca-a8eb-4d60-9d2d-8ab678c872e6 | null | FCVI-DURAFLEX5L | BC47912 | Viso | 121090 | CMC Steel Florida | USA | NAFTA | MY | 25 | α – Alpha | Manufacturing | {"type":"thumbnail","fileName":"04273d4c-d7f9-4f35-831a-26521be2acbd.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/04273d4c-d7f9-4f35-831a-26521be2acbd.jpeg","id":"f5981266-e7eb-47e4-a903-e710c39d0ecb"} | 01.09.2023 Interrupted pressing to check for lamination, X-Ray OK, 37 pcs pressed | 2022-05-10 22:00 | 2022-07-21 22:00 | 2023-05-24 22:00 | 2023-08-31 22:00 | null | null | null | null | null | 4. Wrong application conditions specified | null | 2.4. Properties Out of Spec | null | null | null
31.08.2023 last crate packed on August 5th 22 pcs MYV3320185
03.08. 2023 sales approved out of spec for can height, packing
27.07.2023 finished the x-ray? - 21 good pieces
26.06.2023 packed MYV3240182 - 8 pcs made with mix 1301. Remaining 17 pcs - pending press with mix 1301
25.05.2023 Pending to press, waiting for PI results test pots
11.05.2023 Pieces rejected
27.04.2023 mix rejected on thermite test
19.01.2023 mix 1283 rejected
14.03.2023 3rd dwg revision
26.06.2022 2nd dwg revision
11.05.2022 1st dwg
0 | 224 | null |  | 224 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 15:22 | 2023-05-26 21:32 | 12 | 12 | 16 | FALSE | 53689be2-eafe-4a3f-b316-b9712f077dad | null | FCVI-DURAFLEX1000H | BD73973 | Viso | 101904 | INLAND STEEL CO | USA | NAFTA | MY | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"892a05a3-22b0-44fe-b82c-1529d636c2e4.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/892a05a3-22b0-44fe-b82c-1529d636c2e4.jpeg","id":"ebaa7a53-1fa9-45ea-985d-b5b1cab28781"} | MYV3150016 | 2022-07-24 22:00 | 2022-11-24 23:00 | 2023-02-23 23:00 | 2023-04-13 22:00 | null | 2023-04-17 22:00 | 2023-08-09 22:00 | 2023-08-17 22:00 | null | null | null | 2.1. Lamination | null | null | null
BD73973 to BD75283
Trial - WK32 (1301IS461)
Pieces on site but very late and customer reluctant to run these now. CHV3150016
#1 - 101903 - to check MDM right number
GLAZING issues - to add to the list
25.07.2022 1st dwg
0 | 225 | null |  | 225 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-03-01 09:57 | 2023-05-30 07:54 | 12 | 259 | 21 | FALSE | 85bc52af-fab4-4023-8d4d-1b5314a8dd5f | null | FCVI-DURAFLEX20M | BD74252 | Viso | 200359 | TAMSA | Mexico | NAFTA | MY | 8 | α – Alpha | Pieces on Site | {"type":"thumbnail","fileName":"ae637e6a-52b4-4e68-b3b9-d5305913090e.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/ae637e6a-52b4-4e68-b3b9-d5305913090e.jpeg","id":"bd592c00-4592-497c-ac82-9dcd3facf2e4"} | 01.03.2024 Ready to ship. Waiting for trial of BD74252 to start. | 2022-08-29 22:00 | 2023-01-30 23:00 | 2023-03-23 23:00 | 2023-05-04 22:00 | null | 2023-05-11 22:00 | null | null | null | null | null | 2.4. Properties Out of Spec | null | null | null
18.09.2023 to be trialed together with BD74401
05.05.2023 metal can applied packed MYV3250112
02.05.2023 finishing of pieces completed by end of this week
21.04.2023 confirm that 8 good pieces are available
14.04.2023 mix 1301: fired properties and thermite of blend
24.03.2023 pressing start
03.03.2023 preparation of thermites and test pots
24.02.2023 rejuvenation of 1 ton
10.02.2023 share green properties
03.02.2023 re-blend mix
13.01.2023 rejuvenate the whole blend
09.12.2022 re-start pressing in week 51
02.12.2022 to start production
30.08.2022 1st dwg
0 | 226 | null |  | 226 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 12:08 | 2023-05-30 08:02 | 12 | 12 | 17 | FALSE | 5a5112bf-3b00-4643-9faf-45261cee1f02 | null | FCVI-DURAFLEX5M | BC47946 | Viso | 169742 | Big River Steel | USA | NAFTA | CH | 10 | α – Alpha | Pieces on Site | {"type":"thumbnail","fileName":"9f4d92ca-1bce-42d7-a4be-7a6743f1ac92.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/9f4d92ca-1bce-42d7-a4be-7a6743f1ac92.jpeg","id":"bac1e409-3fff-4ffd-b8cf-7182b5557b80"} | Customer loss of interest | 2022-11-13 23:00 | 2023-02-13 23:00 | 2023-02-23 23:00 | 2023-03-29 22:00 | null | 2023-04-30 22:00 | null | null | null | null | null | 2.3. XRAY Defects | null | 6. Customer Loss of Interest or Push for Trial | null
14.11.2022 2nd dwg revision
13.06.2022 1st dwg
0 | 227 | null |  | 227 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 15:26 | 2023-05-30 18:12 | 12 | 12 | 12 | FALSE | 953c5847-9b02-4139-8e66-e586a441d430 | null | FCVI-DURAFLEX5M | BD73437 | Viso | 480048 | VOESTALPINE LINZ 18000900 | Austria | Europe | CH | 60 | β – Beta | Complete | {"type":"thumbnail","fileName":"657ac664-3e09-410c-a84e-4f683702e5bd.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/657ac664-3e09-410c-a84e-4f683702e5bd.jpeg","id":"896d822c-1ff2-41ce-8867-da02eebd85b4"} | 02.05.2023 2nd dwg revision | 2023-01-23 23:00 | 2023-01-30 23:00 | 2023-02-13 23:00 | 2023-03-30 22:00 | null | 2023-04-20 22:00 | 2023-04-23 22:00 | 2023-05-25 22:00 | null | null | null | null | null | null | null
28.04.2022 1st dwg
0 | 228 | null |  | 228 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 12:15 | 2023-05-30 18:28 | 12 | 12 | 21 | FALSE | ce0eeaa9-2e4d-4827-9416-e5196a2d9c1c | null | FCVI-DURAFLEX5L | BC47029 | Viso | 150453 | Nucor Steel West Virginia | USA | NAFTA | MY | 42 | α – Alpha | Complete | {"type":"thumbnail","fileName":"adb5064e-6d73-4cdd-87e4-264bbb96c4d0.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/adb5064e-6d73-4cdd-87e4-264bbb96c4d0.jpeg","id":"2920cd4d-45ec-4e1d-88a4-44d5d0290611"} | 19.06.2023 MYV3240233 expedited. Exportation reference: E633 | 2022-08-26 22:00 | 2022-10-10 22:00 | 2023-05-24 22:00 | 2023-06-18 22:00 | null | 2023-06-29 22:00 | 2023-08-31 22:00 | 2023-09-14 22:00 | null | null | null | 2.2. Contamination | null | null | null
09.06.2023 X-ray of the 42 pcs share results
25.05.2023 Pending to press, waiting for PI results test pots
27.04.2023 mix rejected
22.12.2022 mix 1301 rejected
11.10.2022 PO Date = RFQ Date
27.08.2021 1st dwg
0 | 229 | null |  | 229 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 16:24 | 2023-05-30 19:27 | 12 | 12 | 23 | FALSE | 22f2103c-aa9d-45e7-929f-746e7cb4edb6 | null | FCVI-DURAFLEX5M | BC47003 | Viso | 104569 | Charter Steel Saukville | USA | NAFTA | MY | 20 | α – Alpha | Complete | {"type":"thumbnail","fileName":"43b7fcf6-c289-4a62-ac1e-ae992371af26.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/43b7fcf6-c289-4a62-ac1e-ae992371af26.jpeg","id":"a9faf638-ce35-42ea-b829-444bacdf8308"} | PATTERN !!! BC47052 | 2022-05-05 22:00 | 2023-01-30 23:00 | 2023-06-08 22:00 | 2023-08-03 22:00 | null | 2023-08-23 22:00 | 2023-09-13 22:00 | 2023-09-26 22:00 | null | null | null | 2.2. Contamination | null | null | null
Launch Code FCVI-TS01313
to check Trial Date
04.08.2023 crate nr: MYV3310202 16 pcs
03.08.2023 Packing
27.07.2023 still at insert application
20.07.2023 Pending for can station
06.07.2023 pressing in progress, one piece still to be pressed.
29.06.2023 Started pressing
28.06.2023 XC rings on site. JDE order - issues
26.06.2023 mix 1283 blend 30212 rejuvenated approved
25.05/08.06/22.06.2023 Pending to press, waiting for PI results test pots
06.05.2022 2nd dwg revision
01.09.2021 1st dwg
0 | 230 | null |  | 230 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 12:15 | 2023-05-30 20:35 | 12 | 12 | 20 | FALSE | 38d9f6f0-e4d3-4cc7-8a90-d01cfecd20a9 | null | FCVI-DURAFLEX5L | BC48233 | Viso | 150453 | Nucor Steel West Virginia | USA | NAFTA | MY | 42 | β – Beta | Complete | {"type":"thumbnail","fileName":"8be826e5-bcb0-4f19-a09e-0201f348e0ce.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/8be826e5-bcb0-4f19-a09e-0201f348e0ce.jpeg","id":"ef741d1e-e63b-4390-b702-83d4e907ee23"} | 07.11.2023 MYV3450143 42 pcs | 2022-08-29 22:00 | 2022-11-09 23:00 | 2023-06-06 22:00 | 2023-07-16 22:00 | null | 2023-07-27 22:00 | 2023-08-08 22:00 | 2023-08-24 22:00 | null | null | null | 2.2. Contamination | null | null | null
27.10.2023 to continue pressing. Fire and X-ray. Must ship at least one crate ASAP
20.10.2023 Xray the pieces
13.10.2023 Xrays ASAP after firing
29.09.2023 Blend 33507 approved for pressing
08.09.2023 instructions for HPHF
31.08.2023 to start pressing again
20.07.2023 42 pcs MYV3290156
06.07.2023 pressed
26.06.2023 pending X-rays, results
22.06.2023 in pressing room
08.06.2023 waiting for approved mix 1301, on thermite test, need to be rejuvenated
13.04.2023 waiting for approved mix 1301
19.01.2023 mix with contamination
22.12.2022 mix 1301 rejected
10.11.2022 PO
30.08.2022 1st dwg
0 | 231 | null |  | 231 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 09:39 | 2023-05-31 17:25 | 12 | 12 | 8 | FALSE | ae8ed7b5-c2ef-4c07-8018-26a1c7164463 | null | FCVI-DURAFLEX5M | BD75143 | Viso | 135280 | PEINER TR. PEINE 11750500 | Germany | Europe | TC | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"ad296ebf-9728-4ce6-8ce7-395999e4c47e.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/ad296ebf-9728-4ce6-8ce7-395999e4c47e.jpeg","id":"4d5d0ed5-9f9d-4888-9865-5d3b64a68a85"} | Ready for shipment Date | 2023-01-31 23:00 | 2023-11-01 23:00 | 2023-11-22 23:00 | 2023-12-06 23:00 | null | 2023-12-11 23:00 | 2023-12-13 23:00 | 2023-12-20 23:00 | null | null | null | null | null | null | null
PO Date
1st dwg 01.02.2023
0 | 232 | null |  | 232 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 11:29 | 2023-06-01 07:34 | 12 | 12 | 9 | FALSE | 4f277f22-d26c-48f8-b6a0-96d6233290aa | null | FCVI-DURAFLEX1000L | BC47995 | Viso | 113334 | FERROSTAL | Poland | Europe | TC | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"21498162-66eb-408b-849d-66b2b6d2dee6.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/21498162-66eb-408b-849d-66b2b6d2dee6.jpeg","id":"23874f41-ccb7-4119-aa78-3a4ad191fbd0"} | to check PO Date | 2022-06-27 22:00 | 2023-02-01 23:00 | 2023-04-26 22:00 | 2023-05-23 22:00 | null | 2023-08-02 22:00 | 2023-09-06 22:00 | 2023-09-20 22:00 | null | null | null | 2.1. Lamination | null | null | null
to check Trial Date
24.05.2023 produced in TC last week 21 but lamination on X ray confirmed today / no go for shipment – currently solving next steps
28.06.2022 1st dwg
0 | 233 | null |  | 233 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-03-06 14:27 | 2023-06-01 11:34 | 12 | 259 | 16 | FALSE | 679d4251-b0a1-400b-ad10-222c4bdac3e3 | null | FCVI-DURAFLEX20L | BD75515 | Viso | 100486 | DALMINE ACCIAIERIE SPA (CC1) | Italy | Europe | TC | 10 | β – Beta | Manufacturing | {"type":"thumbnail","fileName":"74f6a63e-78bb-4556-adf4-ba8e33723919.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/74f6a63e-78bb-4556-adf4-ba8e33723919.jpeg","id":"638ae3a6-8d69-4132-a162-1fa602d2be2b"} | Feb 24: Pieces pending for trial, maybe week 8 will start but not confirmed | 2023-04-11 22:00 | 2023-05-04 22:00 | 2023-05-11 22:00 | 2023-07-13 22:00 | null | null | null | null | null | null | null | null | null | null | null
Jan 24: pieces on site. Waiting for trial. Not expected to have follow-up trial due to high price
24.05.2023 produced in TC last week but lamination on X ray confirmed today / no go for shipment – currently solving next steps with Paolo
0 | 235 | null |  | 235 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 09:39 | 2023-06-07 13:49 | 12 | 12 | 7 | FALSE | 54150dd8-686e-4678-a0b7-4d9a0ef2886e | null | FCSR-CDT3292 | KA75040065 | Slidegate Assy. | 151200 | Aperam Châtelet | Belgium | Europe | SR | 80 | α – Alpha | Complete | {"type":"thumbnail","fileName":"4c7ce3c4-b1c9-43cd-9830-a5c242e5af0d.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/4c7ce3c4-b1c9-43cd-9830-a5c242e5af0d.jpeg","id":"f78facf2-1105-4820-986a-117deece6331"} | 3361/3292 confirmed to ship week 26 | 2023-03-29 22:00 | 2023-04-05 22:00 | 2023-06-05 22:00 | 2023-06-29 22:00 | null | 2023-07-06 22:00 | 2023-07-20 22:00 | 2023-08-24 22:00 | null | null | null | null | null | null | null
06.06.2023 pressed and are in impregnation
PO Date~RFQ Date to check
06.05.2022 1st dwg
0 | 236 | null |  | 236 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 09:40 | 2023-06-07 13:53 | 12 | 12 | 8 | FALSE | 768a108c-87fb-44aa-bde9-8575e7297743 | null | FCVI-SHARKSKIN | BZ45590 | Viso | 148933 | Hyundai Dangjin 3 | South Korea | North Asia | SR | 10 | α – Alpha | Manufacturing | {"type":"thumbnail","fileName":"ebf583b8-056f-4c0b-afd2-7fdffa52a22f.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/ebf583b8-056f-4c0b-afd2-7fdffa52a22f.jpeg","id":"8d3750b5-d054-496b-be82-38a2c619f961"} | to check Customer Name !! | 2023-01-04 23:00 | 2023-12-05 23:00 | 2024-01-03 23:00 | 2024-06-05 22:00 | null | null | null | null | null | null | null | null | null | null | null
Mfg Date
PO Date
05.01.2023 2nd dwg revision
24.02.2021 1st dwg
0 | 237 | null |  | 237 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 14:17 | 2023-06-07 14:37 | 12 | 12 | 14 | FALSE | 37b2bb3e-f2dc-472c-a113-c542eda5f0ec | null | FCSR-LTECH | TKA71494065 | Slidegate Assy. | 151200 | Aperam Châtelet | Belgium | Europe | SR | 160 | β – Beta | Complete | {"type":"thumbnail","fileName":"1bff0b42-0ee9-4b59-ad00-3e76c52a2027.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/1bff0b42-0ee9-4b59-ad00-3e76c52a2027.jpeg","id":"ac91e53e-a6a1-4614-b72c-763d474df745"} | Trial Date - to check (Benjamin / Martin) | 2023-04-25 22:00 | 2023-05-14 22:00 | 2023-06-29 22:00 | 2023-08-24 22:00 | null | 2023-09-17 22:00 | 2023-10-01 22:00 | 2023-10-19 22:00 | null | null | null | null | null | null | null
25.08. 2023 in transit SR3340013; SR3340014
22.08.2023 packed 160pcs
29.05.2020 1st dwg
560 pcs in total production schedule
first 80 pcs - PO 15.05.2023 + 320 pcs 07.06.2023 + pcs - 160 pcs - PO 17.07.2023
160 pcs [current kiln 5th - pressed WK28, fired WK29/30, impregnation WK31/32, target WK34]+ 240 pcs [next kiln - 6th - WK35 to start pressing] optionally +80 pcs and then 80 pcs for 7th kiln
checked by Joanna G.
0 | 238 | null |  | 238 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 09:41 | 2023-06-07 14:49 | 12 | 12 | 6 | FALSE | 82012f46-5a9f-4b40-99df-9f355b8f01a3 | null | FCVI-CALW | BP76276 | Viso | 148933 | Hyundai Dangjin 3 | South Korea | North Asia | SR | 10 | α – Alpha | Manufacturing | {"type":"thumbnail","fileName":"f9e24ce8-e6ae-4226-8bb9-601eff6c1437.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/f9e24ce8-e6ae-4226-8bb9-601eff6c1437.jpeg","id":"f10a7fa9-1895-4f6f-8033-fff9605684d1"} | NPI L2: Winged Stopper - N.ASIA | 2023-03-19 23:00 | 2023-08-15 22:00 | 2023-08-18 22:00 | 2023-08-22 22:00 | null | null | null | null | null | null | null | null | null | null | null
16.08.2023 - PO from Abhi
31.08.2023
- pending TRF/ NPR/ COMPONENTS
0 | 239 | null |  | 239 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 15:31 | 2023-06-07 14:57 | 12 | 12 | 7 | FALSE | 9e446fcd-1500-4432-8c36-a31812a3e5d2 | null | FCVI-SSLINER | BZ47323 | Viso | 112896 | QINGDAO IRON + STEEL GENERAL | China | China | SZ | 10 | α – Alpha | PO | {"type":"thumbnail","fileName":"3b7ab04a-04ac-4fc5-ac76-50caa17f28e8.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/3b7ab04a-04ac-4fc5-ac76-50caa17f28e8.jpeg","id":"33068f32-4870-497e-9e8f-423e6337997f"} | Tool Date - to confirm | 2023-06-06 22:00 | 2023-07-05 22:00 | 2023-09-28 22:00 | null | null | null | null | null | null | null | null | null | null | null | null
28.09.2021 1st dwg
0 | 240 | null |  | 240 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-07-19 17:54 | 2023-06-07 15:04 | 12 | 38 | 5 | FALSE | c73c7678-d037-4553-a276-b56cf0c94118 | null | FCVI-DURASLEEVE-LONG | BF98702 | Viso | 430206 | HUACHIPATO | Chile | South America | RJ | 10 | α – Alpha | Tool | {"type":"thumbnail","fileName":"e26a116e-73cc-4649-80fc-1dc5dce00dee.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/e26a116e-73cc-4649-80fc-1dc5dce00dee.jpeg","id":"33714438-3bc1-4690-95c8-4944ad585f55"} | mix 1297 to be shipped from CH - WK26 | 2022-09-07 22:00 | 2023-02-14 23:00 | 2023-06-29 22:00 | null | null | null | null | null | 2023-07-01 22:00 | null | 5. Raw materials delay (e.g., mix delay) | null | null | null | null
existing tooling to be used
Confirmed, no tooling request received AMM 19/07/2023
0 | 241 | null |  | 241 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 15:32 | 2023-06-07 15:07 | 12 | 12 | 11 | FALSE | 2bfea021-2699-4d26-8115-d2fe4b84f905 | null | FCVI-DURASLEEVE-LONG | BF98553 | Viso | 103871 | GERDAU CHARQUEADAS | Brazil | South America | RJ | 30 | α – Alpha | Complete | {"type":"thumbnail","fileName":"90ec86ad-1efc-4602-b17e-6607185f24e4.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/90ec86ad-1efc-4602-b17e-6607185f24e4.jpeg","id":"26f529e1-e029-472c-a34f-9570fbe2040a"} | (** No tooling order, I see Rio has produced back in Feb 2023 so possibly used existing tooling. ** AMM) | 2022-08-17 22:00 | 2023-02-09 23:00 | 2023-03-30 22:00 | 2023-05-08 22:00 | null | 2023-05-15 22:00 | 2023-05-30 22:00 | 2023-06-14 22:00 | null | null | null | null | null | null | null
waiting Trial Report - 6 pcs used (3 tundish) - good results - good erosion rate with short sequences (2-3 heats) targeting 8 heats, WK26 to continue
0 | 242 | null |  | 242 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 15:32 | 2023-06-07 15:15 | 12 | 12 | 11 | FALSE | 16353232-87cb-403c-865d-ad0e9921ce18 | null | FCVI-DURASLEEVE-FLAT | BZ49899 | Viso | 164080 | USIMINAS | Brazil | South America | RJ | 20 | α – Alpha | Complete | {"type":"thumbnail","fileName":"50c30f7e-2557-40d6-802a-394736655897.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/50c30f7e-2557-40d6-802a-394736655897.jpeg","id":"29be9b07-095f-4b9f-a5ce-7d171dee6526"} | (** No tooling order ** AMM) | 2023-01-17 23:00 | 2023-02-21 23:00 | 2023-04-27 22:00 | 2023-06-13 22:00 | null | 2023-06-20 22:00 | 2023-08-14 22:00 | 2023-09-04 22:00 | null | null | null | null | null | null | null
existing tooling
all stock mix 1297 used
Field Trial Plan in August
18.01.2023 1st dwg
0 | 243 | null |  | 243 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 15:33 | 2023-06-07 15:25 | 12 | 12 | 7 | FALSE | cb4472b5-97f2-44db-b221-788c4588c752 | null | FCVI-DURASLEEVE-FLAT | BK63663 | Viso | 152564 | CMC Steel Arizona | USA | NAFTA | SR | 42 | α – Alpha | Complete | {"type":"thumbnail","fileName":"2391388f-f81f-4e58-8cab-15af17fe8ff7.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/2391388f-f81f-4e58-8cab-15af17fe8ff7.jpeg","id":"29f7279d-822a-49bc-a7aa-465104a7b738"} | PATTERN !!! BK63739 | 2022-11-28 23:00 | 2023-01-16 23:00 | 2023-02-02 23:00 | 2023-02-09 23:00 | null | 2023-02-16 23:00 | 2023-03-01 23:00 | 2023-04-13 22:00 | null | null | null | null | null | null | null
Launch Code: FCVI-TS01313
MYV3400194
[17.10.2023 CCAR:Thermacoat is cracking off preheat to start cast]
29.11.2022 1st dwg
0 | 244 | null |  | 244 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-02-21 12:03 | 2023-06-07 15:34 | 12 | 12 | 10 | FALSE | 76cacfb9-b949-4f24-a6fd-762f53cec8b6 | null | FCVI-BIONIC | BK62624 | Viso | 135953 | Nucor Steel Sedalia | USA | NAFTA | SR | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"0fe82334-7d0b-4577-a107-5e2d2b46e4fc.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/0fe82334-7d0b-4577-a107-5e2d2b46e4fc.jpeg","id":"bebd76cd-8da0-4ab0-a42a-1cefb25b8826"} | 07.10.2022 4th dwg revision | 2022-10-02 22:00 | 2022-10-09 22:00 | 2022-10-20 22:00 | 2022-11-23 23:00 | null | 2023-01-09 23:00 | 2023-01-15 23:00 | 2023-01-19 23:00 | null | null | null | null | null | null | null
03.08.2022 3rd dwg revision
18.07.2022 2nd dwg revision
14.02.2022 1st dwg
0 | 245 | null |  | 245 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-07-04 10:09 | 2023-06-07 15:48 | 12 | 12 | 16 | FALSE | d83a1101-614f-4e83-b4f3-c6b02e66fb82 | null | FCSR-LTECH | KA70769060 | Slidegate Assy. | 158099 | JSL(HISSAR) | India | India | SR | 80 | β – Beta | Complete | {"type":"thumbnail","fileName":"92f6f4ba-fb80-45bb-ab42-3b65df7e4a1b.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/92f6f4ba-fb80-45bb-ab42-3b65df7e4a1b.jpeg","id":"22a21aa6-b049-48d2-9b15-0d24b93095dc"} | Trial Date - to check | 2023-03-15 23:00 | 2023-06-11 22:00 | 2023-07-27 22:00 | 2023-09-11 22:00 | null | 2023-10-29 23:00 | 2024-01-22 23:00 | 2024-02-06 23:00 | null | null | null | null | null | null | null
Delivery Date - to check
12.09.2023 shipped to customer
04.09.2023 transferred to Kokotow
01.09.2023 80pcs packed SR3356312
01.09.2023 packing mid of week 36
23.08.2023 pending assembly
29.03.2023 PO send for 40pcs
12.06.2023 PO send for additional 40pcs
16.03.2023 - 1st dwg
Customer Name to check with Sudip
0 | 246 | null |  | 246 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 09:41 | 2023-06-09 16:11 | 12 | 12 | 7 | FALSE | ae107365-9a6c-4837-a148-faacca9f777f | null | FCVI-TS01292 | BK63051 | Viso | 135748 | ArcelorMittal WARSZAWA | Poland | Europe | SR | 10 | α – Alpha | RFQ | {"type":"thumbnail","fileName":"97869349-c8ab-4332-acf1-98cf9eebc9e0.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/97869349-c8ab-4332-acf1-98cf9eebc9e0.jpeg","id":"9c55cf06-cc2d-4c56-ab94-0eb0fe097334"} | PATTERN !!! BK56535 - no Launch Code in MDM - VFIT BK | 2023-02-28 23:00 | null | null | null | null | null | null | null | null | null | null | null | null | null | null
17.09.2018 1st dwg
0 | 247 | null |  | 247 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 09:41 | 2023-06-09 16:16 | 12 | 12 | 6 | FALSE | d99c23a2-1888-4e03-80e0-10f553abfd93 | null | FCVI-TS01292 | BK63069 | Viso | 135748 | ArcelorMittal WARSZAWA | Poland | Europe | SR | 10 | β – Beta | RFQ | {"type":"thumbnail","fileName":"2e642814-777f-4f59-9520-70d073f4c8b1.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/2e642814-777f-4f59-9520-70d073f4c8b1.jpeg","id":"64dded05-aa34-4abb-93ba-31054fdb6481"} | PATTERN !!! BK45439 - no Launch Code in MDM | 2023-05-31 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null | null
07.05.2013 1st dwg
0 | 248 | null |  | 248 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-02-21 12:03 | 2023-06-19 07:13 | 36 | 12 | 7 | FALSE | d625b765-bbc5-4482-87e3-0f076a20b0d1 | null | FCVI-BIONIC | BK62624 | Viso | 135953 | Nucor Steel Sedalia | USA | NAFTA | MY | 10 | β – Beta | Complete | {"type":"thumbnail","fileName":"eb34f45c-56cc-49e3-a51b-608135641d58.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/eb34f45c-56cc-49e3-a51b-608135641d58.jpeg","id":"1d9ad320-13dc-46bb-bc6c-b67fa978c3b7"} | Tooling was duplicated and is available in MY. | 2022-02-13 23:00 | 2022-03-03 23:00 | 2022-05-03 22:00 | 2022-06-24 22:00 | null | 2022-09-14 22:00 | 2022-09-28 22:00 | 2022-10-13 22:00 | null | null | null | null | null | null | null
Initial 10 pcs order placed by GH lab end of May.
At 16th of June MY had however not recevied the order yet. ROADBLOCK to schedule the pattern production.
Tooling part to populate by Allan.
07.10.2022 4th dwg revision
03.08.2022 3rd dwg revision
18.07.2022 2nd dwg revision
14.02.2022 1st dwg
0 | 249 | null |  | 249 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 15:34 | 2023-06-19 19:57 | 12 | 12 | 8 | FALSE | cc1f0066-5d70-457e-bb49-8f094142b5e9 | null | FCVI-DURASLEEVE-LONG | BF98918 | Viso | 430367 | SIDERCA | Argentina | South America | RJ | 20 | α – Alpha | Pieces on Site | {"type":"thumbnail","fileName":"addda31c-fcd1-47cd-8fbf-25c76131ef92.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/addda31c-fcd1-47cd-8fbf-25c76131ef92.jpeg","id":"40824fb3-5e2d-4409-8992-041b9a524fbb"} | Trial Plan ? | 2022-09-28 22:00 | 2023-04-04 22:00 | 2023-04-18 22:00 | 2023-05-07 22:00 | null | 2023-06-29 22:00 | null | null | null | null | null | null | 2. Logistics issues | null | null
2 patterns - this is for CC2
30.06.2023 pcs arrived
21.06.2023 shipped - not arrived - Custom problems - at the warehouse waiting for Customs aproval to go
08.05.2023 manufactured
0 | 250 | null |  | 250 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-08-31 18:37 | 2023-06-19 20:04 | 12 | 12 | 6 | FALSE | e570635f-0b86-49cc-8fb7-8b8416ecd9b2 | null | FCVI-DURASLEEVE-LONG | BF99999 | Viso | 430367 | SIDERCA | Argentina | South America | RJ | 10 | α – Alpha | Tool | {"type":"thumbnail","fileName":"1e78c7e7-949d-4d40-8c65-86a19c45198c.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/1e78c7e7-949d-4d40-8c65-86a19c45198c.jpeg","id":"d07dd842-2521-460c-a6e8-ad828f725309"} | PATTERN - BF99478 - no Launch Code in MDM | 2022-11-28 23:00 | 2023-04-09 22:00 | 2023-06-22 22:00 | null | null | null | null | null | 2023-06-24 22:00 | null | null | null | null | null | null
2 patterns - this is for CC3
Tooling ETA - WK25
(** Tooling order received 22/03/2023 ** AMM)
(** Tooling available ex Hyspec 20/04/2023 ** AMM)
0 | 251 | null |  | 251 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 15:34 | 2023-06-19 20:12 | 12 | 12 | 10 | FALSE | 6c488532-7b6d-4c37-b8a3-edb2016b9635 | null | FCVI-DURASLEEVE-LONG | BF95161 | Viso | 101763 | GERDAU PINDAMONHANGABA | Brazil | South America | CH | 20 | α – Alpha | Complete | {"type":"thumbnail","fileName":"a6785e5d-ce6a-4118-b9a9-33421e8624db.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/a6785e5d-ce6a-4118-b9a9-33421e8624db.jpeg","id":"b3285270-9df9-4922-9268-73c03ca40799"} | 2 patterns - different processes - high pressure made in CH | 2022-01-09 23:00 | 2022-01-16 23:00 | 2022-03-29 22:00 | 2022-05-24 22:00 | null | 2022-07-28 22:00 | 2023-05-14 22:00 | 2023-06-06 22:00 | null | null | null | null | null | null | null
pieces on site - one year
waiting for Field Trial Report - positive results, all three grades checked (H, M, L Carbon) - 30% improvement
24.05.2021 1st dwg
0 | 252 | null |  | 252 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 16:04 | 2023-06-19 20:17 | 12 | 12 | 8 | FALSE | 35026c5c-fa06-4f60-b5f8-c37cde6b3ebe | null | FCVI-DURASLEEVE-LONG | BF95153 | Viso | 101763 | GERDAU PINDAMONHANGABA | Brazil | South America | CH | 10 | β – Beta | Complete | {"type":"thumbnail","fileName":"860c7db0-072a-4f65-adb1-b2c192d92961.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/860c7db0-072a-4f65-adb1-b2c192d92961.jpeg","id":"57008d18-b243-4819-8f12-d6e070c64dd4"} | 2 patterns - different processes - high pressure made in CH | 2022-01-17 23:00 | 2022-01-24 23:00 | 2022-04-03 22:00 | 2022-06-29 22:00 | null | 2022-07-26 22:00 | 2023-05-30 22:00 | 2023-06-06 22:00 | null | null | null | null | null | null | null
pieces on site - one year
waiting for Field Trial Report - positive results, all three grades checked (H, M, L Carbon) - 30% improvement
24.05.2021 1st dwg
0 | 253 | null |  | 253 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 16:08 | 2023-06-19 20:19 | 12 | 12 | 11 | FALSE | 3d241a9e-35e7-4ea4-a813-64f4319ce976 | null | FCVI-DURASLEEVE-FLAT | BF00802 | Viso | 156474 | TERNIUM BRASIL | Brazil | South America | RJ | 20 | α – Alpha | Complete | {"type":"thumbnail","fileName":"09c47007-a4ac-415b-b554-c1520b770138.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/09c47007-a4ac-415b-b554-c1520b770138.jpeg","id":"0ff80b43-9aa4-47f1-b802-c90139636481"} | PATTERN !!! BF80569 (current) | 2023-05-02 22:00 | 2023-05-09 22:00 | 2023-05-16 22:00 | 2023-06-06 22:00 | null | 2023-06-13 22:00 | 2023-07-25 22:00 | 2023-08-07 22:00 | null | null | null | null | null | null | null
RFQ submited - pending
1 crate extra under regular order
Trial Plan in July
0 | 254 | null |  | 254 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-02 09:32 | 2023-06-19 20:30 | 12 | 12 | 9 | FALSE | 795f0e80-7ea7-485c-b2ff-a687624cbfbc | null | FCVI-DURASLEEVE-FLAT | BF99825 | Viso | 107118 | ACESITA/STL PLT 1 | Brazil | South America | RJ | 20 | α – Alpha | Complete | {"type":"thumbnail","fileName":"28e470f0-2d53-41d4-8a00-b41fa147ec2b.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/28e470f0-2d53-41d4-8a00-b41fa147ec2b.jpeg","id":"da45a081-24b5-433b-b0cf-815cfbd28fcf"} | Trial Date ? | 2023-01-18 23:00 | 2023-01-31 23:00 | 2023-04-03 22:00 | 2023-06-13 22:00 | null | 2023-06-22 22:00 | 2023-07-02 22:00 | 2023-07-20 22:00 | null | null | null | null | null | null | null
Trial Plan Date - 1st week of July -WK27 (specific steel grades)
existing tooling, but mix 1297 delivery
0 | 255 | null |  | 255 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-10-10 10:34 | 2023-06-20 07:30 | 12 | 12 | 15 | FALSE | 682b1041-5cd8-47df-8617-769a1903d0f0 | null | FCSR-SURFCDT | KA73102040 | Slidegate Assy. | 911012 | Mexico C/O Vesuvius USA | USA | NAFTA | SR | 100 | α – Alpha | Complete | {"type":"thumbnail","fileName":"1673e105-883c-411a-bf91-8be515ea4e98.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/1673e105-883c-411a-bf91-8be515ea4e98.jpeg","id":"6d8f3891-4696-4216-920d-a77d1915d5cc"} | 01.2024 on side? - to check with Travis | 2023-05-09 22:00 | 2023-05-16 22:00 | 2023-06-29 22:00 | 2023-08-21 22:00 | null | 2024-01-03 23:00 | 2024-03-06 23:00 | 2024-04-17 22:00 | null | null | null | null | null | null | null
12.2023 MY production
03.11.2023 arrived to MY
31.08.2023 shipped to customer
24.08.2023 transferred to Kokotow
22.08.2023 104pcs packed SR3345559
Customer to be checked !!!
PGB0011000 - LG31 - PO for VES MEXICO - 17.05.2023
current kiln 5th - pressed WK28, fired WK29/30, impregnation WK31/32, packing ongoing WK33
23.08.2023 packed 104pcs
31.03.2021 1st dwg
checked by Joanna G.
0 | 256 | null |  | 256 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-29 19:43 | 2023-06-21 15:04 | 12 | 12 | 4 | FALSE | 3663b4b1-a33a-4b42-84de-46fbfc908b01 | null | FCVI-DURASLEEVE-FLAT | BZ44668 | Viso | 180480 | CSP-COMPANHIA SIDERURGICA DO PECEM | Brazil | South America | RJ | 20 | α – Alpha | Manufacturing | {"type":"thumbnail","fileName":"fc8d4ca9-f8bb-41b5-a740-35ddfce49890.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/fc8d4ca9-f8bb-41b5-a740-35ddfce49890.jpeg","id":"f27a7609-a717-4137-b273-f2133b08d4a1"} | pending RFQ - submitted 10.05.2023 | 2023-05-09 22:00 | 2023-06-25 22:00 | 2023-07-19 22:00 | 2023-09-06 22:00 | null | null | null | null | null | null | null | null | null | null | null
Customer change to AM Pecem
existing tooling - BZ40427
mix 1297 to be shipped from CH - 1MT in WK26
1st dwg
0 | 257 | null |  | 257 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 09:41 | 2023-06-21 15:14 | 12 | 12 | 6 | TRUE | 7ab81fa1-fb7d-44da-9afc-200dd6886634 | null | FCVI-DURAFLEX5L | BD75473 | Viso | 107118 | ACESITA/STL PLT 1 | Brazil | South America | RJ | 30 | β – Beta | RFQ | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][7]_[BD75473][1]_[2].jpg"} | pending PO | 2023-05-08 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null | null
Revise RFQ date + dwg loading
New tooling - new design with thickness modification covered by this pattern, previous one was BD73163 (8 heats), target 10 heats max
09.05.2023 1st dwg
0 | 258 | null |  | 258 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-20 03:18 | 2023-06-21 15:38 | 12 | 12 | 5 | FALSE | 20828d8b-7d6a-450a-b84e-8a4c313ce7a9 | null | FCVI-DURAFLEX5L | BC48159 | Viso | 100035 | Acindar SA | Argentina | South America | RJ | 20 | α – Alpha | PO | {"type":"thumbnail","fileName":"2ffc3203-d654-4530-8417-8867904aa3c1.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/2ffc3203-d654-4530-8417-8867904aa3c1.jpeg","id":"88dea4fc-e8c3-4e4b-b80c-9e6aa7e9e1d9"} | 02.06.2023 pending PO - to confirm | 2022-08-02 22:00 | 2023-07-06 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null
0 | 259 | null |  | 259 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-06-21 15:52 | 2023-06-21 15:40 | 12 | 12 | 3 | FALSE | a0f3c905-a762-4547-8ca5-3c005d591189 | null | FCVI-DURAFLEX20L | BD75242 | Viso | 430367 | SIDERCA | Argentina | South America | RJ | 20 | β – Beta | RFQ | {"type":"thumbnail","fileName":"061b98cb-d2c1-4a48-b422-1cd2ef7193ec.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/061b98cb-d2c1-4a48-b422-1cd2ef7193ec.jpeg","id":"be58f0c5-bdd9-46a1-b4e9-f89cad0a15d0"} | pending PO | 2023-01-31 23:00 | null | null | null | null | null | null | null | null | null | null | null | null | null | null
0 | 260 | null |  | 260 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 15:35 | 2023-06-27 15:13 | 12 | 12 | 6 | FALSE | 0ff0d577-2109-4195-a529-e3dffc4b5b6c | null | FCVI-TS01267 | BC48092 | Viso | 101234 | Gerdau Monroe | USA | NAFTA | MY | 30 | α – Alpha | Manufacturing | {"type":"thumbnail","fileName":"1eed01bf-cdaf-41ae-bafb-b5a5baecf64f.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/1eed01bf-cdaf-41ae-bafb-b5a5baecf64f.jpeg","id":"a5f967df-4538-4d5f-bbc4-042d28654a08"} | to check PO Date | 2022-07-24 22:00 | 2023-02-28 23:00 | 2023-04-25 22:00 | 2023-06-25 22:00 | null | null | null | null | null | null | null | null | null | null | null
*26.06.2023 - not enough mix for 30 pcs - 28 pcs with 1324, 2 pcs remaining to pressed with 1267
0 | 261 | null |  | 261 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-10-14 07:08 | 2023-06-27 15:35 | 12 | 116 | 10 | FALSE | 77a677c2-a838-410b-a438-22c5e6064d88 | null | FCSR-SURFCDT | KA76196050 | Slidegate Assy. | 200099 | Gerdau Whitby - USD | Canada | NAFTA | SR | 40 | α – Alpha | Pieces on Site | {"type":"thumbnail","fileName":"35f179f6-2a03-44d9-8f3e-32c548ceff41.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/35f179f6-2a03-44d9-8f3e-32c548ceff41.jpeg","id":"29542802-cf86-4a2d-a72b-6ba6d22e0a72"} | SK02984000 raw plate | 2022-08-29 22:00 | 2023-05-21 22:00 | 2023-05-21 22:00 | 2023-11-01 23:00 | null | 2024-01-13 23:00 | null | null | null | null | null | null | null | null | null
16.11.2023 shipped
02.11.2023 44pcs packed SR3445686
JDE Request Made - 17.04.2023
JDE set-up completed - 29.05.2023
Internal Orders placed - Not yet, WL set-up not complete, hopefully WK26
22.05.2023 PO placed
30.08.2023 1st dwg
0 | 262 | null |  | 262 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-10-14 07:07 | 2023-06-27 15:46 | 12 | 116 | 8 | FALSE | 512d34a9-54dc-4c1c-8d82-7f2652db35a7 | null | FCSR-SURFCDT | KK32601050 | Slidegate Assy. | 200099 | Gerdau Whitby - USD | Canada | NAFTA | SR | 40 | α – Alpha | Pieces on Site | {"type":"thumbnail","fileName":"5de2bfbc-b62a-4a37-8fbe-0accdc7abfea.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/5de2bfbc-b62a-4a37-8fbe-0accdc7abfea.jpeg","id":"f842b17e-8cd7-42be-a2e9-f72a6b5f8e32"} | SK05508000 raw plate | 2023-04-16 22:00 | 2023-05-21 22:00 | 2023-05-21 22:00 | 2023-11-11 23:00 | null | 2024-01-13 23:00 | null | null | null | null | null | null | null | null | null
16.11.2023 shipped
12.11.2023 43pcs packed SR3465057
JDE Request Made - 17.04.2023
JDE set-up completed - 13.06.2023
Internal Orders placed - Not yet, WL set-up not complete, hopefully WK26
22.05.2023 PO placed
17.04.2023 1st dwg
0 | 263 | null |  | 263 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-04-25 07:50 | 2023-06-27 15:54 | 12 | 12 | 25 | FALSE | 36cde016-72e7-4067-89c3-88cb09050156 | null | FCSR-LTECH | KA77392050 | Slidegate Assy. | 200099 | Gerdau Whitby - USD | Canada | NAFTA | SR | 45 | α – Alpha | Pieces on Site | {"type":"thumbnail","fileName":"cf808b2f-f117-4ba4-9e7d-6f6cc29f3e20.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/cf808b2f-f117-4ba4-9e7d-6f6cc29f3e20.jpeg","id":"8ab67ed9-6b1a-4a68-87a7-441541bc3f8c"} | Trial Date - to check | 2023-04-06 22:00 | 2023-06-25 22:00 | 2023-09-20 22:00 | 2023-11-15 23:00 | null | 2024-02-14 23:00 | null | null | null | null | null | null | null | null | null
in transit
16.11.2023 45pcs shipped
23.10.2023 45pcs packed SR3435178
17.10.2023 45pcs impregnation, pending design confimation about crate
04.10.2023 47pcs fired
21.09.2023 47pcs pressed
21.09.2023 pressing week 38
for 6th kiln (WK37?)
26.06.2023 PO
SK05482000 raw plate
JDE Request Made - 17.04.2023
JDE set-up completed - 29.05.2023
Internal Orders placed - WL set-up not complete WK26
07.04.2023 1st dwg
checked by Joanna G.
0 | 264 | null |  | 264 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-04-25 08:46 | 2023-06-27 15:58 | 12 | 12 | 23 | FALSE | 1875cd54-4cc6-40e6-a6b1-866179d1ac9f | null | FCSR-LTECH | KK32619050 | Slidegate Assy. | 200099 | Gerdau Whitby - USD | Canada | NAFTA | SR | 50 | α – Alpha | Pieces on Site | {"type":"thumbnail","fileName":"39a1a5cc-2e5a-4bca-9d17-3d3776dfa0c8.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/39a1a5cc-2e5a-4bca-9d17-3d3776dfa0c8.jpeg","id":"f00b3bb3-054a-4114-b506-1702e1b966cc"} | 02.2024 trial date - to check | 2023-04-16 22:00 | 2023-06-25 22:00 | 2023-09-20 22:00 | 2023-11-15 23:00 | null | 2024-01-31 23:00 | null | null | null | null | null | null | null | null | null
in transit
16.11.2023 50pcs shipped
05.11.2023 packing 50pcs SR3455093
18.10.2023 pending impregnation, pending design confirmation about crate
04.10.2023 34pcs fired
26.09.2023 43pcs pressed
21.09.2023 pressing week 38
26.06.2023 PO
For 6th kiln (WK37?)
SK03487000 raw plate
JDE Request Made - 17.04.2023
JDE set-up completed - 13.06.2023
Internal Orders placed - Not yet, WL set-up not complete, hopefully WK26
17.04.2023 1st dwg
checked by Joanna G.
0 | 265 | null |  | 265 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 15:36 | 2023-06-30 12:45 | 36 | 12 | 10 | FALSE | dbd93095-39d7-48a3-83c7-2b4dafca51a4 | null | FCVI-TS01303 | BF99502 | Viso | 100850 | TERNI ACCIAI SPEC SPA | Italy | Europe | TC | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"69622abe-509f-4d57-9711-f3cb1a937918.png","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/69622abe-509f-4d57-9711-f3cb1a937918.png","id":"a4bce28b-73ae-4676-ad85-2a8e87213eeb"} | 1st piece already used. Casting problems not related to SEN | 2023-02-20 23:00 | 2023-02-27 23:00 | 2023-05-11 22:00 | 2023-07-13 22:00 | null | 2023-07-25 22:00 | 2023-08-23 22:00 | 2023-08-29 22:00 | null | null | 5. Raw materials delay (e.g., mix delay) | 2.6. Shape/Dimensions/Flatness/parallelism | null | null | null
1st pattern with 1303 coming from China; some delay due to mix shipment and reception which forced to postpone packing date to W28 ;however right now there is a deviation on liner thickness which calls for concession, concession finally approved by F.Lopez on 3rd of July 2023.
Product shipped exTC on 14th July 2023.
0 | 266 | null |  | 266 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-12-17 04:46 | 2023-07-17 16:35 | 40 | 23 | 17 | FALSE | 8882cecc-1966-40ea-bf71-9171816ccc11 | null | FCPS-IP00094 | QF09547 | Purge Plugs | 103871 | GERDAU CHARQUEADAS | Brazil | South America | SR | 25 | High | RFQ | {"type":"thumbnail","fileName":"aee4dcce-0570-4f45-9d0b-1de14cadb278.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/aee4dcce-0570-4f45-9d0b-1de14cadb278.jpeg","id":"5553f134-499c-41ac-adb3-97cf731edaa2"} | PATTERN !!! QF09547 | 2023-03-19 23:00 | 2023-07-16 22:00 | null | null | null | 2023-12-14 23:00 | null | null | null | null | null | null | null | null | null
TS3926
Launch Code FCPS-IP00094
1st dwg 20.03.2023
0 | 267 | null |  | 267 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-12-11 12:18 | 2023-07-17 16:40 | 40 | 40 | 7 | FALSE | 20be7886-6dba-44b0-b531-b98159e57d52 | null | FCPS-OPTIFLOW+ | PQ21408 | Purge Plugs | 156457 | AM RESENDE | Brazil | South America | RJ | 16 | α – Alpha | Complete | {"type":"thumbnail","fileName":"9c9f9c6e-c93e-4784-b4bc-13bd0cbd0fd8.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/9c9f9c6e-c93e-4784-b4bc-13bd0cbd0fd8.jpeg","id":"7c3efecf-3a08-4236-8ab7-9ce3deb63c1c"} | PATTERN: PQ21473 | 2023-03-23 23:00 | 2023-04-19 22:00 | 2023-06-05 22:00 | 2023-07-02 22:00 | null | 2023-07-12 22:00 | 2023-11-05 23:00 | 2023-11-29 23:00 | null | null | null | null | null | null | null
1st dwg 24.03.2023
0 | 268 | null |  | 268 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-02-16 18:32 | 2023-07-17 16:46 | 40 | 40 | 12 | FALSE | 477c4732-849f-4123-85d4-a82fafdeed6c | null | FCPS-OPTICLEAN+ | QF09133 | Purge Plugs | 156304 | VSB | Brazil | South America | SR | 25 | β – Beta | Trial | {"type":"thumbnail","fileName":"0967e7e0-3f9e-4f8d-af53-ad9f6a7f50d9.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/0967e7e0-3f9e-4f8d-af53-ad9f6a7f50d9.jpeg","id":"fba895cc-9387-4152-8717-6a071a3c4aab"} | PATTERN !!! QF09125 | 2022-09-20 22:00 | 2023-06-13 22:00 | null | null | null | 2023-11-05 23:00 | 2024-01-14 23:00 | null | null | null | null | null | null | 5. Customer Operational Delays | null
Launch Code: FCPS-IP00024
1st dwg 21.09.2022
0 | 269 | null |  | 269 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-09-18 13:05 | 2023-07-17 16:52 | 40 | 12 | 4 | FALSE | 91876a63-8c7b-47e0-b9fb-e61f0f9732cb | null | FCPS-OPTIFLOW+ | PQ20632 | Purge Plugs | 101497 | ArcelorMittal Juiz de Fora | Brazil | South America | RJ | 10 | β – Beta | Complete | {"type":"thumbnail","fileName":"e61d934d-95b0-4871-acc3-9fc02a68b149.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/e61d934d-95b0-4871-acc3-9fc02a68b149.jpeg","id":"3a0da037-5326-49bd-b7e0-3d3b8ec8734a"} | PATTERN !!! PQ20665 | 2022-07-12 22:00 | 2022-10-03 22:00 | 2022-12-04 23:00 | 2023-03-05 23:00 | null | 2023-03-26 22:00 | 2023-04-02 22:00 | 2023-06-21 22:00 | null | null | null | null | null | null | null
Launch Code FCPS-IP00081
1st dwg 13.07.2022
0 | 270 | null |  | 270 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-02-16 18:29 | 2023-07-17 16:55 | 40 | 40 | 13 | FALSE | 484357de-9afe-4ea0-b5cf-145cff80de12 | null | FCPS-IP00094 | QF09703 | Purge Plugs | 101763 | GERDAU PINDAMONHANGABA | Brazil | South America | SR | 25 | β – Beta | Trial | {"type":"thumbnail","fileName":"c178689e-0205-412e-a85a-5e1326496445.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/c178689e-0205-412e-a85a-5e1326496445.jpeg","id":"ba23dd72-b1ab-4985-b853-1c4ca32ce3aa"} | PATTERN !!! QF09547 | 2023-03-19 23:00 | 2023-07-16 22:00 | null | null | null | null | 2024-02-04 23:00 | null | null | null | null | null | null | null | null
Launch Code: FCPS-IP00094
TS3926
1st dwg 20.03.2023
0 | 271 | null |  | 271 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-02-16 18:33 | 2023-07-17 16:59 | 40 | 40 | 9 | FALSE | c9fb9ee8-9abd-4982-9b66-b9c483a0a010 | null | FCSR-SURFCDT | KA76063 | Slidegate Assy. | 110296 | ARCELORMITTAL BRASIL S/A - TUBARÃO | Brazil | South America | WG | 500 | α – Alpha | Complete | {"type":"thumbnail","fileName":"a70704d7-108e-4570-8341-916d0f1e7c8c.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/a70704d7-108e-4570-8341-916d0f1e7c8c.jpeg","id":"3e9afcf0-9481-480b-8402-5f5b02daa2bd"} | 05.07.2023 PO Date | 2023-06-28 22:00 | 2023-07-04 22:00 | null | null | null | 2023-11-19 23:00 | 2023-12-10 23:00 | 2024-01-23 23:00 | null | null | null | null | null | null | null
18.08.2022 1st dwg
0 | 272 | null |  | 272 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-30 09:57 | 2023-07-18 14:56 | 40 | 12 | 7 | FALSE | d10d23fc-fe6e-4aef-988e-5fc826d5e8a9 | null | FCPS-OPTIFLOW+ | PQ21259 | Purge Plugs | 124089 | GV DO BRASIL | Brazil | South America | RJ | 30 | β – Beta | Complete | {"type":"thumbnail","fileName":"46e297ea-07d8-4503-9307-3810943ffb72.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/46e297ea-07d8-4503-9307-3810943ffb72.jpeg","id":"ca293b25-06f4-4cd1-98c5-a117dfc5069c"} | PATTERN !!! PQ21283 | 2023-02-27 23:00 | 2023-05-11 22:00 | 2023-06-04 22:00 | 2023-07-17 22:00 | null | 2023-08-01 22:00 | 2023-08-08 22:00 | 2023-08-17 22:00 | null | null | null | null | null | null | null
Launch Code FCPS-IP00094
1st dwg 28.02.2023
0 | 273 | null |  | 273 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-23 14:21 | 2023-07-31 14:22 | 12 | 12 | 20 | FALSE | 520f202c-3cce-41f0-9da1-01a90139f2c7 | null | FCVI-SHARKSKIN | BZ49550 | Viso | 120976 | TARANTO | Italy | Europe | SR | 10 | α – Alpha | Pieces on Site | {"type":"thumbnail","fileName":"f3b38ed5-381f-410d-b317-0036d1598506.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/f3b38ed5-381f-410d-b317-0036d1598506.jpeg","id":"291e8b39-6399-4f23-bb0d-50d570e07b21"} | 20.11.2023 No permission to access the site ! | 2022-11-16 23:00 | 2023-01-05 23:00 | 2023-05-31 22:00 | 2023-09-21 22:00 | null | 2023-09-27 22:00 | null | null | null | null | null | null | null | 3. Commercial issues/relationship | null
21.09.2023 - shipment to customer (2/10 pcs)
14.09.2023 - WK37 will be packed 6 pcs, pcs is after thermacout
07.09.2023 - to clarify with Julien packing one crate for Taranto.
28.08.2023 - ON HOLD DECISION FROM PIOTR SPERKA (to sent consesion pcs to the customer)
25.08.2023 - to be pressed, pcs using old sandcores, and we waiting on delivery
17.08.2023 - 1 piece OK to be packed in WK33, pending RPM approval
16.08.2023 - after QC inspection, finishing on-going
03.08.2023 consession - Stefano / Francisco
WK31 seat out of diamension (39mm)
05.01.2023 - dwg revision
17.11.2022 - 1st dwg
0 | 274 | null |  | 274 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-23 14:21 | 2023-07-31 14:29 | 12 | 12 | 30 | FALSE | 89a555bc-fb65-4b1e-899d-e2b28827fa1c | null | FCVI-ANTICLOG | VI-ANTICLOG | Viso | 120976 | TARANTO | Italy | Europe | SR | 10 | α – Alpha | Pieces on Site | {"type":"thumbnail","fileName":"8c22573b-ca54-4b7d-be35-0888732132c9.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/8c22573b-ca54-4b7d-be35-0888732132c9.jpeg","id":"1f623bd8-0017-48bc-8fb2-7c53c8540123"} | PATTERN !!! BZ49568 | 2022-11-16 23:00 | 2023-01-05 23:00 | 2023-05-25 22:00 | 2023-09-21 22:00 | null | 2023-09-28 22:00 | null | null | null | null | null | null | null | 3. Commercial issues/relationship | null
20.11.2023 No permission to access the site !
21.09.2023- shipment to customer (4/10 pcs)
14.09.2023 - WK37 will be packed 6 pcs, pcs is after thermacout
07.09.2023 - to clarify with Julien packing one crate for Taranto.
17.08.2023 - 5 pcs OK, to be packed in WK33, pending RPM approval
16.08.2023 - after QC inspection, finishing on-going
03.08.2023 consession - Stefano / Francisco
WK31 seat out of diamension (39mm)
05.01.2023 - 2nd dwg revision
17.11.2022 - 1st dwg
0 | 275 | null |  | 275 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 14:18 | 2023-08-02 09:49 | 12 | 12 | 15 | FALSE | d91239e3-5293-457f-90d4-e6a0de0a0524 | null | FCSR-LTECH | KA77319 | Slidegate Assy. | 113315 | CELSA BARCELONA | Spain | Europe | SR | 34 | α – Alpha | Pieces on Site | {"type":"thumbnail","fileName":"28cd4335-927d-4a39-864b-5234af17979d.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/28cd4335-927d-4a39-864b-5234af17979d.jpeg","id":"fd3fa59c-2303-45f1-a758-26f9040372ff"} | Trial Date - to check | 2023-04-03 22:00 | 2023-04-13 22:00 | 2023-07-20 22:00 | 2023-09-19 22:00 | null | 2023-10-15 22:00 | null | null | null | null | null | null | null | null | null
Delivery Date - to check
20.09.2023 shipped to customer
19.09.2023 transferred to Kokotow
18.09.2023 order reduced from 40pcs to 34pcs
13.09.2023 packed 34pcs SR3375708
13.09 not fully crate will be packed 13.09 (about 29pcs)
07.09 prioritize assembly for field trials, will be packed 08.09
01.09.2023 pending assembly, packing mid of week 36
SK03479000
current kiln 5th - pressed WK28, fired WK29/30, impregnation WK31/32]
14.04.2023 - PO
04.04.2023 1st dwg
checked by Joanna G.
0 | 276 | null |  | 276 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 16:26 | 2023-08-02 09:51 | 12 | 12 | 17 | FALSE | 6fa52ac6-ef43-41fb-b14d-7e7f334114a2 | null | FCSR-LTECH | KA75974 | Slidegate Assy. | 103897 | OAM Ozd | Hungary | Europe | SR | 20 | α – Alpha | Pieces on Site | {"type":"thumbnail","fileName":"ac60b70a-5016-44e6-a82a-348ad959d9bc.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/ac60b70a-5016-44e6-a82a-348ad959d9bc.jpeg","id":"7d91a670-0674-48b8-a4f8-b5b38e365db1"} | Trial Date - to check | 2023-02-23 23:00 | 2023-03-02 23:00 | 2023-07-06 22:00 | 2023-09-10 22:00 | null | 2023-09-24 22:00 | null | null | null | null | null | null | null | null | null
Delivery Date - to check
11.09 transferred to Kokotow
08.09 20pcs packed SR3360048
07.09 prioritize assembly for field trials, will be packed 11.09
01.09.2023 pending assembly, packing mid of week 36
SK0257000
current kiln 5th - pressed WK28, fired WK29/30, impregnation WK31/32]
03.03.2023 PO
2023 1st dwg
checked by Joanna G.
0 | 277 | null |  | 277 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 14:19 | 2023-08-02 09:53 | 12 | 12 | 13 | FALSE | 043efe86-2379-45bf-a16b-8b8e962da5ad | null | FCSR-LTECH | KA76204 | Slidegate Assy. | 126582 | DNEPROSTEEL | Ukraine | Europe | SR | 10 | α – Alpha | Pieces on Site | {"type":"thumbnail","fileName":"b57f4358-f2a3-4e3d-ae16-f3996bffe8f5.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/b57f4358-f2a3-4e3d-ae16-f3996bffe8f5.jpeg","id":"89c817cf-74c1-4ac1-84a7-02d282fd442e"} | New PO for next 10 pcs (Uli) | 2022-08-31 22:00 | 2023-05-30 22:00 | 2023-07-06 22:00 | 2023-09-14 22:00 | null | 2023-10-01 22:00 | null | null | null | null | null | null | null | null | null
15.09.2023 transferred to commercial ware house
08.09 transferred to Kokotow
07.09 10 pcs packed SR3360034
07.09 prioritize assembly for field trials, will be packed 11.09
01.09.2023 pending assembly, packing mid of week 36
SK03008000
current kiln 5th - pressed WK28, fired WK29/30, impregnation WK31/32]
31.05.2023 PO
01.09.2022 1st dwg
checked by Joanna G.
0 | 278 | null |  | 278 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 12:31 | 2023-08-02 10:04 | 12 | 12 | 20 | FALSE | 8dfae4a4-b697-4d12-8391-08bee7b1f905 | null | FCSR-LTECH | KA74977050 | Slidegate Assy. | 200336 | Ternium Mexico, SA de DV (Puebla) | Mexico | NAFTA | SR | 192 | α – Alpha | Complete | {"type":"thumbnail","fileName":"a2a4edd9-b15e-4a84-81c3-283cd2efe90a.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/a2a4edd9-b15e-4a84-81c3-283cd2efe90a.jpeg","id":"51cf796f-ee16-47ab-8f65-33f9a6116b0e"} | 04.2024 trial date - to check | 2023-06-27 22:00 | 2023-07-04 22:00 | 2023-09-20 22:00 | 2023-11-15 23:00 | null | 2024-01-31 23:00 | 2024-04-01 22:00 | 2024-04-10 22:00 | null | null | null | null | null | null | null
02.2024 pcs on site - to check
in transit
16.11.2023 192pcs shipped
06.11.2023 192pcs transferred to Kokotow
02.11.2023 192pcs packed SR3445638, SR3445614
17.10.2023 57pcs impregnated, the rest pending impregnation
08.10.2023 79pcs fired
04.10.2023 120pcs fired
26.09.2023 207pcs pressed
21.09.2023 pressing week 38
SK00426 raw plate
05.07.2023 PO Date ~ RFQ Date
for 6th kiln (WK35?)
27.04.2022 1st dwg
checked by Joanna G.
0 | 279 | null |  | 279 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-04-25 08:48 | 2023-08-02 10:06 | 12 | 12 | 26 | FALSE | 3a54cc69-07a2-4b04-9029-3779a5778759 | null | FCSR-LTECH | TKA70769040 | Slidegate Assy. | 152515 | ARRENDADORA SIMEC, S.A. DE C.V. | Mexico | NAFTA | SR | 182 | α – Alpha | Trial | {"type":"thumbnail","fileName":"9d7fbb4e-a1c3-426b-a54e-7524663aeb42.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/9d7fbb4e-a1c3-426b-a54e-7524663aeb42.jpeg","id":"ced4dae2-7e4c-4da8-8372-0e3a8b00a188"} | 04.2024 trial date - to check | 2023-07-03 22:00 | 2023-07-10 22:00 | 2023-09-20 22:00 | 2023-11-15 23:00 | null | 2024-01-31 23:00 | 2024-04-01 22:00 | null | null | null | null | null | null | null | null
02.2024 pcs on site date - to check
in transit
21.11.2023 82pcs SR3465937 shipped
16.11.2023 100pcs SR3455827 shipped
16.11.2023 82pcs packed SR3465937
09.11.2023 100pcs packed SR3455827
08.11 pending assembly, waiting for new components - wrong dimensions, delivery will be 20.11.2023
17.10.2023 101pcs impregnation, the rest pending impregnation
12.10.2023 SR3395718 shipped to customer
04.10.2023 200pcs fired
21.09.2023 pressing done (week 38)
DVB0255000 semifinished plate (LG21L)
11.07.2023 PO Date ~RFQ Date
for 6th kiln (WK35?)
KA70769040 (DVB0255000) for VASUVIUS MEXICO (900090) to take 20/200 pcs from PO 6th kiln
200 pcs:
• 20 pcs - alternative RM (only color code, no info about RM) – green label (SIMEC DM) 18 pcs SR3395718
• 180 pcs – pink label 6th kiln
16.03.2023 1st dwg
checked by Joanna G.
0 | 280 | null |  | 280 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-07-04 10:18 | 2023-08-02 11:25 | 12 | 12 | 18 | FALSE | 6c972290-ca9b-43fa-a94a-6ccb6615c3de | null | FCSR-LTECH | TKA71494065 | Slidegate Assy. | 151200 | Aperam Châtelet | Belgium | Europe | SR | 400 | α – Alpha | Complete | {"type":"thumbnail","fileName":"ee2d5f4b-dfe8-4d2b-a692-c7014346e928.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/ee2d5f4b-dfe8-4d2b-a692-c7014346e928.jpeg","id":"8e882df4-002c-4967-925c-93baa25a19a4"} | 17.11.2023 shipped 160pcs | 2023-05-30 22:00 | 2023-06-06 22:00 | 2023-08-24 22:00 | 2023-10-23 22:00 | null | 2023-11-05 23:00 | 2023-11-16 23:00 | 2023-11-29 23:00 | null | null | null | null | null | null | null
16.11.2023 ready 400/400pcs
14.11.2023 80pcs packed SR3465377
08.11.2023 ready 320/400pcs
03.11.2023 80pcs packed SR3445816
25.10.2023 80pcs packed SR3435381
03.11.2023 shipped 160pcs
24.10.2023 80pcs packed SR3435305, 80pcs packed SR3435307
17.10.2023 345pcs impregnation, the rest pending impregnation
08.10.2023 138pcs fired
04.10.2023 280pcs fired
22.09.2023 pressed 420pcs
21.09.2023 pressing week 38
29.05.2020 1st dwg
560 pcs in total production schedule
first 80 pcs - PO 15.05.2023 + 320 pcs 07.06.2023 + pcs - 160 pcs - PO 17.07.2023
160 pcs [current kiln 5th - pressed WK28, fired WK29/30, impregnation WK31/32, target WK34]+ 240 pcs [next kiln - 6th - WK35 to start pressing] optionally +80 pcs and then 80 pcs for 7th kiln
checked by Joanna G.
0 | 281 | null |  | 281 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-12-12 18:47 | 2023-08-02 17:55 | 12 | 38 | 11 | FALSE | 5fa12342-2b18-4558-ac24-6290f14fd599 | null | FCVI-SWIRL | BF00935 | Viso | 146826 | TAEWOONG | South Korea | North Asia | SR | 30 | α – Alpha | Tool | {"type":"thumbnail","fileName":"7de0a1f6-93bc-4fa1-898b-9e89f43dbcf5.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/7de0a1f6-93bc-4fa1-898b-9e89f43dbcf5.jpeg","id":"64391357-0497-4799-990d-f0a6a6ff7c9e"} | PATTERN !!! BF00794 | 2023-05-29 22:00 | 2023-09-13 22:00 | 2023-11-07 23:00 | null | null | null | null | null | null | null | null | null | null | null | null
08.11.2023 ExOne - Quote - 411,80 EUR / LT to confirm - Hubert Handzel
07.11.2023 ZZ17451 EIC 226,37 € / $238,77 (Youngji Lee)
26.10.2023
1) ship ZZ pcs to SZ VISO plant for finishing
2) risk by the European STD fiber 2x3mm of grad 880 not available to be replaced by bio-soluble with different performance
14.09.2023 PO Date
30.05.2023 1st dwg
(** Tooling order received 18/10/2023 ** AMM)
(** Tooling available ex Hyspec 10/11/2023 ** AMM)
0 | 282 | null |  | 282 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-12-12 18:49 | 2023-08-02 18:12 | 12 | 38 | 7 | FALSE | 0ef67bff-43af-4f17-a959-7772d6ecc42b | null | FCVI-SWIRL | BF00232 | Viso | 146826 | TAEWOONG | South Korea | North Asia | SR | 30 | α – Alpha | Tool | {"type":"thumbnail","fileName":"914babe1-b55e-4217-b05a-ee642eb2ae01.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/914babe1-b55e-4217-b05a-ee642eb2ae01.jpeg","id":"59fcf801-40d1-42dd-8962-79769941f47a"} | PATTERN !!! BF00760 | 2023-05-28 22:00 | 2023-09-13 22:00 | 2023-10-25 22:00 | null | null | null | null | null | null | null | null | null | null | null | null
26.10.2023
1) ship ZZ pcs to SZ VISO plant for finishing
2) risk by the European STD fiber 2x3mm of grad 880 not available to be replaced by bio-soluble with different performance
14.09.2023 PO Date
29.05.2023 1st dwg
No tooling order, possibly use BF00794 Tooling. AMM
0 | 283 | null |  | 283 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-12-12 18:51 | 2023-08-02 18:34 | 12 | 38 | 23 | FALSE | eb1b15c3-2bfd-4f30-92b4-997475f99fe1 | null | FCVI-ANTICLOG | BW13933 | Viso | 121229 | Cleveland-Cliffs Middletown | USA | NAFTA | SR | 15 | α – Alpha | Tool | {"type":"thumbnail","fileName":"35e269c5-0294-431c-bd86-1610c50a6178.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/35e269c5-0294-431c-bd86-1610c50a6178.jpeg","id":"ede1c9ec-07e7-468d-bd08-718f5b8860b0"} | PATTERN - BW13933, Launch Code - FCVI-ACS | 2023-07-26 22:00 | 2023-09-04 22:00 | 2023-11-16 23:00 | null | null | null | null | null | 2023-11-18 23:00 | null | null | null | null | null | null
17.11.2023 - Mixes (99kg) arrived to MY
02.11.2023 - Picked-up from GH by forwarder
25.09.2023 - PO1651426 OL
13.09.2023 - Demand placed MYS for BW
13.09.2023 - packing list available for 60kg TS1332 + 20kg TS1333
14.09.2023 - mixes packed air freight quoted,
WK39 mixes delivery
24.08.2023 to schedule production in MY once mixes arrive
17.08.2023 order to ExOne - delay broken equipment, WK37 sandcore from ExOne to start pressing - delay, to confirm capability in SR - no experience with mix 948 – Criterion 50 , 35k GBP investment in equipment, 3 months to get it,
16.08.2023 - Ricardo shared TOT, but will not send ancillary components to SR from MY (cans, wax, etc.)
WK33 - AMT - sandcore tool design ready
10.08.2023 - tooling BL04152/60 - in regular use - no way to transfer, TRF in SR PDL (on-hold)
27.07.2023 1st dwg
(** Tooling order received 07/12/2023 ** AMM)
0 | 284 | null |  | 284 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-12-12 18:52 | 2023-08-02 18:35 | 12 | 38 | 18 | FALSE | b097d80f-d49c-40f3-82f0-987f6b8f4e09 | null | FCVI-ANTICLOG | BW13958 | Viso | 100141 | Cleveland-Cliffs Middletown | USA | NAFTA | MY | 10 | α – Alpha | Tool | {"type":"thumbnail","fileName":"929b1020-a3e3-4814-a333-152f8289152e.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/929b1020-a3e3-4814-a333-152f8289152e.jpeg","id":"9c809c4d-593a-4f35-9de1-7bc86e2615f4"} | PATTERN - BW13958, Launch Code - FCVI-ANTISTICKING | 2023-07-16 22:00 | 2023-09-04 22:00 | 2023-11-16 23:00 | null | null | null | null | null | 2023-11-18 23:00 | null | null | null | null | null | null
17.11.2023 - Mixes (99kg) arrived to MY
09.11.2023 Demand placed on MYS
02.11.2023 - Picked-up from GH by forwarder
23.10.2023 - Airfreight procedure
25.09.2023 - PO 1651426 OP for mixes
19.09.2023 - shipping documentation preparation
14.09.2023 - mixes packed air freight quoted
pending PO - Sam
mixes to be transffered from GH - end of September
17.08.2023 - order to ExOne - delay broken equipment, WK37 sandcore from ExOne to start pressing - delay, to confirm capability in SR - no experience with castables 2. Mix 948 – Criterion 50, 35k GBP investment in equipment, 3 months to get it,
16.08.2023 - Ricardo shared TOT, but will not send ancillary components to SR from MY (cans, wax, etc.)
WK33 - AMT - sandcore tool design ready
10.08.2023 - tooling BL04152/60 - in regular use - no way to transfer, TRF in SR PDL (on-hold)
17.07.2023 1st dwg
MEXICO PRODUCING BY MACHINING EXISTING BL04012, AMM
0 | 285 | null |  | 285 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-30 11:46 | 2023-08-02 18:41 | 12 | 12 | 36 | FALSE | 7e37ae6b-097e-4b48-b941-02b75225a392 | null | FCVI-ACS | BZ50806 | Viso | 480048 | VOESTALPINE LINZ 18000900 | Austria | Europe | SR | 10 | α – Alpha | Manufacturing | {"type":"thumbnail","fileName":"bf85e966-94e3-4cef-90ee-a1d7895df572.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/bf85e966-94e3-4cef-90ee-a1d7895df572.jpeg","id":"4ade5f00-9369-488c-ae32-a6d00cd8c164"} | 30.11.2023 loaded around 11:00 and ETA 04.12.2023 (Monday next week) | 2023-07-24 22:00 | 2023-08-15 22:00 | 2023-09-20 22:00 | 2023-11-29 23:00 | null | null | null | null | null | null | null | null | null | null | null
23.11.2023 BZ50806 – ready to ship in KK, but to be combine with BZ50814 – to be ready 27.11
22.11.2023 due to stock tacking (24-25.11) firefighting on shopfloor to pack and have ready in Kokotów 27.11
16.11.2023 pieces in assembling stage
25.10.2023 WK46 exw SR, after X-Ray, machining required
16.10.2023 - 11 pcs pressed for 10 in crate
WK39 - tooling validation and mixes blended
21.09.2023 - mixes delivered
14.09.2023 - shipment by Raben connected with Erdemir mixes, pick up schedule 15.09 ETA 19.09, to be repacked 20.09 and sent to TC
05.09.2023 - tooling arrived from TC, pending mixes from GH in wk38
31.08.2023, TRF/NPR ok, pending tool dwg, fibre (AC19640) / can (AC21279) - ok, 125kg TS1332, 65kg TS1333, 50kg TS1132, 50 kg TS1145, 145 kg TS1064
28.08.2023 - pending order to GH
25.08.2023 - placed TRF
WK35 tooling ready from TC, to be drifted to WK36 once mixes from GH are available, mixes order adminstration (issues with PRS) ...
0 | 286 | null |  | 286 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-30 11:47 | 2023-08-02 18:45 | 12 | 12 | 41 | FALSE | aebc9910-5d13-4ba5-b4ae-ae093cd66c6a | null | FCVI-ANTISTICKING | BZ50814 | Viso | 480048 | VOESTALPINE LINZ 18000900 | Austria | Europe | SR | 10 | α – Alpha | Manufacturing | {"type":"thumbnail","fileName":"f2d34cb8-7806-4013-83be-7b0ef98f24f9.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/f2d34cb8-7806-4013-83be-7b0ef98f24f9.jpeg","id":"9f47a311-d436-484c-bbc5-a8352b92b00c"} | 30.11.2023 loaded around 11:00 and ETA 04.12.2023 (Monday next week) | 2023-07-24 22:00 | 2023-08-15 22:00 | 2023-09-20 22:00 | 2023-11-29 23:00 | null | null | null | null | null | null | null | null | null | null | null
23.11.2023 to be ready 27.11 but to be combine with BZ50806 – ready to ship in KK
22.11.2023 due to stock tacking (24-25.11) we are firefighting on shopfloor to pack and have ready in Kokotów 27.11
16.11.2023 pieces in assembling stage
25.10.2023 WK46 exw SR, after X-Ray, machining required
16.10.203 - 11 pcs in schedule, 9 done, last 2 pcs - 17.10.2023
WK39 - tooling validation and mixes blended
21.09.2023 - mixes delivered
14.09.2023 - shipment by Raben connected with Erdemir mixes, pick up schedule 15.09 ETA 19.09, to be repacked 20.09 and sent to TC
05.09.2023 - tooling arriveed from TC, pending mixes from GH in WK38
31.08.2023 - TRF/NPR - done, pending tool dwg, AC19640 3mm fiber /AC21279 – can 3mm OK
145kg TS1332, 50kg TS1311, 100kg TS1132, 50kg TS1145, 125kg TS1064
28.08.2023 - pending order to GH
25.08.2023 - placed TRF, WK35 tooling ready from TC, to be drifted to week 36 once mixes from GH are available, mixes order ad...
0 | 287 | null |  | 287 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-12-12 18:54 | 2023-08-02 19:06 | 12 | 38 | 20 | FALSE | 0a8dbd48-382a-4e07-9038-431f0c8cb127 | null | FCVI-ANTICLOG | VI-ANTICLOG | Viso | 147170 | Hyundai | South Korea | North Asia | SZ | 10 | α – Alpha | Tool | {"type":"thumbnail","fileName":"203d870e-501a-40ac-85cc-235f7a0bae99.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/203d870e-501a-40ac-85cc-235f7a0bae99.jpeg","id":"68bfcd99-87a1-46b9-8745-7dd9c21ea278"} | new RFQ - BF00984 patten has changed to BZ, pending new RFQ (Abhi) | 2023-06-28 22:00 | 2023-08-29 22:00 | 2023-10-08 22:00 | null | null | null | null | null | null | null | null | null | null | null | null
09.10.2023 Mix arrived to SZ
19.09.2023 Forwarder pick-up
14.09.2023 - mix 1311 packed from GH, air fright quoted
PATTERN - BF00984, Launch Code - FCVI-ANTISTICKING
01.09.2023 - Mix 1311 - pending transfer from GH to SZ
Tooling transfer + mixes from SZ to SR PDL - cancelled due to Vincent B. decision,
date of trial - Abhi! pending PO - Fred V.
internal PO for tooling: 1202313727 - ready for shipment, transport procedure, for mixes: 1202313730, manufactured, properties pending approval TS238 (500kg), TS240 (200kg), 288 (100kg) (Fuhu) to be shipped by air freight to GH for rejuvenation
29.06.2023 1st dwg
To date no tooling order received, AMM 12/12/2023
0 | 288 | null |  | 288 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-03-01 10:08 | 2023-08-03 14:34 | 12 | 259 | 16 | FALSE | fb1620a9-8fc0-4478-ab10-fbe387075f8f | null | FCVI-DURAFLEXHF | BC48621 | Viso | 155588 | CMC Steel Arizona | USA | NAFTA | MY | 10 | β – Beta | Pieces on Site | {"type":"thumbnail","fileName":"306e58df-59fb-4ac9-9682-64143f719130.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/306e58df-59fb-4ac9-9682-64143f719130.jpeg","id":"6f8b5c86-5a69-4767-b72f-e1d80962b938"} | 15.02.2024 new pieces ordered. waiting for production | 2023-07-25 22:00 | 2023-08-31 22:00 | 2023-09-03 22:00 | 2023-11-12 23:00 | null | 2023-11-19 23:00 | null | null | null | null | null | null | null | null | null
13.11.2023 18 pcs packed (MYV3450236), scanned pcs -rejected nr 3 & 10.
27.10.2023 3D scanning to be done after firing
08.09.2023 - share feedback glaze test, share x-ray first 6 pcs X-rayed cured
04.09.2023 one piece pressed: glaze and fire to check oxidation. Glaze configuration to test on the piece: G82 in upper part; in the Bionic chevrons area, ½ with B82 and other ½ with G97
21.07.2023 make pcs with 1301, not 1283
26.07.2023 2nd dwg revision
22.03.2023 1st dwg
0 | 289 | null |  | 289 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-03-07 14:32 | 2023-08-18 17:15 | 12 | 259 | 9 | TRUE | aa7dcbae-9f39-49d6-8d21-e5226dab5dd0 | null | FCVI-DURAFLEX20H | BD76398 | Viso | 480048 | VOESTALPINE LINZ 18000900 | Austria | Europe | SR | 20 | α – Alpha | PO | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][7]_[BD76398][1]_[5].jpg"} | 06.03.2024: in SR, waiting for thermite validation, investigating the TC consistency. | 2023-08-03 22:00 | 2023-08-15 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null
February 24: Order in S&OP week 9, SR waiting for pcs from TC, firing will be done in TC (ex TC wk 8)
January 24: GH remaking mix, expected to ship to TC in week3.
new Duraflex mix for test of COLD RE-USE in Linz - BD76398
to check RFQ Date
16.08.2023 - item created in S&OP, PO placed for 20 pcs the end of September
0 | 290 | null |  | 290 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-09-21 21:20 | 2023-08-18 17:24 | 12 | 12 | 3 | FALSE | 36b52322-6313-439b-a365-4e065773a09a | null | FCVI-DURAFLEX1000L | BD75465 | Viso | 102563 | Trinecke Zelezarny | Czechia | Europe | SR | 10 | α – Alpha | PO | null | To check RFQ Date | 2023-08-03 22:00 | 2023-08-15 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null
Order of BD75465 (Duraflex for TZ bloom caster for testing cold re-start mix)
10pcs was ordered on wk38
0 | 291 | null |  | 291 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-03-06 13:50 | 2023-08-18 17:33 | 12 | 259 | 9 | FALSE | 9df13175-d8a6-441d-865d-b5d1ae67fa86 | null | FCVI-DURAFLEX20H | BC49173 | Viso | 114332 | JSW Steel - Vijayanagar Works | India | India | SR | 20 | α – Alpha | PO | {"type":"thumbnail","fileName":"82108120-36d4-4b96-b2da-39946fc4034d.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/82108120-36d4-4b96-b2da-39946fc4034d.jpeg","id":"62a72303-a069-4835-8ace-3bcd97dfaa99"} | 06.03.2024: | 2023-08-03 22:00 | 2023-08-22 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null
1334=thermite validation pending (transportation 5th of march)
1335=to grind, mandrel NOK
February 24:
1334=delay on tooling manufacturing - machining mandrel, now confirmation middle of March, to push delivery time packing first week of April,
1335=same
January 24:
1334=GH remaking mix, expected to ship to TC in week4
1335=In production in SR
10 with 1334, 10 with 1335 under concession
23.08.2023 PO
17.08.2023 pending PO for 20 pcs to be placed on SR
04.08.2023 1st dwg
0 | 292 | null |  | 292 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-02-26 09:40 | 2023-08-18 17:44 | 12 | 259 | 20 | FALSE | 2af65b65-1e2e-4ac0-9de8-6a2c79ade6c6 | null | FCVI-DURAFLEX1000L | BD74104 | Viso | 110635 | Jindal Shadeed Iron & Steel LLC | Oman | Europe | SR | 40 | α – Alpha | Manufacturing | {"type":"thumbnail","fileName":"71a0e131-4437-431a-afde-91100e0081c9.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/71a0e131-4437-431a-afde-91100e0081c9.jpeg","id":"feec9be7-c5be-4fd3-8cea-3a4f39852614"} | XX.11.2023 Arrived in Sohar port. Checking if already arrived at customer's site | 2022-10-09 22:00 | 2023-03-27 22:00 | 2023-05-04 22:00 | 2023-11-29 23:00 | null | null | null | null | null | null | null | null | null | null | null
06.11.2023 2 tons of rejuvenated 1301, Fired properties shared
25.08 HOLD by Julien Magnier mixes 10283 don't have good properties
laminated in TC / cancelled / transferred to SR PDL
moved for production in Skawina PDL
28.03.2022 - PO for 40 pcs of BD74104 placed by JSiS
23.10.2023 2nd revision
10.10.2022 1st dwg
0 | 293 | null |  | 293 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-12-12 18:55 | 2023-08-18 17:58 | 12 | 38 | 23 | FALSE | b9868947-a8f7-471b-8c49-bd4f505a7b33 | null | FCVI-ACS | BZ51051 | Viso | 110296 | ARCELORMITTAL BRASIL S/A - TUBARÃO | Brazil | South America | RJ | 10 | α – Alpha | Tool | {"type":"thumbnail","fileName":"8069e672-170a-43aa-ab52-8f32125d93fd.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/8069e672-170a-43aa-ab52-8f32125d93fd.jpeg","id":"e3110a46-8c8c-49f7-86b7-deb364481a38"} | 22.11.2023 RJ plant all production slots are full, not be able to produce pieces for Tubarão in 2023 | 2023-08-13 22:00 | 2023-09-17 22:00 | 2023-11-13 23:00 | null | null | null | null | null | null | null | null | null | null | null | null
14.11.2023 - Mixes arrived to RJ
11.11.2023 Cargo Arrived at Brazil
08.11.2023 Due to metal drums and temperature control, the cargo will be removed to Paris and there get a flight directly to Rio de Janeiro
02.11.2023 - Picked-up from GH by forwarder
26.10.2023 Airfreight by Interfreight vs. PGLBR $1,494 (Romulo Macedo)
19.10.2023 - Airfreight procedure on-going
04.10.2023 - Mixes packed - airfreight quotation requested
18.09.2023 - PO available - mixes being adjusted in GH
14.09.2023 - mixes to be packed from GH (15.09)
07.09.2023 pending PO for mixes TS1332 380kg / TS1333 240kg / TS1311 55kg
21.08.2023 mixes to be transferred to RJ from GH in WK38 by airfreight to start production in WK42
12.07.2023 Customer Presentation
14.08.2023 1st dwg
No tooling order received, AMM 12/12/2023
0 | 294 | null |  | 294 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-12-12 18:56 | 2023-08-18 17:59 | 12 | 38 | 31 | FALSE | ecdf6855-9f9b-41d7-b564-42622ad5fefb | null | FCVI-ACS | BZ51044 | Viso | 110296 | ARCELORMITTAL BRASIL S/A - TUBARÃO | Brazil | South America | RJ | 10 | α – Alpha | Tool | {"type":"thumbnail","fileName":"2998a54e-f62f-4f49-a09e-cdbcdab677ca.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/2998a54e-f62f-4f49-a09e-cdbcdab677ca.jpeg","id":"d57b20fd-ce9c-4756-bd13-c4d32377b7b8"} | 22.11.2023 RJ plant all production slots are full, not be able to produce pieces for Tubarão in 2023 | 2023-08-13 22:00 | 2023-09-17 22:00 | 2023-11-13 23:00 | null | null | null | null | null | null | null | null | null | null | null | null
14.11.2023 - Mixes arrived to RJ
11.11.2023 Cargo Arrived at Brazil
08.11.2023 Due to metal drums and temperature control, the cargo will be removed to Paris and there get a flight directly to Rio de Janeiro
02.11.2023 - Picked-up from GH by forwarder
26.10.2023 Airfreight by Interfreight vs. PGLBR $1,494 (Romulo Macedo)
19.10.2023 - Airfreight procedure on-going
04.10.2023 - Mixes packed - airfreight quotation requested
18.09.2023 - PO available - mixes being adjusted in GH
14.09.2023 - mixes to be packed from GH (15.09), pending PO from RJ
07.09.2023 PO for mixes TS1332 380kg / TS1333 240kg / TS1311 55kg; Concession instead TS1332 Top 238 / Port 1178
21.08.2023 mixes to be transferred to RJ from GH in WK38 by airfreight to start production in WK42
12.07.2023 Customer Presentation
14.08.2023 1st dwg
12.12.2023 No tooling order received, AMM.
0 | 295 | null |  | 295 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-12-12 18:57 | 2023-08-18 18:03 | 12 | 38 | 13 | FALSE | 747884f6-e981-419b-9782-694479c1e27d | null | FCVI-ANTICLOG | BW13941 | Viso | 100141 | Cleveland-Cliffs Middletown | USA | NAFTA | MY | 10 | α – Alpha | Tool | null | 17.11.2023 - Mix arrived (99 kg) to MY | 2023-08-17 22:00 | 2023-09-04 22:00 | 2023-11-16 23:00 | null | null | null | null | null | null | null | null | null | null | null | null
09.11.2023 - Demand Placed on MYS for BW
02.11.2023 - Picked-up from GH by forwarder
24.10.2023 - PO 1657859 (TS1332 650, TS1333 200, TS1311 70)
23.10.2023 - Airfreight procedure, invoice 1512301026 for TS332 60, TS1333 20)
25.09.2023 - PO 1651426 OP for mixes
19.09.2023 - shipping documentation preparation
14.09.2023 - mixes packed, air freight quoted
BW00213 / BK64968
mixes TS1332 TS1333 to be transfered from GH to MYV
05.09.2023 pending PO - Sam
mixes to be transffered from GH - end of September
12.12.2023 No tooling order received, AMM
0 | 296 | null |  | 296 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-12-12 18:59 | 2023-08-18 18:07 | 12 | 38 | 23 | FALSE | bbf593be-1978-4295-bfb6-2ad8f192e031 | null | FCVI-ACS | BZ51036 | Viso | 118716 | ERDEMIR EREGLI | Turkey | Europe | TC | 10 | α – Alpha | Tool | {"type":"thumbnail","fileName":"5a9610bb-66ee-43ef-a838-8068a1611e27.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/5a9610bb-66ee-43ef-a838-8068a1611e27.jpeg","id":"deb758e1-1b44-4537-a5aa-0c053cdf8b08"} | 30.11.2023 - Pr can start wk48 | 2023-08-10 22:00 | 2023-09-05 22:00 | 2023-11-29 23:00 | null | null | null | null | null | null | null | null | null | null | null | null
- target 1332 ready for WK48 in SR (300kg) & 100 kg 1333
24.11.2023 - bag ex hyspec WK47 +1-2 wk delivery
23.11.2023 pending official PO FOC from Levent / Cem
17.11.2023 Filling gears & tool modification drawing on wk46, +2 week for delivery
18.10.2023 - BZ50897 - 2 pcs pressed out of spec in TC, tooling redesign
WK39 shipment to TC
21.09.2023- mixes delivered to SR
19.09.2023 - pending PO 10 pcs FOC (Cem)
14.09.2023 - mixes packed, pick up scheduled (15.09) ETA 19.09 to SR to be repacked and shiped to TC
07.09- 3 pcs to be press in TC
31.08.2023
- TRF OK
- pending drawing/ NPR
- pending confirmation for tooling transfer from TC
MIX 130 kg TS1332, 60 TS1333
45kg 1132, 65kg TS1074 per pattern
11.08.2023 1st dwg
(** Tooling order received 04/09/2023 ** AMM)
(** Tooling completed 21/09/2023 ** AMM)
0 | 297 | null |  | 297 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 15:58 | 2023-08-22 08:57 | 36 | 12 | 11 | FALSE | f33dc400-6b68-40d1-a1f8-70670c1f936e | null | FCVI-UNIVERSALSTOPPER | BP77654 | Viso | 103781 | SAARSTAHL | Germany | Europe | TC | 16 | α – Alpha | Pieces on Site | {"type":"thumbnail","fileName":"6d94d510-621d-46a7-9727-57665cd44859.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/6d94d510-621d-46a7-9727-57665cd44859.jpeg","id":"9a75054b-da06-473c-b729-3b047ee9b297"} | PATTERN !!! BB16000 | 2023-07-30 22:00 | 2023-08-07 22:00 | 2023-08-14 22:00 | 2023-09-19 22:00 | null | 2023-09-25 22:00 | null | null | null | null | null | null | null | 1. Customer Order Book/Scheduling | null
with glaze trials special G150 and G19+G150
TOOLING EXISTING
estimate date end september out of TC
TYK/RHI vs 1064 vs 1397/1105
"Low Carbon; Medium Carbon; High Strength, Low Alloy; Free Cutting Grades, sulphur controlled grades"
09.09.2020 4th dwg revision
0 | 298 | null |  | 298 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-04-25 08:50 | 2023-08-23 16:43 | 12 | 12 | 15 | FALSE | f33850f4-216c-45b5-948a-e0502fa21808 | null | FCSR-LTECH | TKA70769040 | Slidegate Assy. | 152515 | ARRENDADORA SIMEC, S.A. DE C.V. | Mexico | NAFTA | SR | 20 | β – Beta | Trial | {"type":"thumbnail","fileName":"ebe20bf7-498d-4a49-9da2-531dba24e225.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/ebe20bf7-498d-4a49-9da2-531dba24e225.jpeg","id":"03bfc4ab-5ec3-4d83-99f7-cb93a3652c51"} | 04.2024 trial date - to check | 2023-07-03 22:00 | 2023-07-10 22:00 | 2023-08-03 22:00 | 2023-10-11 22:00 | null | 2024-01-31 23:00 | 2024-04-01 22:00 | null | null | null | null | null | null | null | null
02.2024 pcs on site date - to check
in transit
12.10.2023 shipped 18pcs
28.09.2023 transferred to Kokotow SR3395718
27.09.2023 packed 18pcs (alternative RM) SR3395718
22.09.2023 will be banded
21.09.2023 pending assembly (19pcs will be finished in week 39)
20.09.2023 pressed 180pcs
01.09.2023 pending Artur action
DVB0255000 semifinished plate (LG21L)
11.07.2023 PO Date ~RFQ Date
current kiln 5th - pressed WK28, fired WK29/30, impregnation WK31/32
to take 20/200 pcs from PO 6th kiln
200 pcs:
• 20 pcs - alternative RM (only color code, no info about RM) – green label (SIMEC DM)
• 180 pcs – pink label 6th kiln
30.01.2023 1st dwg
checked by Joanna G.
0 | 299 | null |  | 299 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-24 17:07 | 2023-08-23 19:49 | 12 | 12 | 5 | FALSE | 8772ec44-74b0-45d0-a213-3db89e0a12b5 | null | FCSR-CDT3397 | KA77731040 | Slidegate Assy. | 135579 | Liberty Ostrava | Czechia | Europe | SR | 15 | α – Alpha | PO | {"type":"thumbnail","fileName":"c842703e-463a-441d-917f-cdeea8b893e1.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/c842703e-463a-441d-917f-cdeea8b893e1.jpeg","id":"8d2486b4-5c8e-45ff-a416-b16ab4c84537"} | SLCDT 3420 KA76519055 | 2023-06-01 22:00 | 2023-08-22 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null
02.06.2023 1st dwg
0 | 300 | null |  | 300 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-08-23 20:05 | 2023-08-23 20:05 | 12 | 12 | 2 | FALSE | a04bdb3e-882d-42f2-89a3-cbfbd6aa137a | null | FCSR-CDT3397 | KA78291 | Slidegate Assy. | 113319 | BALBOA S.A. | Spain | Europe | SR | 15 | α – Alpha | PO | {"type":"thumbnail","fileName":"194bacc1-a0f7-4942-81ad-05b58d476b31.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/194bacc1-a0f7-4942-81ad-05b58d476b31.jpeg","id":"9009576f-f331-4af2-be6d-973069bd263a"} | 27.07.2023 1st dwg | 2023-07-26 22:00 | 2023-08-22 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null
0 | 301 | null |  | 301 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-08-23 20:14 | 2023-08-23 20:13 | 12 | 12 | 2 | FALSE | c7f651e5-ec1a-4151-905d-f9510eb3860f | null | FCSR-CDT3397 | KA78309 | Slidegate Assy. | 113240 | ArcelorMittal SESTAO | Spain | Europe | SR | 15 | α – Alpha | PO | {"type":"thumbnail","fileName":"e7bd269e-f97d-4e19-b123-aefb9d1c8c23.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/e7bd269e-f97d-4e19-b123-aefb9d1c8c23.jpeg","id":"a201eb4c-a291-4411-ac9f-3d9801557e31"} | 27.07.2023 1st dwg | 2023-07-26 22:00 | 2023-08-22 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null
0 | 302 | null |  | 302 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-26 07:56 | 2023-08-24 09:33 | 12 | 12 | 6 | FALSE | 6ef09090-f28e-4019-9a51-dc6ee631ab05 | null | FCPS-OPTIFLOW+ | PS-OPTIFLOWP | Purge Plugs | 172170 | ArcelorMittal Steelton LLC (CRPAS2) | USA | NAFTA | SR | 20 | α – Alpha | PO | {"type":"thumbnail","fileName":"15561278-1b69-4a97-a332-30c9ee047936.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/15561278-1b69-4a97-a332-30c9ee047936.jpeg","id":"fcda87cc-4996-4417-809a-562a2416a177"} | PATTERN !!! QF09430 | 2022-12-13 23:00 | 2023-05-16 22:00 | null | null | null | null | null | null | null | null | 6. Components delay (e.g., cans delay) | null | null | null | null
Launch Code FCPS-OPTIFLOW+ (instead of FCPS-HSC)
2x PO: 01.16.2023 & 17.05.2023
to move the delivery dates in the order:
From 22.09.2023 to 10.11.2023
From 06.10.2023 to 08.12.2023
14.12.2022 1st dwg
0 | 303 | null |  | 303 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-25 21:42 | 2023-08-24 18:25 | 12 | 12 | 5 | FALSE | 906546c4-e9d7-4d73-bf86-350433fe4fca | null | FCVI-UNIVERSALSTOPPER | BP77654 | Viso | 200335 | Ternium Mexico, SA de DV (Monterrey) | Mexico | NAFTA | MY | 10 | α – Alpha | PO | {"type":"thumbnail","fileName":"9b3fc08e-db23-44c6-8c70-49fb3bfaba8f.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/9b3fc08e-db23-44c6-8c70-49fb3bfaba8f.jpeg","id":"25065681-157c-4ed5-acc8-0347fb038c66"} | Delay of CH RM | 2023-08-06 22:00 | 2023-09-25 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null
1111 BP54117 and 1096/1105 (electric grades) BP63910, seat 711 BF98967,
1397/1105 10pcs vs 1096(GH)/1105 10 pcs
26.09.2023 PO
07.08.2023 1st dwg
23.07.2023 RFQ submited
0 | 304 | null |  | 304 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-25 21:32 | 2023-08-24 18:27 | 12 | 12 | 5 | FALSE | 474eda76-02b7-4124-b7d6-b2c098d92dd7 | null | FCVI-UNIVERSALSTOPPER | BP77704 | Viso | 135667 | JSW STEEL - Dolvi Works | India | India | CL | 7 | α – Alpha | PO | {"type":"thumbnail","fileName":"d6d39340-b653-4e6d-a627-3364e0b09ae5.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/d6d39340-b653-4e6d-a627-3364e0b09ae5.jpeg","id":"468d4605-a7cc-47fd-9445-dadf34399ec5"} | Customer: JSW Dolvi [billet no Ar] | 2023-08-10 22:00 | 2023-08-30 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null
1096(GH)/1109 7 pcs vs 1397(GH)/1109 7 pcs ref 1111
6 strand 1096 two central (BP64884), 1111 4 perifery strands (BP62912)
"low C, medium C" 20-25 ppm Ca (one grade all the time) Railway grades"
31.08.2023 PO mix
11.08.2023 1st dwg
0 | 305 | null |  | 305 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-25 21:39 | 2023-08-24 18:28 | 12 | 12 | 5 | FALSE | 3faec413-5ea3-4278-aa52-e760ead476ff | null | FCVI-UNIVERSALSTOPPER | BP77969 | Viso | 122463 | Steel Dynamics Southwest-Sinton Division | USA | NAFTA | MY | 10 | α – Alpha | RFQ | {"type":"thumbnail","fileName":"74aba636-e8ad-4bc9-80bd-ef0b5c9464bd.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/74aba636-e8ad-4bc9-80bd-ef0b5c9464bd.jpeg","id":"6e543a34-baba-46ba-a47e-b4e01c5527bd"} | Current: 1225 BP69586 | 2023-10-04 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null | null
LC and ULC AlCa, Ca 30 ppm (10-50ppm)
05.10.2023 1st dwg
18.08.2023 RFQ submitted
0 | 306 | null |  | 306 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-30 15:20 | 2023-08-25 19:01 | 12 | 12 | 13 | FALSE | 5083f581-6a14-4ba1-aff0-05cde82b9746 | null | FCPS-OPTIFLOW+ | PL13885 | Purge Plugs | 100850 | TERNI ACCIAI SPEC SPA | Italy | Europe | SR | 76 | β – Beta | Complete | {"type":"thumbnail","fileName":"975845b0-52cb-4259-8f51-5fec04f3ee79.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/975845b0-52cb-4259-8f51-5fec04f3ee79.jpeg","id":"eb4e7549-87f2-4944-84ac-02774422f47c"} | PATTERN !!! PL13828 | 2022-03-23 23:00 | 2022-10-25 22:00 | 2023-02-02 23:00 | 2023-03-30 22:00 | null | 2023-04-13 22:00 | 2023-06-08 22:00 | 2023-06-29 22:00 | null | null | null | null | null | null | null
Launch Code FCPS-OPTIFLOW+ instead of FCPS-HSC
to check PO Date
to check Trial Date
04.2023 pcs on site
12.01.2023 - 15.06.2023 ready for shipment
23.03.2023 2nd dwg revision
24.03.2022 1st dwg
0 | 307 | null |  | 307 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 16:14 | 2023-08-25 19:03 | 12 | 12 | 12 | FALSE | 838d03f9-fec5-4468-bc34-dc0eeeb9d530 | null | FCPS-OPTIFLOW+ | PL13885 | Purge Plugs | 100850 | TERNI ACCIAI SPEC SPA | Italy | Europe | SR | 34 | α – Alpha | Manufacturing | {"type":"thumbnail","fileName":"c9eef255-e453-4aeb-8e45-bc938fd10435.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/c9eef255-e453-4aeb-8e45-bc938fd10435.jpeg","id":"8949fabf-6fde-4e5f-87f1-81328a79e78b"} | PATTERN !!! PL13828 | 2022-03-23 23:00 | 2022-05-04 22:00 | 2022-06-23 22:00 | 2022-09-25 22:00 | null | 2023-10-19 22:00 | null | null | null | null | null | null | null | null | null
Launch Code FCPS-OPTIFLOW+ insted of FCPS-HSC
to check PO Date
to check Trial Date
26.09.2022 - 21.12.2022 ready for shipment
23.03.2023 2nd dwg
24.03.2022 1st wg
0 | 308 | null |  | 308 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-30 15:08 | 2023-08-25 19:21 | 12 | 12 | 13 | FALSE | 683433f9-88fe-489b-bcad-6f473f406fa2 | null | FCPS-OPTICLEAN+ | QF08796 | Purge Plugs | 145569 | TEMIRTAU LITEYNY ZAVOD | Kazakhstan | Europe | SR | 20 | α – Alpha | Complete | {"type":"thumbnail","fileName":"5dbd270c-41d3-49a2-8f21-f8ca4094f888.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/5dbd270c-41d3-49a2-8f21-f8ca4094f888.jpeg","id":"09437809-0ccd-4cbe-b79a-54af387dbd55"} | to check PO Date | 2023-01-24 23:00 | 2023-01-31 23:00 | 2023-03-30 22:00 | 2023-05-25 22:00 | null | 2023-07-27 22:00 | 2023-09-14 22:00 | 2023-09-28 22:00 | null | null | null | null | null | null | null
to check Trial Date
26.05.2023 ready for shipment
04.01.2022 1st dwg
0 | 309 | null |  | 309 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 16:28 | 2023-08-25 21:47 | 12 | 12 | 11 | FALSE | 2d8420d2-2adb-4313-9987-f353aa3a47ab | null | FCPS-OPTIFLOW+ | PQ20491 | Purge Plugs | 163559 | Baku Steel | Azerbaijan | Europe | SR | 250 | β – Beta | Complete | {"type":"thumbnail","fileName":"0b4c1a9a-2085-4169-8e02-10f817bf11d3.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/0b4c1a9a-2085-4169-8e02-10f817bf11d3.jpeg","id":"2e54afef-fcc1-4771-8fe4-80b0cdbdae63"} | to check PO Date | 2022-12-11 23:00 | 2022-12-18 23:00 | 2023-01-11 23:00 | 2023-04-10 22:00 | null | 2023-05-24 22:00 | 2023-07-05 22:00 | 2023-08-02 22:00 | null | null | null | null | null | null | null
to check Trial Date
11.04.2023 ready for shipment
25.08.2023 2nd revision dwg
16.02.2022 1st dwg
0 | 310 | null |  | 310 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 16:14 | 2023-08-25 21:50 | 12 | 12 | 9 | FALSE | 975c7947-ff6a-49e1-a391-ac191e6e5877 | null | FCPS-OPTIFLOW+ | PQ20491 | Purge Plugs | 163559 | Baku Steel | Azerbaijan | Europe | SR | 250 | β – Beta | Complete | {"type":"thumbnail","fileName":"488daa7a-abd1-4db5-b115-2b51e0f70711.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/488daa7a-abd1-4db5-b115-2b51e0f70711.jpeg","id":"ef4721b6-f8ee-4dbc-b022-7862ca550d6f"} | to check Trial Date | 2022-02-15 23:00 | 2022-04-05 22:00 | 2022-09-29 22:00 | 2022-12-15 23:00 | null | 2023-01-25 23:00 | 2023-02-22 23:00 | 2023-05-24 22:00 | null | null | null | null | null | null | null
06.04.2022 PO Date
20.09.2022 / 16.12.2022 Mfg
16.12.2022 ready for shioment
25.08.2023 2nd revision dwg
16.02.2022 1st dwg
0 | 311 | null |  | 311 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-20 09:37 | 2023-08-25 22:05 | 12 | 12 | 9 | FALSE | 85e501cd-627e-4815-b211-ce41a356639d | null | FCPS-OPTIFLOW+ | PQ19246 | Purge Plugs | 100902 | ArcelorMittal Steel Vanderbijlpark | South Africa Republic | Europe | SR | 20 | α – Alpha | Complete | {"type":"thumbnail","fileName":"867c6904-b945-463f-9093-3d4ed250684b.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/867c6904-b945-463f-9093-3d4ed250684b.jpeg","id":"adb77ea1-e12b-4f4a-90b3-59a9a99aa56b"} | 01.09.2022 ready for shipment | 2022-03-29 22:00 | 2022-05-25 22:00 | 2022-08-11 22:00 | 2022-09-25 22:00 | null | 2022-11-10 23:00 | 2022-11-17 23:00 | 2022-12-15 23:00 | null | null | null | null | null | null | null
12.08.2022
26.05.2022 PO
30.03.2022 1st dwg
checked by Krzysztof Wołek
0 | 312 | null |  | 312 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 16:21 | 2023-08-25 22:12 | 12 | 12 | 5 | FALSE | d1afc057-39bd-45e7-aa0a-dc97a79075ff | null | FCPS-OPTICLEAN+ | QF09174 | Purge Plugs | 135746 | TATA KPO | India | India | SR | 5 | α – Alpha | Manufacturing | {"type":"thumbnail","fileName":"83801c85-5d8f-4f4d-8630-413679513854.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/83801c85-5d8f-4f4d-8630-413679513854.jpeg","id":"7d146ead-3302-44e1-bfc9-65357507c68c"} | to check PO Date | 2022-09-28 22:00 | 2022-11-03 23:00 | 2023-01-19 23:00 | 2023-02-15 23:00 | null | null | null | null | null | null | null | null | null | null | null
to check Trial Date
16.02.2023 ready for shipment
29.09.2022 1st dwg
0 | 313 | null |  | 313 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 16:15 | 2023-08-25 22:43 | 12 | 12 | 8 | FALSE | ff1fd473-bf47-4930-b844-8a53a2f7d2e3 | null | FCPS-OPTIFLOW+ | PQ20491 | Purge Plugs | 163559 | Baku Steel | Azerbaijan | Europe | SR | 200 | α – Alpha | Complete | {"type":"thumbnail","fileName":"431bedca-c3a9-4072-816e-99a5a7eb85d8.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/431bedca-c3a9-4072-816e-99a5a7eb85d8.jpeg","id":"54e44cc0-2477-419b-9741-683127a55509"} | to check PO Date | 2022-02-15 23:00 | 2022-03-02 23:00 | 2022-07-28 22:00 | 2022-09-19 22:00 | null | 2022-11-13 23:00 | 2022-11-28 23:00 | 2023-01-26 23:00 | null | null | null | null | null | null | null
to check Trial Date
20.09.2022 ready for shioment
25.03.2023 2nd revision
16.02.2022 1st dwg
0 | 314 | null |  | 314 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 16:15 | 2023-08-25 22:59 | 12 | 12 | 3 | FALSE | ec082116-aa22-4088-8208-68dde10f28e4 | null | FCPS-OPTIFLOW+ | PQ19246 | Purge Plugs | 100902 | ArcelorMittal Steel Vanderbijlpark | South Africa Republic | Europe | SR | 30 | β – Beta | Manufacturing | {"type":"thumbnail","fileName":"1ced7a88-bc18-4999-be49-c8845468462c.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/1ced7a88-bc18-4999-be49-c8845468462c.jpeg","id":"f1776607-810e-4879-9d92-3f1e5c05958c"} | to check PO Date | 2022-03-29 22:00 | 2022-05-08 22:00 | 2022-07-28 22:00 | 2022-09-25 22:00 | null | null | null | null | null | null | null | null | null | null | null
to check Trial Date
26.09.2022 ready for shipment
30.03.2022 1st dwg
0 | 315 | null |  | 315 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-24 15:17 | 2023-09-01 10:30 | 12 | 12 | 11 | FALSE | 912c7a68-1342-4d37-b45a-8f82b88a9d48 | null | FCSR-LTECH | KA73250048 | Slidegate Assy. | 114991 | KARDEMIR | Turkey | Europe | SR | 20 | β – Beta | Pieces on Site | {"type":"thumbnail","fileName":"23aa09ef-8bfb-49e8-af65-7d0037f82438.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/23aa09ef-8bfb-49e8-af65-7d0037f82438.jpeg","id":"fef83979-42ce-4fcb-85ec-4e6f63082ab0"} | Trial Date - to check | 2023-04-23 22:00 | 2023-05-13 22:00 | 2023-05-23 22:00 | 2023-09-18 22:00 | null | 2023-10-29 23:00 | null | null | null | null | null | null | null | null | null
Delivery Date - to check
19.09.2023 shipped to customer
15.09.2023 order adjust from 20pcs to 23pcs (all WIP packed)
11.09 transferred to Kokotow
08.09 23pcs packed SR3366148
07.09 prioritize assembly for field trials, will be packed 08.09
01.09.2023 pending assembly, packing 01.09
PO 14.03.2023
24.04.2023 2nd dwg revision
30.04.2021 1st dwg
0 | 316 | null |  | 316 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 09:30 | 2023-09-07 16:46 | 12 | 12 | 13 | FALSE | 7150f0fc-e63e-4ab2-a88e-ba6e531e0e53 | null | FCVI-ANTISTICKING | BZ51127 | Viso | 110296 | ARCELORMITTAL BRASIL S/A - TUBARÃO | Brazil | South America | RJ | 9 | α – Alpha | Manufacturing | {"type":"thumbnail","fileName":"955c26f5-0443-49af-90cb-dbf84a39706f.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/955c26f5-0443-49af-90cb-dbf84a39706f.jpeg","id":"0e914df5-3d3f-4752-a8fd-57bce6f2d549"} | 14.11.2023 Mixes arrived to RJ | 2023-08-20 22:00 | 2023-09-05 22:00 | 2023-11-13 23:00 | 2023-11-29 23:00 | null | null | null | null | null | null | null | null | null | null | null
11.11.2023 Cargo Arrived at Brazil
08.11.2023 Due to metal drums and temperature control, the cargo will be removed to Paris and there get a flight directly to Rio de Janeiro
26.10.2023 Airfreight by PGLBR $1,494 (Romulo Macedo)
18.09.2023 - PO available - mixes being adjusted in GH
14.09.2023 - mixes to be packed from GH (15.09)
07.09.2023 Concession - instead of TS1332 Top 238 / Port 1178 / TS1311 Bore (52kg) - Mixes to be shipped from GH to RJ
12.07.2023 Customer Presentation
21.08.2023 1st dwg
0 | 317 | null |  | 317 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-12-12 19:01 | 2023-09-08 06:44 | 12 | 38 | 23 | FALSE | 3a1c017b-dd41-42a5-9d52-ac69dd3f61c8 | null | FCVI-ACS | BZ50897 | Viso | 118716 | ERDEMIR EREGLI | Turkey | Europe | TC | 10 | α – Alpha | Tool | {"type":"thumbnail","fileName":"c5cde511-dc27-4e66-9eaf-279dc4735e07.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/c5cde511-dc27-4e66-9eaf-279dc4735e07.jpeg","id":"37f57287-ed0b-4074-b071-d8d53ea1698a"} | 30.11.2023 - Pr can start wk48 | 2023-08-10 22:00 | 2023-09-05 22:00 | 2023-11-29 23:00 | null | null | null | null | null | null | null | null | null | null | null | null
- target 1332 ready for WK48 in SR (300kg) & 100 kg 1333
23.11.2023 pending official PO FOC from Levent / Cem
24.11.2023 - bag ex hyspec WK47 +1-2 wk delivery
17.11.2023 Filling gears & tool modification drawing on wk46, +2 week for delivery
06.11.2023 Design pending, drawings of new tooling would be available WK45
23.10.2023 - redesign of top PUR, BAG, Port area, Z shut off based on green sketch
19.10.2023 - To redesign of the bag at GH cost - BZ50897
18.10.2023 - TC produced 2 pcs, used tools and bag for BZ29289, green oversize (Robert Kobielusz)
19.09.2023 - pending PO 10 pcs FOC (Cem)
14.09.2023 - shipment by Raben connected with Linz mixes, pick up schedule 15.09 ETA 19.09, to be repacked 20.09 and sent to TC
07.09.2023 - 3 pcs of another pattern BZ50897 to be pressed in TC
11.08.2023 1st dwg
(** Tooling order received 28/08/2023 ** AMM)
(** Tooling available ex Hyspec 30/11/2023 ** AMM)
0 | 318 | null |  | 318 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-09-08 09:27 | 2023-09-08 09:27 | 36 | 36 | 2 | FALSE | 60591fac-4779-4589-8d10-566699303617 | null | FCVI-BIONIC | VI-BIONIC | Viso | 113046 | Huta Stalowa Wola | Poland | Europe | SR | 10 | α – Alpha | RFQ | {"type":"thumbnail","fileName":"063d1c62-25d8-4643-8b8d-df90c8b1ff1d.png","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/063d1c62-25d8-4643-8b8d-df90c8b1ff1d.png","id":"837a519d-bfc3-4f2b-88b3-6b9b877656a6"} | BF00430 new shape for Bionic on Flat Face for narrow mold and special tolerance to handle on product design. Volume to confirm. Design is still under fine-tuning (08th Sept 23). | 2023-05-17 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null | null
0 | 319 | null |  | 319 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 16:23 | 2023-09-18 00:53 | 40 | 12 | 7 | FALSE | 91341c1a-4a72-462f-b2d6-3ec5665d11df | null | FCPS-3926HB | PK18290 | Purge Plugs | 124089 | GV DO BRASIL | Brazil | South America | RJ | 4 | α – Alpha | Complete | {"type":"thumbnail","fileName":"32719c63-ab13-46f3-94f4-d7d03eda9354.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/32719c63-ab13-46f3-94f4-d7d03eda9354.jpeg","id":"a085d30d-7845-41fa-ac59-1ec4bf4ef5d0"} | PATTERN !!! PK18290 | 2023-04-26 22:00 | 2023-05-03 22:00 | 2023-06-01 22:00 | 2023-07-02 22:00 | null | 2023-07-23 22:00 | 2023-08-06 22:00 | 2023-08-24 22:00 | null | null | null | null | null | null | null
Lauch Code FCPS-3926HB
27.04.2023 1st dwg
0 | 320 | null |  | 320 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-09-18 09:29 | 2023-09-18 09:29 | 12 | 12 | 2 | FALSE | ca75a50e-3127-4968-8744-fbe5a2cdd513 | null | FCVI-DURASLEEVECS | VI-DURASLEEVECS | Viso | 115218 | COLAKOGLU | Turkey | Europe | SR | 10 | α – Alpha | PO | {"type":"thumbnail","fileName":"8b285d4f-8030-4a24-82a0-97ddbb90cfac.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/8b285d4f-8030-4a24-82a0-97ddbb90cfac.jpeg","id":"dcb13a38-435f-446c-8f01-907c3568eb36"} | PATTERN !!! BZ50921 - Flex Cold Start | 2023-08-04 22:00 | 2023-09-03 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null
0 | 321 | null |  | 321 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-19 15:15 | 2023-09-18 11:04 | 12 | 12 | 13 | FALSE | cc9cd7fc-c5ff-4fae-a5a0-094e96f412e3 | null | FCVI-DURAFLEXHP+ | BD73437 | Viso | 480048 | VOESTALPINE LINZ 18000900 | Austria | Europe | TC | 25 | β – Beta | Complete | {"type":"thumbnail","fileName":"BD73437.JPG","nativeFile":{},"fieldName":"DrawingImage","serverUrl":"https://vesuvius.sharepoint.com","fieldId":"e781e375-f1a3-4a20-909d-d2c60697c622","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/BD73437.JPG","id":"613c0059-c294-431e-b845-744e1ade9d6f"} | ex DURAFLEX 5M | 2023-05-01 22:00 | 2023-05-31 22:00 | 2023-06-28 22:00 | 2023-09-14 22:00 | null | 2023-09-20 22:00 | 2023-10-01 22:00 | 2023-10-19 22:00 | null | null | null | null | null | null | null
01.06.2023 PO Date
First delivery request for 60 pcs has been placed in S&OP2 on 29/03/2023 and cancelled on 04/04/2023 - Bogdan L.
Tooling Date? duplicated or transffered?
2nd dwg revision 02.05.2023
1st dwg 28.04.2023
0 | 322 | null |  | 322 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 15:04 | 2023-09-18 17:18 | 12 | 12 | 10 | FALSE | 1eeb3b90-6aa8-4c08-aba2-915b62825f03 | null | FCSR-LTECH | KA70769045 | Slidegate Assy. | 103871 | GERDAU CHARQUEADAS | Brazil | South America | SR | 20 | α – Alpha | Pieces on Site | {"type":"thumbnail","fileName":"b75e9f2c-fd6e-4845-805d-02b673ed6cf7.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/b75e9f2c-fd6e-4845-805d-02b673ed6cf7.jpeg","id":"f197cdb3-b9ee-40eb-bd31-0becc50c58ff"} | 31.08.2023 transferred to Kokotow 20pcs | 2023-03-14 23:00 | 2023-03-29 22:00 | 2023-06-15 22:00 | 2023-08-30 22:00 | null | 2023-10-29 23:00 | null | null | null | null | null | null | null | null | null
30.08.2023 20 pcs on alternative raw materials packed, marked on green label (SR3355750; SR3355751)
current kiln 5th - pressed WK28, fired WK29/30, impregnation WK31/32
DVB0254000 - raw plate
23.08.2023 pending assembly
0 | 323 | null |  | 323 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-02-21 12:29 | 2023-09-19 15:13 | 12 | 12 | 6 | TRUE | b09a761b-af70-4f1b-87eb-6ddd5f081498 | null | FCPS-OPTIFLOW+ | PQ21408 | Purge Plugs | 113709 | MARIENHÜTTE A 18560910 | Austria | Europe | SR | 10 | α – Alpha | RFQ | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][7]_[PQ21408][1]_[3].jpg"} | to check qty | 2023-03-27 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null | null
28.03.2023 - 1st dwg
0 | 324 | null |  | 324 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-09-19 15:15 | 2023-09-19 15:15 | 12 | 12 | 1 | FALSE | fd89c5f1-74db-47ce-9fe8-e4f54c41006b | null | FCPS-OPTIFLOW+ | PQ21770 | Purge Plugs | 100587 | ArcelorMittal Eisenhüttenstadt | Germany | Europe | SR | 10 | α – Alpha | RFQ | null | to check qty | 2023-07-13 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null | null
pending PO
0 | 325 | null |  | 325 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-09-19 15:20 | 2023-09-19 15:20 | 12 | 12 | 1 | FALSE | b5d099cd-c73c-40b0-8d1f-663b72295a7d | null | FCPS-OPTIFLOW+ | PQ21531 | Purge Plugs | 165320 | Rustavi Steel | Georgia | Europe | SR | 10 | α – Alpha | RFQ | null | to check qty / RFQ Date | 2023-07-31 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null | null
PL14628
1st dwg
0 | 326 | null |  | 326 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-09-19 15:26 | 2023-09-19 15:26 | 12 | 12 | 1 | FALSE | a928d642-c921-4b2b-933a-0d0c25ffba61 | null | FCPS-OPTIFLOW+ | PQ20517 | Purge Plugs | 113315 | CELSA BARCELONA | Spain | Europe | SR | 10 | α – Alpha | RFQ | null | to check qty | 2023-09-04 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null | null
to correct RFQ Date
1st dwg
0 | 327 | null |  | 327 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-09-19 16:03 | 2023-09-19 15:29 | 12 | 12 | 2 | FALSE | 46b9700d-6b0b-4636-b322-302d85cfcae8 | null | FCPS-OPTIFLOW+ | PL13133 | Purge Plugs | 118716 | ERDEMIR EREGLI | Turkey | Europe | SR | 10 | α – Alpha | RFQ | null | PATTERN !!! PL13224 / PL13190 | 2023-09-04 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null | null
to check qty
to correct RFQ Date
1st dwg - to be added
0 | 328 | null |  | 328 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 16:18 | 2023-09-19 15:31 | 12 | 12 | 7 | FALSE | fdc42241-295e-41ca-aeca-61234e75d055 | null | FCPS-OPTICLEAN+ | PL14297 | Purge Plugs | 100850 | TERNI ACCIAI SPEC SPA | Italy | Europe | SR | 10 | α – Alpha | Complete | null | to check qty | 2022-10-25 22:00 | 2022-11-23 23:00 | 2023-01-05 23:00 | 2023-03-07 23:00 | null | 2023-04-11 22:00 | 2023-06-22 22:00 | 2023-06-29 22:00 | null | null | null | null | null | null | null
to correct RFQ Date / PO Date
1st dwg - to be added
0 | 329 | null |  | 329 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 16:19 | 2023-09-19 15:34 | 12 | 12 | 6 | FALSE | 4ff24704-ca60-475c-b219-caf16883bfd8 | null | FCPS-OPTICLEAN+ | PL13984 | Purge Plugs | 120976 | TARANTO | Italy | Europe | SR | 10 | α – Alpha | Complete | null | PATTERN !!! PL13976 | 2022-08-15 22:00 | 2022-08-22 22:00 | 2022-09-05 22:00 | 2022-09-29 22:00 | null | 2022-10-13 22:00 | 2022-11-21 23:00 | 2022-12-18 23:00 | null | null | null | null | null | null | null
to check qty
to correct RFQ Date
1st dwg - to be added
0 | 330 | null |  | 330 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-09-21 07:35 | 2023-09-21 07:35 | 12 | 12 | 1 | FALSE | 3e49f3d9-3655-47c5-af9f-4d8738f8af24 | null | FCVI-DURASLEEVE-LONG | BK63838 | Viso | 137262 | Yehuda - Ashod | Israel | Europe | SR | 10 | α – Alpha | RFQ | null | PATTERN !!! BK63869 - to be checked with Design Team | 2023-09-04 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null | null
to check RFQ Date
to check PO Date
1st dwg - to be added
0 | 331 | null |  | 331 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 16:00 | 2023-09-21 07:49 | 12 | 12 | 5 | FALSE | 02bc7eee-a20a-46ac-af8a-f7831806150c | null | FCVI-CLEANSTOPPER | BP74016 | Viso | 101367 | SSAB Europe Oy Raahe | Finland | Europe | SR | 5 | α – Alpha | Complete | {"type":"thumbnail","fileName":"e18e3fab-b732-4b11-9c94-e2a8a463b0ea.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/e18e3fab-b732-4b11-9c94-e2a8a463b0ea.jpeg","id":"fda9a3bc-8309-4363-b071-d3208a24d798"} | 5 pieces to be tried / 2 pieces tried on week 37. No clear results so far. | 2022-06-27 22:00 | 2022-09-28 22:00 | 2023-01-05 23:00 | 2023-02-22 23:00 | null | 2023-08-14 22:00 | 2023-09-11 22:00 | 2023-09-13 22:00 | null | null | null | null | null | null | null
- to be checked Francisco
PO Date to be checked
Mfg Date - 09.11.2022, 23.02.2023, 07.2023
28.06.2022 1st dwg
0 | 332 | null |  | 332 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-20 03:39 | 2023-09-21 08:00 | 12 | 12 | 3 | FALSE | 4c6fd94c-71f9-4dc2-b9ef-2dc5dd53a37a | null | FCVI-CISO | BP73778 | Viso | 164570 | SISAK | Croatia | Europe | OS | 56 | α – Alpha | PO | {"type":"thumbnail","fileName":"1d7bcc12-0b2e-4c77-9717-a28cd5eabdc7.png","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/1d7bcc12-0b2e-4c77-9717-a28cd5eabdc7.png","id":"24478aa3-7dc0-4a07-9591-4d78f1ad296d"} | PATTERN !!! - BP73778 (TS1292) | 2022-03-29 22:00 | 2023-09-20 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null
21.09.2023 - PO pending
30.03.20222 - 1st dwg
0 | 333 | null |  | 333 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 16:07 | 2023-09-21 21:13 | 12 | 12 | 4 | FALSE | 8caf2869-47c9-48b5-9a74-54e65a82e51a | null | FCVI-DURAFLEX1000L | BC45429 | Viso | 115033 | ArcelorMittal WARSZAWA | Poland | Europe | SR | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"3f83c601-f326-40ac-a941-95d58a902e2d.png","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/3f83c601-f326-40ac-a941-95d58a902e2d.png","id":"76b3edfe-893e-42fa-8e27-058351fc3cec"} | RFQ Date - to be checked | 2022-11-30 23:00 | 2023-02-28 23:00 | 2023-03-28 22:00 | 2023-05-17 22:00 | null | 2023-06-28 22:00 | 2023-07-12 22:00 | 2023-07-19 22:00 | null | null | null | null | null | null | null
PO Date - to be checked
Mfg Date - to be checked
24.06.2020 1st dwg
0 | 335 | null |  | 335 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-04-15 16:12 | 2023-09-21 21:25 | 12 | 58 | 4 | TRUE | e021940e-3872-4ed3-a645-986ec5aba859 | null | FCVI-DURASLEEVE-LONG | BF94743 | Viso | 100217 | Benteler Lingen | Germany | Europe | SR | 10 | α – Alpha | Complete | null | Several pcs used with no issues , customer is happy with the results, | 2023-02-28 23:00 | 2023-04-10 22:00 | 2023-06-01 22:00 | 2023-07-03 22:00 | null | 2023-07-31 22:00 | 2023-09-04 22:00 | 2023-09-27 22:00 | null | null | null | null | null | null | null
new RFQ to reduce the cost and achieve conversion
to check all dates
0 | 336 | null |  | 336 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 11:27 | 2023-09-21 21:29 | 12 | 12 | 3 | FALSE | ee14f509-4ad9-43c0-a8c5-78e47f337420 | null | FCVI-DURASLEEVE-LONG | BK62228 | Viso | 113334 | FERROSTAL | Poland | Europe | SR | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"76480fba-d04b-41b1-9ce2-187162e381b4.png","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/76480fba-d04b-41b1-9ce2-187162e381b4.png","id":"e3c5996f-d0b0-43f0-b896-dd215f4a3b93"} | Several pcs used with no issues , customer is happy with the results | 2023-05-01 22:00 | 2023-05-08 22:00 | 2023-05-22 22:00 | 2023-06-05 22:00 | null | 2023-07-10 22:00 | 2023-07-31 22:00 | 2023-08-09 22:00 | null | null | null | null | null | null | null
to check all Dates
05.09.2023 PO Date~RFQ Date
1st dwg - to be added
0 | 337 | null |  | 337 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-02-21 12:14 | 2023-09-21 21:32 | 12 | 12 | 7 | TRUE | 04b9e5c2-c95f-4d41-af48-f6329ad40b3b | null | FCVI-CISO | BC48696 | Viso | 171656 | AQS | Algeria | Europe | SR | 10 | α – Alpha | Pieces on Site | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[c64d1fa3-5837-4f2e-a9b1-9b47b170cb64][1]_[4].jpeg"} | Still pending | 2023-05-25 22:00 | 2023-06-05 22:00 | 2023-06-29 22:00 | 2023-07-31 22:00 | null | 2023-08-28 22:00 | null | null | null | null | null | null | null | null | null
Commercial issues on PO matching the PCS
Manufacturing ISSUES on Glazing
to check all Dates
1st dwg - to be added
0 | 338 | null |  | 338 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-12-12 19:02 | 2023-09-21 21:35 | 12 | 38 | 6 | FALSE | aef59c91-e72a-4d7a-acca-a4770dbe6f2b | null | FCVI-CISO | BC49124 | Viso | 100217 | Benteler Lingen | Germany | Europe | SR | 10 | α – Alpha | Tool | null | Still pending | 2023-06-26 22:00 | 2023-07-03 22:00 | 2023-09-03 22:00 | null | null | null | null | null | null | null | null | null | null | null | null
Manufacturing ISSUES on Glazing
to check all Dates
1st dwg - to be added
12.12.2023 No tooling order, AMM
0 | 339 | null |  | 339 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-02-02 12:23 | 2023-09-21 21:39 | 12 | 12 | 10 | FALSE | b20273d0-7aba-454a-adfc-650a32de5daf | null | FCVI-DURAFLEX1000L | BC46781 | Viso | 105102 | HENNIGSDORF | Germany | Europe | SR | 5 | α – Alpha | Pieces on Site | {"type":"thumbnail","fileName":"6c66ba7e-adce-4278-9ab8-d69eab5220b2.png","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/6c66ba7e-adce-4278-9ab8-d69eab5220b2.png","id":"81958cc8-f5ab-4b2d-a738-0c2fada24feb"} | 05-06.02.2024 estimated time delivery Monday-Tuesday - Anna Bajorek | 2023-05-18 22:00 | 2023-08-13 22:00 | 2023-11-05 23:00 | 2024-01-31 23:00 | null | 2024-02-05 23:00 | null | null | null | null | 6. Components delay (e.g., cans delay) | null | null | null | null
01.02.2024 5 pcs shipped
30.01.2024 5 pcs packed and ready for shipment - Ilona
25.01.2024 5 pcs after canning, waiting for finishing and QC wall - Dawid Sacha
06.11.2023 with 1301 under concession - 2 tons of rejuvenated 1301 - Fired properties shared
17.10.2023 topic in hand of RFQ to decide if dwg revision or new pattern code. update qty to 5 pcs; corrected PO date + tool/rm date: 12.10.2023 long lead time for cans; agreed air freight improved
06.10.2023 PO?
14.08.2023 trf issued, still pending
19.05.2021 - dwg published
19.03.2021 - 1st dwg
to check all Dates
(** Tooling order received 14/08/2023 ** AMM)
(** Tooling available ex Hyspec 07/09/2023 ** AMM)
0 | 340 | null |  | 340 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-12-12 19:06 | 2023-09-21 21:43 | 12 | 38 | 4 | FALSE | 2a381479-74f3-471d-8a6e-e4dc1f6218dc | null | FCVI-TS01243 | BC48969 | Viso | 480062 | CELSA HUTA OSTROWIEC | Poland | Europe | SR | 10 | α – Alpha | Tool | null | On delay due issues to get EMC to offer | 2023-06-26 22:00 | 2023-07-03 22:00 | 2023-09-03 22:00 | null | null | null | null | null | null | null | null | null | null | null | null
Solution is to offer special discount for one crate trial but still under discusión
to check all Dates
1st dwg - to be added
12.12.2023 No tooling order received, AMM
0 | 341 | null |  | 341 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-25 23:03 | 2023-10-18 11:30 | 12 | 12 | 6 | FALSE | 73223484-83c8-4eb9-ab03-8c82c1b9c54a | null | FCVI-CLEANSTOPPER | BP67333 | Viso | 480048 | VOESTALPINE LINZ 18000900 | Austria | Europe | SR | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"08a91e20-297c-46d7-9322-90245474f954.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/08a91e20-297c-46d7-9322-90245474f954.jpeg","id":"f3190fa3-70ed-4b12-a036-3818946a874b"} | PO Date | 2022-11-08 23:00 | 2023-02-28 23:00 | 2023-05-09 22:00 | 2023-08-07 22:00 | null | 2023-08-28 22:00 | 2023-09-11 22:00 | 2023-09-13 22:00 | null | null | null | null | null | null | null
Mfg Date
09.11.2022 4th dwg revision
0 | 343 | null |  | 343 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-04-25 08:25 | 2023-10-18 13:20 | 40 | 12 | 15 | FALSE | 066ccc18-372b-4fbb-baf7-876121251090 | null | FCSR-LTECH | KA70769040 | Slidegate Assy. | 124089 | GV DO BRASIL | Brazil | South America | SR | 42 | β – Beta | Trial | {"type":"thumbnail","fileName":"2f99563b-2401-4fe9-916c-234195e3a638.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/2f99563b-2401-4fe9-916c-234195e3a638.jpeg","id":"5dccaed0-9e0d-4921-906e-d47dc87d35ac"} | 04.2024 trial | 2023-10-29 23:00 | 2023-11-05 23:00 | 2023-11-21 23:00 | 2023-12-06 23:00 | null | 2024-02-28 23:00 | 2024-04-01 22:00 | null | null | null | null | null | null | null | null
02.2024 pcs on site
18.12.2023 shipping
07.12.2023 42pcs packed SR3495858
29.11.2023 assembly postponed to week 49 (due to priority on Hyundai plates)
22.11.2023 assembly planned for week 48
08.11.2023 to check status of raw plates (alternative rm)
06.11.2023 PO Date in SR
30.10.2023 43 pcs ready (Artur Pachel) green label
DVB025400 with alternative body raws
currently: use LT80 with TS3214 CDT 5 heats maximum
16.03.2023 1st dwg
0 | 344 | null |  | 344 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-25 21:27 | 2023-10-25 21:05 | 12 | 12 | 4 | FALSE | 9310af46-d089-4686-9904-93c295c58eb4 | null | FCVI-UNIVERSALSTOPPER | BP77696 | Viso | 135667 | JSW STEEL - Dolvi Works | India | India | SR | 10 | α – Alpha | PO | {"type":"thumbnail","fileName":"5affe120-af52-4a74-9ac9-26c7ed77c810.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/5affe120-af52-4a74-9ac9-26c7ed77c810.jpeg","id":"d9690f1c-0ea9-4c8b-8277-34820bc2011b"} | Current: 1096 BP98744 | 2023-08-10 22:00 | 2023-08-30 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null
1397/1105 5 pcs vs 1096(GH)/1105 5pcs
"low carbon Si killed", Ca 15-20ppm. Si killed, Al killed, AlSi killed"
31.08.2023 PO mix
11.08.2023 1st dwg
0 | 345 | null |  | 345 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-25 21:59 | 2023-10-25 21:59 | 12 | 12 | 2 | FALSE | d688049f-b030-4873-a75b-2a8631a0368f | null | FCVI-UNIVERSALSTOPPER | BP78272 | Viso | 119039 | SSAB Alabama | USA | NAFTA | MY | null | α – Alpha | RFQ | {"type":"thumbnail","fileName":"9af3f0e1-2bb0-407b-abb1-dca8f8ecd265.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/9af3f0e1-2bb0-407b-abb1-dca8f8ecd265.jpeg","id":"483f21c9-ddf4-482a-a604-3eb421b49730"} | Current: 1096 BP63837 | 2023-10-01 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null | null
1096/1109 vs 1397/1109
02.10.2023 1st dwg
18.08.2023 RFQ submitted
0 | 346 | null |  | 346 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-25 22:08 | 2023-10-25 22:07 | 12 | 12 | 3 | FALSE | 1841a4a3-b999-4e0e-9039-1993f19059db | null | FCVI-UNIVERSALSTOPPER | BP78256 | Viso | 131166 | EZDK-Flat | Egypt | Europe | SR | 10 | α – Alpha | RFQ | {"type":"thumbnail","fileName":"8d20c7f6-747c-4e8c-b425-88c5380b7587.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/8d20c7f6-747c-4e8c-b425-88c5380b7587.jpeg","id":"77bce783-10e7-42a6-811c-4b9a3e945ad7"} | 1096 BP66616 (1096/1105/238) | 2023-09-29 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null | null
1111 BF01420 238 body (trial planned with 1096)
1397/1105 1096 in the seat
1111(238) BP63746 Competitor HighTech, IFGL
Al killed steel - Silicon free
30.09.2023 1st dwg
17.09.2023 RFQ submitted
0 | 347 | null |  | 347 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-25 22:12 | 2023-10-25 22:12 | 12 | 12 | 1 | FALSE | 9c152d20-5383-474f-bdfd-bd1ec02df6bb | null | FCVI-UNIVERSALSTOPPER | BP77654 | Viso | 146609 | EZZ STEEL COMPANY | Egypt | Europe | SR | 10 | α – Alpha | RFQ | null | PATTERN !!! BP78280 | 2023-09-16 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null | null
1096/1109 vs 1397/1105
1111(238) BP63746 Competitor HighTech, IFGL
17.09.2023 RFQ submitted
0 | 348 | null |  | 348 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-25 22:39 | 2023-10-25 22:39 | 12 | 12 | 2 | FALSE | 59933fb5-34ad-44fa-8e26-9105cdbd6105 | null | FCVI-UNIVERSALSTOPPER | BP77654 | Viso | 430556 | TERNIUM - SIDERAR | Argentina | South America | RJ | 10 | α – Alpha | RFQ | {"type":"thumbnail","fileName":"5892b836-4d5e-47e0-b3ee-398e7aa3c5bf.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/5892b836-4d5e-47e0-b3ee-398e7aa3c5bf.jpeg","id":"d2879d6a-c723-473c-a2c6-343648e5113b"} | PATTERN !!! | 2023-10-03 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null | null
Current: 1225 BP68067 (1225/288/238)
1397/1109 and 1397/1109 in the seat
"Low Carbon; Medium Carbon" 14-23ppm Ca (not complete grades)"
04.10.2023 RFQ submitted
0 | 349 | null |  | 349 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-02-21 12:31 | 2023-10-25 22:46 | 12 | 12 | 5 | TRUE | 8e709b08-6a30-4425-a644-a22753f66f0e | null | FCVI-UNIVERSALSTOPPER | BP77654 | Viso | 156474 | TERNIUM BRASIL | Brazil | South America | RJ | 10 | α – Alpha | RFQ | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][7]_[BP77654][1]_[3].jpg"} | Current: ripple 1225 (1111 246) Sept 1225 | 2023-08-06 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null | null
1397GH/1105 with 937 seat (after sept trial of ZrO2)
"Ultra-low Carbon; Low Carbon; Medium Carbon; High Carbon Steel; High Strength, Low Alloy" 8-23 (>25) ppm"
07.08.2023 1st dwg
0 | 350 | null |  | 350 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 15:43 | 2023-10-25 22:55 | 12 | 12 | 6 | FALSE | 6ed2d8b9-c753-4a3f-90d9-77369093608b | null | FCVI-UNIVERSALSTOPPER | BP77654 | Viso | 101764 | Vizag Steel SMS1 | India | India | CL | 10 | α – Alpha | Manufacturing | {"type":"thumbnail","fileName":"7e325f1c-2e40-45b9-aabb-ff2464155e61.png","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/7e325f1c-2e40-45b9-aabb-ff2464155e61.png","id":"08563ae4-e180-45be-9aec-7a7d2518c29b"} | PATTERN !!! RP00139 | 2023-07-30 22:00 | 2023-08-07 22:00 | 2023-09-03 22:00 | 2023-10-09 22:00 | null | null | null | null | null | null | null | null | null | null | null
PO Date - to check
11.2023 - Trial Date
10.10.2023 glaze G150 testing: pieces have been produced in CLMX
*occasional long pre-heat, G77
05.01.2021 4th dwg revision
0 | 351 | null |  | 351 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-25 23:06 | 2023-10-25 23:02 | 12 | 12 | 5 | FALSE | 5f58b6f6-3f94-46db-bdce-430ef42b4582 | null | FCVI-CLEANSTOPPER | BP67952 | Viso | 480048 | VOESTALPINE LINZ 18000900 | Austria | Europe | TC | 10 | β – Beta | Complete | {"type":"thumbnail","fileName":"981496df-59af-44cd-ae7a-2984991c695b.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/981496df-59af-44cd-ae7a-2984991c695b.jpeg","id":"ce99dc63-dac6-40ae-adc8-38cff0308aee"} | PO Date | 2023-05-07 22:00 | 2023-05-14 22:00 | 2023-06-04 22:00 | 2023-08-07 22:00 | null | 2023-08-27 22:00 | 2023-09-10 22:00 | 2023-10-24 22:00 | null | null | null | null | null | null | null
Mfg Date
Trial Date
25.11.2021 3rd dwg revision
0 | 352 | null |  | 352 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-26 07:20 | 2023-10-26 07:20 | 12 | 12 | 2 | FALSE | cecbd5f7-818d-483d-bf41-8635a3baa696 | null | FCVI-CFF | BZ50160 | Viso | 118716 | ERDEMIR EREGLI | Turkey | Europe | SR | 10 | α – Alpha | Manufacturing | {"type":"thumbnail","fileName":"6643ded9-be6d-40f8-a4e7-37aa8e37f9f5.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/6643ded9-be6d-40f8-a4e7-37aa8e37f9f5.jpeg","id":"0f70f30b-ee68-4075-85b4-cdb8e806b5fb"} | PO Date - to check ! | 2023-03-28 22:00 | 2023-05-08 22:00 | 2023-07-23 22:00 | 2023-09-11 22:00 | null | null | null | null | null | null | null | null | null | null | null
25.10.2023 1 piece canned – will go to next process to validate if OK, if yes – grinding + canning + next steps
23.10.2023 pending can welding since WK41
24.07.2023 new bag/concession granted
15.06.2023 sandcore delivery
25.09.2023 4th dwg revision
27/31.06.2023 2nd / 3rd dwg revision
29.03.2023 1st dwg
24.02.2023 RFQ submitted
0 | 353 | null |  | 353 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-02-21 10:48 | 2023-10-26 08:57 | 12 | 12 | 4 | FALSE | d546514a-8677-4af8-a0b8-8a2ba040d688 | null | FCVI-CFF | BZ50129 | Viso | 118716 | ERDEMIR EREGLI | Turkey | Europe | SR | 10 | α – Alpha | Manufacturing | {"type":"thumbnail","fileName":"a3bc8b07-ef58-4ffd-adaa-9f9e2912bb9c.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/a3bc8b07-ef58-4ffd-adaa-9f9e2912bb9c.jpeg","id":"146c2adf-08a1-4dce-a1f5-fe58200fd9bf"} | PATTERN !!! BZ52257 & BZ52265 | 2023-06-26 22:00 | 2023-07-03 22:00 | 2023-08-15 22:00 | 2023-10-24 22:00 | null | null | null | null | null | null | null | null | null | null | null
20.02.2024 PO cancelled / TRF on going
25.10.2023 in progress / we need to remove cans and canning again
23.10.2023 waiting for Glazing since WK41
16.06.2023 local tooling
05.05.2023 waiting for drawings
27.06.2023 3rd dwg revision
05.04.2023 2nd dwg revision
38.03.2023 1st dwg
24.02.2023 RF submitted
0 | 354 | null |  | 354 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-02-21 10:45 | 2023-10-26 09:05 | 12 | 12 | 3 | FALSE | 1f96fcda-0681-4035-a790-64cfefeb338c | null | FCVI-CFF | BZ50178 | Viso | 118716 | ERDEMIR EREGLI | Turkey | Europe | SR | 10 | α – Alpha | Manufacturing | {"type":"thumbnail","fileName":"84a03ba6-2b9f-43ba-97a7-64ac8f0c1b95.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/84a03ba6-2b9f-43ba-97a7-64ac8f0c1b95.jpeg","id":"b0adbda5-7f4f-4c15-a87e-da18cc55f849"} | PATTERN !!! BZ52257 & BZ52265 | 2023-04-10 22:00 | 2023-05-08 22:00 | 2023-06-14 22:00 | 2023-10-24 22:00 | null | null | null | null | null | null | null | null | null | null | null
20.02.2024 PO cancelled / TRF on going
25.10.2023 in progress
23.10.2023 waiting for Glazing since WK41
27.06.2023 dwg revision
28.03.2023 1st dwg
24.02.2023 RFQ submitted
0 | 355 | null |  | 355 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 15:44 | 2023-10-27 19:21 | 12 | 12 | 3 | FALSE | 14de399d-7493-4c8f-a9fe-9197accc6ed6 | null | FCVI-DURAFLEX5M | BD67116 | Viso | 118716 | ERDEMIR EREGLI | Turkey | Europe | SR | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"ccd9a63e-5d6f-457d-925b-0219f8595f21.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/ccd9a63e-5d6f-457d-925b-0219f8595f21.jpeg","id":"27b41277-ebf3-4984-8d19-ff769381555b"} | 11.03.2020 1st dwg | 2020-03-10 23:00 | 2020-04-06 22:00 | 2020-09-10 22:00 | 2020-11-05 23:00 | null | 2020-11-29 23:00 | 2021-02-03 23:00 | 2021-02-24 23:00 | null | null | null | null | null | null | null
0 | 356 | null |  | 356 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-28 13:16 | 2023-10-27 19:44 | 12 | 12 | 3 | FALSE | e5d912a1-52ce-4418-8acb-5ad51aea9ca9 | null | FCVI-DURAFLEX5M | BD68171 | Viso | 102563 | Trinecke Zelezarny | Czechia | Europe | TC | 10 | β – Beta | Complete | {"type":"thumbnail","fileName":"9eba0bdc-c6ce-4232-9650-7689bbfec775.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/9eba0bdc-c6ce-4232-9650-7689bbfec775.jpeg","id":"f092e8a2-cbed-4433-8a4b-78202df9a399"} | 01.07.2021 2nd dwg revision | 2020-07-13 22:00 | 2020-07-26 22:00 | 2021-04-06 22:00 | 2021-04-13 22:00 | null | 2021-05-16 22:00 | 2021-09-30 22:00 | 2021-10-21 22:00 | null | null | null | null | null | null | null
14.07.2020 1st dwg
0 | 357 | null |  | 357 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-27 19:54 | 2023-10-27 19:54 | 12 | 12 | 2 | FALSE | fec5bc51-14e5-4439-9d0d-ae0df0e666e7 | null | FCVI-DURAFLEX5M | BD67074 | Viso | 102563 | Trinecke Zelezarny | Czechia | Europe | TC | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"a4113e0c-256c-4723-9d99-2fbf59fd0524.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/a4113e0c-256c-4723-9d99-2fbf59fd0524.jpeg","id":"6221d28d-1458-449d-b4ef-5d8a7bcd3e62"} | 04.30.2020 1st dwg | 2020-03-03 23:00 | 2020-03-08 23:00 | 2020-03-15 23:00 | 2020-06-04 22:00 | null | 2020-06-07 22:00 | 2020-10-05 22:00 | 2020-10-26 23:00 | null | null | null | null | null | null | null
0 | 358 | null |  | 358 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-08 08:54 | 2023-10-27 20:03 | 12 | 12 | 7 | FALSE | 6cef23c6-2d32-46ef-8991-2eac8b9b482a | null | FCVI-DURAFLEX5M | BC45254 | Viso | 113315 | CELSA BARCELONA | Spain | Europe | SR | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"6885bd95-4c4a-4b48-890e-d442aced0b3f.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/6885bd95-4c4a-4b48-890e-d442aced0b3f.jpeg","id":"d5febe5b-93b7-4216-80fc-6829abf85141"} | PATTERN !!! BC44687 | 2020-01-06 23:00 | 2020-01-12 23:00 | 2020-01-19 23:00 | 2021-03-17 23:00 | null | 2021-04-14 22:00 | 2021-05-31 22:00 | 2021-06-14 22:00 | null | null | null | null | null | null | null
22.11.2019 1st dwg
0 | 359 | null |  | 359 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-27 20:34 | 2023-10-27 20:34 | 12 | 12 | 2 | FALSE | 81d41220-6632-47a6-95a0-1a6c8de923db | null | FCVI-DURAFLEX5M | BD68650 | Viso | 131166 | EZDK-Flat | Egypt | Europe | SR | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"7750e3d5-c3f7-4932-9443-767d2659c767.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/7750e3d5-c3f7-4932-9443-767d2659c767.jpeg","id":"b31c5890-3e6a-4e23-aeb7-7d1a0852b9fe"} | 05.01.2021 2nd dwg revision | 2020-09-08 22:00 | 2021-01-03 23:00 | 2021-01-10 23:00 | 2021-07-26 22:00 | null | 2021-08-13 22:00 | 2022-02-01 23:00 | 2022-02-22 23:00 | null | null | null | null | null | null | null
08.09.2020 1st dwg
0 | 360 | null |  | 360 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-27 21:45 | 2023-10-27 20:44 | 12 | 12 | 4 | FALSE | 92c67577-195f-4407-88ff-2d380920ae95 | null | FCVI-DURAFLEX5M | BD71175 | Viso | 135280 | PEINER TR. PEINE 11750500 | Germany | Europe | SR | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"cf34e39a-61d6-47a9-8d6f-c2a9b7362578.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/cf34e39a-61d6-47a9-8d6f-c2a9b7362578.jpeg","id":"c105abda-772e-4932-af57-726f509aa727"} | 09.02.2022 3rd dwg revision | 2021-06-30 22:00 | 2021-11-23 23:00 | 2021-11-30 23:00 | 2022-01-25 23:00 | null | 2022-02-27 23:00 | 2022-07-03 22:00 | 2022-07-20 22:00 | null | null | null | null | null | null | null
01.07.2021 2nd dwg revision
04.06.2021 1st
0 | 361 | null |  | 361 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-27 20:54 | 2023-10-27 20:54 | 12 | 12 | 2 | FALSE | b1b14efd-777d-44bc-9732-98a87307739b | null | FCVI-DURAFLEX5M | BC46302 | Viso | 113315 | CELSA BARCELONA | Spain | Europe | SR | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"485725c6-2953-40f4-93dd-bc2bfd55d772.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/485725c6-2953-40f4-93dd-bc2bfd55d772.jpeg","id":"b2070eeb-59f7-464c-9871-43e976cd29fe"} | 10.03.2021 2nd dwg revision | 2021-01-21 23:00 | 2021-01-27 23:00 | 2021-02-03 23:00 | 2021-04-06 22:00 | null | 2021-04-28 22:00 | 2021-10-24 22:00 | 2021-11-07 23:00 | null | null | null | null | null | null | null
22.01.2021 1st dwg
0 | 362 | null |  | 362 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-27 21:11 | 2023-10-27 21:11 | 12 | 12 | 2 | FALSE | 3d54ff67-1c23-4d6b-a019-f78b984593b4 | null | FCVI-DURAFLEX5M | BD70151 | Viso | 118716 | ERDEMIR EREGLI | Turkey | Europe | SR | 10 | β – Beta | Complete | {"type":"thumbnail","fileName":"7bffb113-432f-49d4-9b96-b4ea7f4bacff.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/7bffb113-432f-49d4-9b96-b4ea7f4bacff.jpeg","id":"147650ed-2887-4649-b344-736f99a86002"} | 27.05.2022 4th dwg revision | 2021-04-25 22:00 | 2021-12-26 23:00 | 2022-01-16 23:00 | 2022-04-10 22:00 | null | 2022-05-16 22:00 | 2022-07-28 22:00 | 2022-08-15 22:00 | null | null | null | null | null | null | null
08.03.2022 3rd dwg revision
26.04.2021 2nd dwg revision
25.02.2021 1st dwg
0 | 363 | null |  | 363 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-27 21:28 | 2023-10-27 21:27 | 12 | 12 | 2 | FALSE | 6b90d603-2cf4-40cd-a1fa-efc588bea60b | null | FCVI-DURAFLEX5M | BC46757 | Viso | 171656 | AQS | Algeria | Europe | SR | 10 | β – Beta | Complete | {"type":"thumbnail","fileName":"d36aec37-7ce9-4823-bcd9-13fe9b8bfa1f.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/d36aec37-7ce9-4823-bcd9-13fe9b8bfa1f.jpeg","id":"8e7650d0-abc5-4e6e-8eb8-5dd3073d4b91"} | 05.05.2021 1st dwg | 2021-05-04 22:00 | 2021-08-09 22:00 | 2021-10-10 22:00 | 2022-02-07 23:00 | null | 2022-03-20 23:00 | 2022-05-16 22:00 | 2022-06-01 22:00 | null | null | null | null | null | null | null
0 | 364 | null |  | 364 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-27 21:42 | 2023-10-27 21:42 | 12 | 12 | 2 | FALSE | 9ad9dc84-28e3-4f18-b6c5-a1782dd168e9 | null | FCVI-DURAFLEXHP | BC46765 | Viso | 135579 | Liberty Ostrava | Czechia | Europe | TC | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"eee6531f-567d-424b-8595-f6f8f05a7178.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/eee6531f-567d-424b-8595-f6f8f05a7178.jpeg","id":"f342d318-7dab-4d8f-a1ed-848743161521"} | 06.05.2021 1st dwg | 2021-05-05 22:00 | 2022-02-03 23:00 | 2022-02-21 23:00 | 2022-05-20 22:00 | null | 2022-08-07 22:00 | 2022-09-26 22:00 | 2022-10-02 22:00 | null | null | null | null | null | null | null
0 | 365 | null |  | 365 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-14 23:40 | 2023-10-27 21:53 | 12 | 12 | 3 | FALSE | 98d58712-64e4-4a37-b231-d53073df8eb5 | null | FCVI-DURAFLEXHP | BD71183 | Viso | 135280 | PEINER TR. PEINE 11750500 | Germany | Europe | SR | 10 | β – Beta | Complete | {"type":"thumbnail","fileName":"6679f7f0-4c8d-465a-aa67-bac4799af25b.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/6679f7f0-4c8d-465a-aa67-bac4799af25b.jpeg","id":"83f26022-3595-4b47-bc24-45fc6001ccda"} | 04.06.2021 1st dwg | 2021-06-03 22:00 | 2021-11-23 23:00 | 2021-12-01 23:00 | 2022-01-25 23:00 | null | 2022-02-27 23:00 | 2022-05-22 22:00 | 2022-06-09 22:00 | null | null | null | null | null | null | null
0 | 366 | null |  | 366 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-28 12:23 | 2023-10-27 22:05 | 12 | 12 | 3 | FALSE | 06d93104-0467-4afb-9414-167f15486c5c | null | FCVI-DURAFLEX20H | BD71746 | Viso | 480048 | VOESTALPINE LINZ 18000900 | Austria | Europe | TC | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"d7d85e95-4e56-4598-896d-3fcd75baabb9.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/d7d85e95-4e56-4598-896d-3fcd75baabb9.jpeg","id":"68f55ed4-1667-4761-8369-612aabce330f"} | 19.08.2021 1st dwg | 2021-08-18 22:00 | 2021-11-23 23:00 | 2021-12-01 23:00 | 2022-01-25 23:00 | null | 2022-02-05 23:00 | 2022-02-15 23:00 | 2022-02-24 23:00 | null | null | null | null | null | null | null
0 | 367 | null |  | 367 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-27 22:18 | 2023-10-27 22:12 | 12 | 12 | 3 | FALSE | d232a501-0c5f-42a1-be81-1386bc082dfc | null | FCVI-DURAFLEX20M | BD71951 | Viso | 104094 | SIDENOR BASAURI | Spain | Europe | SR | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"0a648633-3e13-4433-87fc-7404de120dca.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/0a648633-3e13-4433-87fc-7404de120dca.jpeg","id":"7ef79977-a276-4bcc-b30f-a08032c4c698"} | 20.09.2021 1st dwg | 2021-09-19 22:00 | 2021-10-03 22:00 | 2021-10-21 22:00 | 2021-11-30 23:00 | null | 2022-01-04 23:00 | 2022-01-16 23:00 | 2022-02-03 23:00 | null | null | null | null | null | null | null
0 | 368 | null |  | 368 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-20 06:09 | 2023-10-27 22:17 | 12 | 12 | 5 | FALSE | 9f312d3a-df29-4002-90fb-cba7dde6bd3c | null | FCVI-DURAFLEXHP | BD71969 | Viso | 104094 | SIDENOR BASAURI | Spain | Europe | TC | 15 | β – Beta | Complete | {"type":"thumbnail","fileName":"cb8c66b1-b2c4-41e5-93a7-04393a54822d.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/cb8c66b1-b2c4-41e5-93a7-04393a54822d.jpeg","id":"0bc1d70a-abbf-4a4a-8277-72ae526a466d"} | 20.09.2021 1st dwg | 2021-09-19 22:00 | 2021-10-03 22:00 | 2021-10-10 22:00 | 2021-11-30 23:00 | null | 2022-01-04 23:00 | 2022-01-19 23:00 | 2022-02-10 23:00 | null | null | null | null | null | null | null
0 | 369 | null |  | 369 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-20 06:10 | 2023-10-27 22:24 | 12 | 12 | 5 | FALSE | 95e6ad22-2d51-4bcf-9496-70acd7bf08d0 | null | FCVI-DURAFLEXHP | BD72777 | Viso | 104094 | SIDENOR BASAURI | Spain | Europe | TC | 4 | β – Beta | Complete | {"type":"thumbnail","fileName":"50d262b9-a5d0-4c55-a3a9-9b12825e9770.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/50d262b9-a5d0-4c55-a3a9-9b12825e9770.jpeg","id":"d4f479c0-2067-4a10-854b-24d718ec06a4"} | 4/30 trialed | 2022-01-25 23:00 | 2022-01-30 23:00 | 2022-02-07 23:00 | 2023-02-22 23:00 | null | 2023-02-28 23:00 | 2023-03-14 23:00 | 2023-04-05 22:00 | null | null | null | null | null | null | null
26.01.2022 1st dwg
0 | 370 | null |  | 370 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 15:46 | 2023-10-27 22:31 | 12 | 12 | 3 | FALSE | eb2d4721-5a71-446b-8e3f-9ed3c31544a4 | null | FCVI-DURAFLEX1000M | BC44992 | Viso | 135579 | Liberty Ostrava | Czechia | Europe | TC | 10 | β – Beta | Complete | {"type":"thumbnail","fileName":"2b6b1978-9d64-483c-8ab5-feced0e6a36a.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/2b6b1978-9d64-483c-8ab5-feced0e6a36a.jpeg","id":"b541157c-a940-43f5-86da-49991ca7ade9"} | 19.07.2021 3rd dwg revision | 2022-04-07 22:00 | 2022-04-14 22:00 | 2022-05-04 22:00 | 2022-06-08 22:00 | null | 2022-06-13 22:00 | 2022-10-09 22:00 | 2022-10-20 22:00 | null | null | null | null | null | null | null
02.02.2021 2nd dwg revision
11.03.2020 1st dwg
0 | 371 | null |  | 371 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-28 12:39 | 2023-10-28 12:39 | 12 | 12 | 2 | FALSE | f410a26c-c3e9-4f04-8863-a47ec1b59a05 | null | FCVI-DURAFLEX1000H | BD69286 | Viso | 100902 | ArcelorMittal Steel Vanderbijlpark | South Africa Republic | Europe | TC | 60 | β – Beta | Complete | {"type":"thumbnail","fileName":"1171c7de-b019-47b1-993e-b245e824b8f0.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/1171c7de-b019-47b1-993e-b245e824b8f0.jpeg","id":"93d941f0-cc0f-46a5-aa01-b4f5218882bc"} | 27.07.2021 2nd dwg revision | 2021-10-26 22:00 | 2021-12-08 23:00 | 2021-12-14 23:00 | 2022-02-03 23:00 | null | 2022-04-10 22:00 | 2022-05-31 22:00 | 2022-06-27 22:00 | null | null | null | null | null | null | null
12.11.2020 1st dwg
0 | 372 | null |  | 372 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-28 12:52 | 2023-10-28 12:52 | 12 | 12 | 2 | FALSE | 9d363aae-8901-41a9-adab-fa266abe4e76 | null | FCVI-DURAFLEX1000M | BC44992 | Viso | 135579 | Liberty Ostrava | Czechia | Europe | TC | 10 | β – Beta | Complete | {"type":"thumbnail","fileName":"1f1258c4-88a9-40a9-8490-f93bd139ab72.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/1f1258c4-88a9-40a9-8490-f93bd139ab72.jpeg","id":"adf6450a-e446-434c-a6e3-8f2bb8795920"} | 19.07.2021 3rd dwg revision | 2020-03-10 23:00 | 2020-10-14 22:00 | 2020-10-28 23:00 | 2020-12-02 23:00 | null | 2020-12-07 23:00 | 2021-01-14 23:00 | 2021-01-28 23:00 | null | null | null | null | null | null | null
02.02.2021 2nd dwg revision
11.03.2020 1st dwg
0 | 373 | null |  | 373 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-28 12:59 | 2023-10-28 12:59 | 12 | 12 | 2 | FALSE | 7ec859e8-255f-41e2-8af2-f11aa7225fcf | null | FCVI-DURAFLEX1000H | BD68619 | Viso | 166080 | NLMK LIPETSK | Russia | Europe | TC | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"0f8ba692-466b-492d-94a4-89b5f09ebb95.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/0f8ba692-466b-492d-94a4-89b5f09ebb95.jpeg","id":"c98c0a88-d1a8-43be-b975-8003e6b204c8"} | 13.11.2020 2nd dwg revision | 2020-09-03 22:00 | 2020-11-09 23:00 | 2020-11-13 23:00 | 2021-03-21 23:00 | null | 2021-04-20 22:00 | 2021-05-23 22:00 | 2021-06-09 22:00 | null | null | null | null | null | null | null
04.09.2020 1st dwg
0 | 374 | null |  | 374 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-31 08:46 | 2023-10-29 20:04 | 12 | 12 | 3 | FALSE | 4981d481-a1ff-48fb-a920-d74d3004f857 | null | FCVI-DURASLEEVE-FLAT | BZ44684 | Viso | 104251 | British Steel Scunthorpe | United Kingdom | Europe | SR | 20 | α – Alpha | Complete | {"type":"thumbnail","fileName":"3c9123d8-1081-4a10-858e-1a2c7216b6d7.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/3c9123d8-1081-4a10-858e-1a2c7216b6d7.jpeg","id":"7292ad87-4237-437e-b620-a33d31b74058"} | 22.10.2020 1st dwg | 2020-10-21 22:00 | 2021-02-01 23:00 | 2021-04-14 22:00 | 2021-08-22 22:00 | null | 2022-02-28 23:00 | 2022-08-21 22:00 | 2022-09-14 22:00 | null | null | null | null | null | null | null
0 | 375 | null |  | 375 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-29 20:12 | 2023-10-29 20:12 | 12 | 12 | 2 | FALSE | 33985e91-34d2-46d5-9333-6c867334f88c | null | FCVI-DURASLEEVE-FLAT | BZ48123 | Viso | 110153 | ArcelorMittal Avilés | Spain | Europe | SR | 20 | α – Alpha | Complete | {"type":"thumbnail","fileName":"328e5855-72b9-44bc-88ef-7132e9348827.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/328e5855-72b9-44bc-88ef-7132e9348827.jpeg","id":"886b65bd-1386-422d-a293-c103e4767015"} | 04.02.2022 1st dwg | 2022-02-03 23:00 | 2022-04-06 22:00 | 2022-05-26 22:00 | 2022-07-07 22:00 | null | 2022-07-19 22:00 | 2022-07-25 22:00 | 2022-08-11 22:00 | null | null | null | null | null | null | null
0 | 376 | null |  | 376 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-29 20:22 | 2023-10-29 20:22 | 12 | 12 | 2 | FALSE | dfcbdac6-5146-46a2-8638-0da7c0699cd4 | null | FCVI-DURASLEEVE-NNS | BF95583 | Viso | 165611 | Baotou Iron & Steel (CSP) | China | China | SZ | 20 | α – Alpha | Complete | {"type":"thumbnail","fileName":"f3f64342-0402-4fd8-9d62-a27ac2e75e9a.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/f3f64342-0402-4fd8-9d62-a27ac2e75e9a.jpeg","id":"1761b270-acb7-45be-916f-a4f3065a2c6e"} | 30.06.2021 1st dwg | 2021-06-29 22:00 | 2021-07-14 22:00 | 2021-09-19 22:00 | 2022-02-10 23:00 | null | 2022-03-03 23:00 | 2022-04-03 22:00 | 2022-04-21 22:00 | null | null | null | null | null | null | null
0 | 377 | null |  | 377 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 12:34 | 2023-10-29 20:30 | 12 | 12 | 3 | FALSE | 62391dd8-e9bd-4afa-a440-390b41b0f8b1 | null | FCVI-DURASLEEVE-FLAT | BF97225 | Viso | 100850 | TERNI ACCIAI SPEC SPA | Italy | Europe | SR | 20 | α – Alpha | Complete | {"type":"thumbnail","fileName":"2c939c0c-f34f-402d-8553-efd147b96349.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/2c939c0c-f34f-402d-8553-efd147b96349.jpeg","id":"13c21622-6477-40fb-8fa5-80c726d1bd77"} | 01.03.2022 1st dwg | 2022-02-28 23:00 | 2022-04-05 22:00 | 2022-04-14 22:00 | 2022-05-05 22:00 | null | 2022-06-26 22:00 | 2022-10-16 22:00 | 2022-11-06 23:00 | null | null | null | null | null | null | null
0 | 378 | null |  | 378 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 12:34 | 2023-10-30 06:55 | 12 | 12 | 4 | FALSE | dd27b277-15f8-46a5-9dc9-6d9cf4192c3e | null | FCVI-DURASLEEVE-FLAT | BZ47422 | Viso | 114834 | ANSHAN NO 2 | China | China | SZ | 20 | α – Alpha | Complete | {"type":"thumbnail","fileName":"38a8b580-5105-4342-88fd-59775ee35503.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/38a8b580-5105-4342-88fd-59775ee35503.jpeg","id":"add81fc2-b7f3-49fe-b1e3-2c32638267d7"} | 12.10.2021 1st dwg | 2021-10-11 22:00 | 2022-03-20 23:00 | 2022-05-19 22:00 | 2022-07-07 22:00 | null | 2022-09-18 22:00 | 2022-09-27 22:00 | 2022-10-13 22:00 | null | null | null | null | null | null | null
0 | 379 | null |  | 379 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-10-30 20:56 | 2023-10-30 07:05 | 12 | 12 | 4 | FALSE | 91b9e7fc-d961-44cd-babe-a68143af4040 | null | FCVI-DURASLEEVE-NNS | BF96318 | Viso | 131832 | Nucor Decatur | USA | NAFTA | CH | 20 | α – Alpha | Complete | {"type":"thumbnail","fileName":"f994406b-0044-4fff-bac1-9c590e3ae77d.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/f994406b-0044-4fff-bac1-9c590e3ae77d.jpeg","id":"5ce271e8-3cbf-49d0-890b-c0d340b0c6f0"} | 19.10.2021 1st dwg | 2021-10-18 22:00 | 2021-11-04 23:00 | 2022-01-04 23:00 | 2022-02-16 23:00 | null | 2022-02-28 23:00 | 2022-03-21 23:00 | 2022-05-08 22:00 | null | null | null | null | null | null | null
0 | 380 | null |  | 380 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 16:27 | 2023-10-30 07:10 | 12 | 12 | 6 | FALSE | f6584aff-3bcb-483f-b7a5-378e680b617a | null | FCVI-DURASLEEVE-NNS | BF96847 | Viso | 131832 | Nucor Decatur | USA | NAFTA | CH | 20 | β – Beta | Complete | {"type":"thumbnail","fileName":"78ffca25-999e-46bb-acdd-5e35d61e7697.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/78ffca25-999e-46bb-acdd-5e35d61e7697.jpeg","id":"609d7c9b-b87c-473b-aec7-8c5bafa58b4d"} | 12.01.2022 1st dwg | 2022-01-11 23:00 | 2022-01-20 23:00 | 2022-03-19 23:00 | 2022-05-24 22:00 | null | 2022-06-04 22:00 | 2022-09-15 22:00 | 2022-10-05 22:00 | null | null | null | null | null | null | null
0 | 381 | null |  | 381 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 12:33 | 2023-10-30 07:53 | 12 | 12 | 3 | FALSE | ecce7816-0037-4c89-b2aa-07827895a9a3 | null | FCVI-DURASLEEVE-LONG | BF99668 | Viso | 200034 | Evraz Rocky Mountain Steel | USA | NAFTA | MY | 20 | α – Alpha | Complete | {"type":"thumbnail","fileName":"f0907c47-7328-440d-8390-f02f9a2b4221.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/f0907c47-7328-440d-8390-f02f9a2b4221.jpeg","id":"7a9aa410-56f9-4f5d-b33c-ef570f0f5d09"} | MYV3150174 | 2023-01-02 23:00 | 2023-01-16 23:00 | 2023-03-13 23:00 | 2023-04-12 22:00 | null | 2023-04-26 22:00 | 2023-05-17 22:00 | 2023-06-02 22:00 | null | null | null | null | null | null | null
WK16 Trial
13.04.2023 Mfg
17.01.2023 PO
09.05.2023 4th dwg revision
24.01.2023 3rd dwg revision
03.01.2023 2nd dwg revision
19.12.2022 1st dwg
0 | 382 | null |  | 382 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 12:33 | 2023-10-30 08:17 | 12 | 12 | 4 | FALSE | 6618cc94-f688-4389-ab25-1e8c4aaf0b26 | null | FCVI-DURASLEEVE-NNS | BF97258 | Viso | 112873 | Handan CSP | China | China | SZ | 20 | α – Alpha | Complete | {"type":"thumbnail","fileName":"ffadb60e-6ea7-4c3f-8d84-57979be25998.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/ffadb60e-6ea7-4c3f-8d84-57979be25998.jpeg","id":"9102867c-fc0c-4621-92e3-24eaf14be4fa"} | 03.03.2022 1st dwg | 2022-03-02 23:00 | 2022-03-31 22:00 | 2022-04-14 22:00 | 2022-05-09 22:00 | null | 2022-05-29 22:00 | 2022-06-15 22:00 | 2022-06-30 22:00 | null | null | null | null | null | null | null
0 | 383 | null |  | 383 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 12:32 | 2023-10-30 08:29 | 12 | 12 | 3 | FALSE | 3bdb8dff-97c7-4e72-8d1d-fc5016ca277a | null | FCVI-DURASLEEVE-NNS | BF97258 | Viso | 112873 | Handan CSP | China | China | SZ | 20 | β – Beta | Complete | {"type":"thumbnail","fileName":"c5ed6b57-1f39-4335-a8a1-454566b51981.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/c5ed6b57-1f39-4335-a8a1-454566b51981.jpeg","id":"ef699d95-e5e3-4f9f-8f24-69fa4429fdb8"} | 03.03.2022 1st dwg | 2022-03-02 23:00 | 2022-06-13 22:00 | 2022-07-28 22:00 | 2022-09-04 22:00 | null | 2022-09-24 22:00 | 2022-10-09 22:00 | 2022-10-20 22:00 | null | null | null | null | null | null | null
0 | 384 | null |  | 384 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 12:29 | 2023-10-30 08:54 | 12 | 12 | 4 | FALSE | 1f7ce1bd-5387-473b-b833-7d91bf8297f2 | null | FCVI-DURASLEEVE-NNS | BF97498 | Viso | 150589 | Cleveland-Cliffs Butler | USA | NAFTA | CH | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"48450c1e-a814-4042-bd34-587d5604772a.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/48450c1e-a814-4042-bd34-587d5604772a.jpeg","id":"ad6888dc-d641-42b3-bae4-3cfbb71abade"} | 16.03.2023 New trial crate at ATS waiting for schedule to run pieces. Customer should have WK13/14 on site. Piece ran by customer without notice - to retrial | 2022-04-04 22:00 | 2022-04-28 22:00 | 2022-05-24 22:00 | 2022-06-02 22:00 | null | 2022-10-23 22:00 | 2023-03-15 23:00 | 2023-04-06 22:00 | null | null | null | null | null | null | null
25.05.2022 2nd dwg revision
05.04.2022 1st dwg
18.03.2022 RFQ submitted
0 | 385 | null |  | 385 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 12:31 | 2023-10-30 09:13 | 12 | 12 | 3 | FALSE | 7b1f9548-8cb9-423e-8685-554d03e3a052 | null | FCVI-DURASLEEVE-FLAT | BZ48669 | Viso | 112907 | Shaoguan | China | China | SZ | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"2a93e73a-3b38-4eae-a1fa-394514c9cc5c.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/2a93e73a-3b38-4eae-a1fa-394514c9cc5c.jpeg","id":"9cf0789e-1e68-497f-9b23-0d259b7cb323"} | 22.06.2022 1st dwg | 2022-06-21 22:00 | 2022-07-06 22:00 | 2022-08-13 22:00 | 2022-09-04 22:00 | null | 2022-09-15 22:00 | 2022-10-09 22:00 | 2022-10-16 22:00 | null | null | null | null | null | null | null
0 | 386 | null |  | 386 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 12:31 | 2023-10-30 09:25 | 12 | 12 | 4 | FALSE | f15abcd5-f165-4cc4-aa4b-53a4076e9d67 | null | FCVI-DURASLEEVE-FLAT | BF98249 | Viso | 128299 | JIUQUAN IRON + STEEL GROUP Cø | China | China | SZ | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"76b768b7-6687-48de-b4ea-be6fa702b7c6.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/76b768b7-6687-48de-b4ea-be6fa702b7c6.jpeg","id":"aafd93ad-6355-47cc-8d5f-524112507003"} | 08.07.2022 1st dwg | 2022-07-07 22:00 | 2022-07-14 22:00 | 2022-08-24 22:00 | 2022-09-04 22:00 | null | 2022-09-19 22:00 | 2022-10-14 22:00 | 2022-10-24 22:00 | null | null | null | null | null | null | null
0 | 387 | null |  | 387 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-07-03 12:52 | 2023-10-30 11:56 | 12 | 12 | 12 | FALSE | 3ac5750d-5288-4ef8-81e6-d5c25a4ad755 | null | FCSR-LTECH | TKA71494065 | Slidegate Assy. | 151200 | Aperam Châtelet | Belgium | Europe | SR | 400 | α – Alpha | Complete | {"type":"thumbnail","fileName":"a5e6744a-d157-4dd8-934a-46fa94baf442.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/a5e6744a-d157-4dd8-934a-46fa94baf442.jpeg","id":"97becd87-fc11-4fd9-8f9a-3004baebb04f"} | order cancelled due to complaints | 2023-08-23 22:00 | 2023-08-31 22:00 | 2023-11-13 23:00 | 2023-12-27 23:00 | null | 2024-01-31 23:00 | 2024-01-31 23:00 | 2024-01-31 23:00 | null | null | null | null | null | null | null
25.01.2024 one more crate to pack for shipping week 7 - to pack all WIP, can be less than 80pcs
24.01.2024 80pcs packed - to check HU
15.01.2024 160pcs packed HU 3000004954 ; HU 3000004957
12.01.2024 160pcs packed HU 3000004441; HU 3000004440
28.12.2023 target to be packed ? - to check with Joanna G.
19.11.2023 412pcs cooked
15.11.2023 412pcs curing
14.11.2023 412pcs pressed
01.09.2023 PO Date ~RFQ Date
WK45 press - 400pcs / total 960pcs
DVB0256000 – LV12 CDT 3378/3444
29.05.2020 1st dwg
0 | 388 | null |  | 388 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-07-04 10:19 | 2023-10-30 11:59 | 12 | 12 | 14 | FALSE | 853b4788-7561-4b50-bddb-ba4861105730 | null | FCSR-LTECH | TKA71494065 | Slidegate Assy. | 151200 | Aperam Châtelet | Belgium | Europe | SR | 480 | β – Beta | Complete | {"type":"thumbnail","fileName":"ee655feb-7037-41d4-ba84-f53fcee4c69c.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/ee655feb-7037-41d4-ba84-f53fcee4c69c.jpeg","id":"f3806344-e8a7-4314-8f2f-4f4d4a28c90d"} | 18.01.2024 orders cancelled 10.01.2024 | 2023-08-23 22:00 | 2023-08-31 22:00 | 2023-12-21 23:00 | 2024-01-17 23:00 | null | 2024-01-17 23:00 | 2024-01-17 23:00 | 2024-01-17 23:00 | null | 2. Customer Loss of Interest or Push for Trial | null | null | null | null | null
01.09.2023 RFQ Date ~ PO Date
480-560 pcs / 960 pcs
DVB0256000 – LV12 CDT 3378/3444
29.05.2020 1st dwg
0 | 389 | null |  | 389 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-04-25 08:53 | 2023-10-30 12:15 | 12 | 12 | 16 | FALSE | 7d689bde-062b-486f-b8b1-8eaa1f4c596b | null | FCSR-LTECH | KK32619050 | Slidegate Assy. | 200099 | Gerdau Whitby - USD | Canada | NAFTA | SR | 319 | β – Beta | Pieces on Site | {"type":"thumbnail","fileName":"b6fd437e-7b4e-4ff7-a2ac-8b77e28bfccd.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/b6fd437e-7b4e-4ff7-a2ac-8b77e28bfccd.jpeg","id":"5bca06dc-082a-45cb-869b-06749669fe9f"} | 04.2024 pcs on site - to check | 2023-10-17 22:00 | 2023-10-24 22:00 | 2023-12-06 23:00 | 2024-01-30 23:00 | null | 2024-04-10 22:00 | null | null | null | null | null | null | null | null | null
in transit
360 pcs ordered / 319 pcs shipped
31.01.2024 79pcs packed HU 3000008300
18.01.2024 120pcs more to pack
16.01.2024 240pcs packed HU 3000005015, HU 3000005016
07.12.2023 packing planned for week3
07.12.2023 to press beginning on December 8th kiln - week50
12.2023 Mix ready for pressing, pressing plan for week 50 25.10.2023 PO date ~ RFQ Date
raw plate SK03487000
0 | 390 | null |  | 390 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-07-03 12:53 | 2023-10-30 12:21 | 12 | 12 | 18 | FALSE | df525b0c-26e7-4c28-b148-d1569871ce07 | null | FCSR-LTECH | KA74159040 | Slidegate Assy. | 147723 | ArcelorMittal Long Products Canada-Ouest | Canada | NAFTA | SR | 310 | β – Beta | Complete | {"type":"thumbnail","fileName":"5ee12ce6-c9a9-437b-af8a-1a2d84899b72.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/5ee12ce6-c9a9-437b-af8a-1a2d84899b72.jpeg","id":"8781c7e3-20c1-41d3-b165-773296fa738d"} | 24.01.2024 96pcs packed HU 300006276 | 2023-10-17 22:00 | 2023-10-24 22:00 | 2023-11-28 23:00 | 2024-01-23 23:00 | null | 2024-04-03 22:00 | 2024-05-01 22:00 | 2024-05-22 22:00 | null | null | null | null | null | null | null
24.01.2024 94pcs packed HU 300006275
23.01.2024 120pcs packed HU 300006563
18.01.2024 310pcs to pack
07.12.2023 pressing week 50, packing planned for week 3
04.12.2023 start mfg to press beginning of December 8th kiln
29.11.2023 order is reduced to 310 pcs (to add 50pcs SK05482000 instead)
25.10.2023 PO date ~ RFQ Date
raw plate: DVB0272000
0 | 391 | null |  | 391 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-08-08 11:55 | 2023-10-30 12:23 | 12 | 116 | 11 | FALSE | 9109f077-33f8-4105-9a0e-4d9ca1615845 | null | FCSR-LTECH | KA76204 | Slidegate Assy. | 126582 | DNEPROSTEEL | Ukraine | Europe | SR | 20 | β – Beta | Pieces on Site | {"type":"thumbnail","fileName":"b491bfb8-c920-4f83-9c12-b1cbfbd772c5.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/b491bfb8-c920-4f83-9c12-b1cbfbd772c5.jpeg","id":"acf769a2-c96a-4a2b-b7e5-f23554783fc7"} | planned arrival 25.07.2024? | 2023-10-02 22:00 | 2023-10-09 22:00 | 2024-04-02 22:00 | 2024-07-02 22:00 | null | 2024-07-24 22:00 | null | null | null | null | null | null | null | null | null
11.07.2024 shipment HU 3000044897 + HU 3000044898
03.07.2024 packing + 10 pcs to be added
16.04.2024 curing
15.04.2024 pressing 29pcs
03.04.2024 mixing
9th kiln (after Launch)
03.04.2024 RM
18.01.2024 production planned for week 5 - beginning of February
29.01.2024 Expected
22.01.2024 RM Date
10.10.2023 PO date ~RFQ Date
0 | 392 | null |  | 392 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-07-04 11:22 | 2023-10-30 12:30 | 12 | 12 | 7 | FALSE | ad1c896c-56e2-47df-ab9a-9979a751d1bd | null | FCSR-FTECHG2 | KA78564090 | Slidegate Assy. | 147170 | Hyundai | South Korea | North Asia | SR | 50 | α – Alpha | Complete | {"type":"thumbnail","fileName":"ce7304da-890c-4049-968f-7a208a3f0d26.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/ce7304da-890c-4049-968f-7a208a3f0d26.jpeg","id":"e53405cd-a5f5-4276-99d6-e69ccbd4409c"} | entire production scrapped !! - renewed 12.02 pressing | 2023-10-02 22:00 | 2023-10-17 22:00 | 2023-10-22 22:00 | 2023-11-28 23:00 | null | 2023-11-28 23:00 | 2023-11-28 23:00 | 2023-11-28 23:00 | null | null | null | null | null | null | null
29.11.2023 pending assembly (40pcs agreed by Technology and R&D)
51pcs fetling 27.11.2023
83pcs carbonization 24.11.2023
83pcs impregnated 21.11.2023
100pcs cooked 19.11.2023
100pcs cured 15.11.2023
105pcs pressed 26.10.2023
PO date 18.10.2023
03.10.2023 1st dwg
0 | 393 | null |  | 393 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 12:31 | 2023-10-30 15:10 | 12 | 12 | 6 | FALSE | 258cae1b-4ba4-44d7-9fe0-d00f551cc0b6 | null | FCSR-LTECH | TKA70983055 | Slidegate Assy. | 480062 | CELSA HUTA OSTROWIEC | Poland | Europe | SR | 20 | α – Alpha | Complete | {"type":"thumbnail","fileName":"854a0aa3-b940-40e9-b602-c0c4a283a4f4.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/854a0aa3-b940-40e9-b602-c0c4a283a4f4.jpeg","id":"82d890a1-2911-4567-9dbf-ead1b4a93221"} | 26.08.2020 1st dwg | 2020-08-25 22:00 | 2020-09-03 22:00 | 2020-11-04 23:00 | 2020-11-29 23:00 | null | 2021-01-06 23:00 | 2021-03-14 23:00 | 2021-03-30 22:00 | null | null | null | null | null | null | null
0 | 394 | null |  | 394 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 12:31 | 2023-10-30 15:15 | 12 | 12 | 5 | FALSE | b6f1e217-547e-4192-bd2b-c68ef983a090 | null | FCSR-LTECH | TKA70983060 | Slidegate Assy. | 100850 | TERNI ACCIAI SPEC SPA | Italy | Europe | SR | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"2ab8f702-56d2-4144-ae75-1c9e15f79e52.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/2ab8f702-56d2-4144-ae75-1c9e15f79e52.jpeg","id":"2dad266e-2193-46ce-9dfd-ead2bc3606ad"} | 26.08.2020 1st dwg | 2020-08-25 22:00 | 2020-09-28 22:00 | 2020-11-11 23:00 | 2021-01-07 23:00 | null | 2021-01-11 23:00 | 2021-09-18 22:00 | 2021-09-29 22:00 | null | null | null | null | null | null | null
0 | 395 | null |  | 395 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 12:07 | 2023-10-30 16:56 | 12 | 12 | 3 | FALSE | f18df4f5-f379-4736-a3c6-d693bd87694d | null | FCSR-LTECH | TKA72047050 | Slidegate Assy. | 126593 | S.A.M. Neuves Maisons | France | Europe | SR | 25 | α – Alpha | Complete | {"type":"thumbnail","fileName":"2c1a6f1c-38b5-4679-b90a-73b212ff9d23.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/2c1a6f1c-38b5-4679-b90a-73b212ff9d23.jpeg","id":"e82b8b59-0984-4c00-be7e-5704fe4e4608"} | 10.09.2020 1st dwg | 2020-09-09 22:00 | 2020-09-27 22:00 | 2020-10-22 22:00 | 2020-12-03 23:00 | null | 2020-12-10 23:00 | 2021-01-06 23:00 | 2021-01-28 23:00 | null | null | null | null | null | null | null
0 | 396 | null |  | 396 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 12:07 | 2023-10-30 17:00 | 12 | 12 | 3 | FALSE | 3f549e82-db8c-43d0-983b-3cd473a4a432 | null | FCSR-LTECH | TKA72047050 | Slidegate Assy. | 130243 | THY MARCINELLE SA | Belgium | Europe | SR | 16 | α – Alpha | Complete | {"type":"thumbnail","fileName":"f2437598-d566-43a1-8797-8fe8977d2edb.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/f2437598-d566-43a1-8797-8fe8977d2edb.jpeg","id":"28c07488-f593-4050-9b51-cd221e8c48a7"} | 10.09.2020 1st dwg | 2020-09-09 22:00 | 2020-10-07 22:00 | 2020-11-19 23:00 | 2020-12-19 23:00 | null | 2021-01-06 23:00 | 2021-07-04 22:00 | 2021-07-29 22:00 | null | null | null | null | null | null | null
0 | 397 | null |  | 397 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 14:23 | 2023-10-30 17:07 | 12 | 12 | 4 | FALSE | 2b11427d-d796-481e-94d7-dba2b5214a9c | null | FCSR-LTECH | T019057A11 | Slidegate Assy. | 151200 | Aperam Châtelet | Belgium | Europe | SR | 100 | α – Alpha | Complete | {"type":"thumbnail","fileName":"de21bb6e-b6ee-4b16-9acc-ca04bc050769.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/de21bb6e-b6ee-4b16-9acc-ca04bc050769.jpeg","id":"3f37a860-fe87-4681-a972-7fe9e35a6486"} | 20.07.2020 PO Date ~ RFQ Date | 2020-07-13 22:00 | 2020-07-19 22:00 | 2020-09-17 22:00 | 2020-11-19 23:00 | null | 2020-11-26 23:00 | 2021-05-19 22:00 | 2021-08-22 22:00 | null | null | null | null | null | null | null
28.03.2019 1st dwg
0 | 398 | null |  | 398 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 12:30 | 2023-10-30 17:14 | 12 | 12 | 6 | FALSE | ae1b6146-aaa8-492e-9695-20dcb3c713bd | null | FCSR-LTECH | TKA72021045 | Slidegate Assy. | 107179 | CELSA ARMERINGSSTÅL AS | Norway | Europe | SR | 70 | α – Alpha | Complete | {"type":"thumbnail","fileName":"b9264cf5-e8a4-4c91-b2c9-6a6799e8d185.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/b9264cf5-e8a4-4c91-b2c9-6a6799e8d185.jpeg","id":"5fa3654b-4dbe-44bd-bdc1-7d1ed129f57b"} | 02.09.2020 1st dwg | 2020-09-01 22:00 | 2020-09-24 22:00 | 2020-10-29 23:00 | 2020-11-24 23:00 | null | 2020-12-06 23:00 | 2021-06-24 22:00 | 2021-08-22 22:00 | null | null | null | null | null | null | null
0 | 399 | null |  | 399 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 12:06 | 2023-10-30 17:29 | 12 | 12 | 3 | FALSE | 74b6e11d-e8e2-4c79-a1aa-28614c359d08 | null | FCSR-LTECH | TKA72070060 | Slidegate Assy. | 135667 | JSW STEEL - Dolvi Works | India | India | SR | 24 | α – Alpha | Complete | {"type":"thumbnail","fileName":"d8f4d502-6115-48a9-9323-9f55528ec298.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/d8f4d502-6115-48a9-9323-9f55528ec298.jpeg","id":"1f914319-b5e3-4898-8654-6de7043bf427"} | 17.09.2020 1st dwg | 2020-09-16 22:00 | 2020-09-29 22:00 | 2020-11-05 23:00 | 2020-12-08 23:00 | null | 2021-02-14 23:00 | 2021-07-14 22:00 | 2021-08-01 22:00 | null | null | null | null | null | null | null
0 | 400 | null |  | 400 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 12:06 | 2023-10-30 18:10 | 12 | 12 | 3 | FALSE | c34e53d3-16bb-470d-954e-3697c66ce6ba | null | FCSR-LTECH | TKA72138035 | Slidegate Assy. | 131166 | EZDK-Flat | Egypt | Europe | SR | 20 | α – Alpha | Complete | {"type":"thumbnail","fileName":"d66d87fc-f712-4969-9a34-cc708195ac8f.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/d66d87fc-f712-4969-9a34-cc708195ac8f.jpeg","id":"ed826e46-2b14-4acb-9e67-98290e0389ac"} | 24.09.2020 1st dwg | 2020-09-23 22:00 | 2020-10-08 22:00 | 2020-11-05 23:00 | 2020-12-02 23:00 | null | 2020-12-14 23:00 | 2021-02-01 23:00 | 2021-02-25 23:00 | null | null | null | null | null | null | null
0 | 401 | null |  | 401 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 12:05 | 2023-10-30 18:13 | 12 | 12 | 3 | FALSE | 81ca1144-dc21-42f1-b80b-544aabeafe08 | null | FCSR-LTECH | TKA72138035 | Slidegate Assy. | 131166 | EZDK-Flat | Egypt | Europe | SR | 20 | β – Beta | Complete | {"type":"thumbnail","fileName":"a6828753-3716-4cf1-be61-c9f67acc2194.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/a6828753-3716-4cf1-be61-c9f67acc2194.jpeg","id":"1ffebf0f-b4d0-489b-9b66-a54ba9255e5b"} | 16.03.2021 PO Date ~ RFQ Date | 2021-03-08 23:00 | 2021-03-15 23:00 | 2021-04-22 22:00 | 2021-06-21 22:00 | null | 2021-06-27 22:00 | 2021-09-19 22:00 | 2021-09-29 22:00 | null | null | null | null | null | null | null
24.09.2020 1st dwg
0 | 402 | null |  | 402 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 12:05 | 2023-10-30 18:24 | 12 | 12 | 3 | FALSE | b7f2d5a1-7100-4034-8816-cf4dfa8d8950 | null | FCSR-LTECH | TKA72021052 | Slidegate Assy. | 165728 | Izmir Demir | Turkey | Europe | SR | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"f7776493-7051-4e38-a623-7eff9206f3aa.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/f7776493-7051-4e38-a623-7eff9206f3aa.jpeg","id":"d713d7f8-5014-47a6-9bf4-6b134e189179"} | 17.03.2021 PO Date ~ RFQ Date | 2021-03-09 23:00 | 2021-03-16 23:00 | 2021-05-06 22:00 | 2021-06-23 22:00 | null | 2021-07-06 22:00 | 2021-09-13 22:00 | 2021-09-23 22:00 | null | null | null | null | null | null | null
02.09.2020 1st dwg
0 | 403 | null |  | 403 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 12:05 | 2023-10-30 18:34 | 12 | 12 | 3 | FALSE | 9ddce745-b716-47ea-b7c4-e94d00286f2f | null | FCSR-LTECH | KA73086 | Slidegate Assy. | 110869 | ASCOVAL | France | Europe | SR | 30 | α – Alpha | Complete | {"type":"thumbnail","fileName":"afc88248-0e41-4dcc-9b74-9776b98d3a21.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/afc88248-0e41-4dcc-9b74-9776b98d3a21.jpeg","id":"1c2e5dfc-20dc-44cc-b07e-f6b5b430b2a1"} | 29.09.2021 PO | 2021-03-28 22:00 | 2021-09-28 22:00 | 2021-10-17 22:00 | 2021-11-28 23:00 | null | 2021-12-14 23:00 | 2022-02-24 23:00 | 2022-03-30 22:00 | null | null | null | null | null | null | null
29.03.2021 1st dwg
20.05.2022 2nd dwg
0 | 404 | null |  | 404 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 12:02 | 2023-10-30 18:40 | 12 | 12 | 4 | FALSE | 1e1c8239-9251-48b4-806a-fad23a075ffd | null | FCSR-LTECH | TKA72021052 | Slidegate Assy. | 156463 | UNISTEEL KUWAIT | Kuwait | Europe | SR | 10 | α – Alpha | Complete | {"type":"thumbnail","fileName":"52c27e28-7d9c-4f8d-90ed-4dbedc0fdaba.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/52c27e28-7d9c-4f8d-90ed-4dbedc0fdaba.jpeg","id":"4def6cff-ea10-45bf-a0d9-21970c1cf73c"} | TKK30621050 TKA72021052 | 2021-04-04 22:00 | 2021-04-11 22:00 | 2021-09-29 22:00 | 2022-01-23 23:00 | null | 2022-04-19 22:00 | 2022-05-31 22:00 | 2022-06-09 22:00 | null | null | null | null | null | null | null
06.2022 - 4 pieces have been tested in June 22 with erosion worse than TS3182 (Martin)
12.04.2021 PO Date ~ RFQ Date
02.09.2020 1st dwg
0 | 405 | null |  | 405 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 12:28 | 2023-10-30 18:49 | 12 | 12 | 7 | FALSE | 5104a5db-e295-40a2-9d65-6b7e65a1f5d0 | null | FCSR-LTECH | TKA70793055 | Slidegate Assy. | 112590 | Steel Dynamics Structural | USA | NAFTA | SR | 20 | α – Alpha | Complete | {"type":"thumbnail","fileName":"2083ff6b-3865-4a83-8b94-19d5da347a4b.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/2083ff6b-3865-4a83-8b94-19d5da347a4b.jpeg","id":"2121b3c5-35f0-4cdf-b0d9-998da473b683"} | DKB0116000 - raw plate | 2020-02-04 23:00 | 2020-02-25 23:00 | 2020-03-19 23:00 | 2020-05-19 22:00 | null | 2020-07-27 22:00 | 2020-09-13 22:00 | 2020-10-15 22:00 | null | null | null | null | null | null | null
05.02.2020 1st dwg
0 | 406 | null |  | 406 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 11:50 | 2023-10-30 18:57 | 12 | 12 | 5 | FALSE | 7a4655d5-4cae-4bb9-85a7-fa6390fa531a | null | FCSR-LTECH | KA73094050 | Slidegate Assy. | 430367 | SIDERCA | Argentina | South America | SR | 15 | α – Alpha | Complete | {"type":"thumbnail","fileName":"299a5e0a-b915-4b7f-b471-3377971c7e31.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/299a5e0a-b915-4b7f-b471-3377971c7e31.jpeg","id":"c5c86a69-1e9c-4276-9d4e-95f647af2124"} | 31.03.2021 1st dwg | 2021-03-30 22:00 | 2021-04-14 22:00 | 2021-05-14 22:00 | 2021-07-11 22:00 | null | 2021-09-19 22:00 | 2022-02-20 23:00 | 2022-03-03 23:00 | null | null | null | null | null | null | null
0 | 407 | null |  | 407 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-21 11:50 | 2023-10-30 19:08 | 12 | 12 | 4 | FALSE | 96b686da-ad5b-4e88-a4ec-c0bed65fa935 | null | FCSR-SURFCDT | KA73102050 | Slidegate Assy. | 101763 | GERDAU PINDAMONHANGABA | Brazil | South America | SR | 30 | α – Alpha | Complete | {"type":"thumbnail","fileName":"15e24441-bf90-4f85-8679-2c93aac32c7e.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/15e24441-bf90-4f85-8679-2c93aac32c7e.jpeg","id":"af210789-5a9e-4194-b874-e39ea80fd099"} | 31.03.2021 1st dwg | 2021-03-30 22:00 | 2021-04-12 22:00 | 2021-05-20 22:00 | 2021-08-11 22:00 | null | 2021-10-17 22:00 | 2022-03-02 23:00 | 2022-03-30 22:00 | null | null | null | null | null | null | null
0 | 408 | null |  | 408 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 12:27 | 2023-10-30 21:27 | 12 | 12 | 5 | FALSE | 247017ec-f991-466a-b739-6cc45933d37a | null | FCVI-DURASLEEVE-NNS | BF97035 | Viso | 200335 | Ternium Mexico, SA de DV (Monterrey) | Mexico | NAFTA | MY | 20 | α – Alpha | Complete | {"type":"thumbnail","fileName":"6c14f01d-518e-4f98-bdd3-9986ab456cf2.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/6c14f01d-518e-4f98-bdd3-9986ab456cf2.jpeg","id":"e571561b-77cb-4e64-bd77-17e907934e23"} | 21.04.2022 PO | 2022-02-02 23:00 | 2022-04-20 22:00 | 2022-05-26 22:00 | 2022-08-03 22:00 | null | 2022-08-14 22:00 | 2022-09-11 22:00 | 2022-10-14 22:00 | null | null | null | null | null | null | null
20.04.2022 2nd dwg revision
03.02.2022 1st dwg
0 | 409 | null |  | 409 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 11:12 | 2023-11-03 10:28 | 12 | 12 | 4 | FALSE | 87b935e9-d26b-49cb-aa5b-11d3ea955951 | null | FCVI-CURVEDSWIRL | BF00644 | Viso | 135774 | Calarasi-Silcotub | Romania | Europe | SR | 10 | α – Alpha | RFQ | {"type":"thumbnail","fileName":"c24cd980-8fcf-4292-a99b-27e02ec94b25.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/c24cd980-8fcf-4292-a99b-27e02ec94b25.jpeg","id":"a1766f9c-1619-4c8f-bbdf-6e279e536f20"} | PO Date - to check | 2023-10-24 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null | null
25.10.2023 publish date
19.05.2023 1st dwg
0 | 410 | null |  | 410 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-22 15:49 | 2023-11-03 13:20 | 12 | 12 | 4 | FALSE | 14eb94f4-1c2b-4f24-bde7-50640f24cb65 | null | FCVI-CURVEDSWIRL | BF92994 | Viso | 271225 | H.K.M. GmbH | Germany | Europe | SR | 60 | β – Beta | PO | {"type":"thumbnail","fileName":"2b893c6d-7a3a-4684-b1bd-801d3f038334.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/2b893c6d-7a3a-4684-b1bd-801d3f038334.jpeg","id":"9db7a8db-73b6-4807-b93c-377fc885c50e"} | 08.11.2023 - LT to confirm (Hubert Handzel) | 2023-10-17 22:00 | 2023-10-24 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null
06.11.2023 Call with supplier (Julien / Fabien)
31.10.2023 Sand core supplier ExOne - Crisis
06.12.2022 publish date
02.08.2021 2nd dwg revision
28.09.2020 1st dwg
0 | 411 | null |  | 411 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-12-12 19:08 | 2023-11-07 15:02 | 12 | 38 | 4 | FALSE | 563f1e9e-a24b-4116-9abc-7d6722407b65 | null | FCVI-R3L | BF48517 | Viso | 140068 | Algoma Steel | Canada | NAFTA | MY | 60 | α – Alpha | Tool | {"type":"thumbnail","fileName":"4f4a0aba-2155-440c-9e04-86b22a43ae42.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/4f4a0aba-2155-440c-9e04-86b22a43ae42.jpeg","id":"ea4faa06-8eac-41d7-96a2-aa222dbe5493"} | RFQ Date = PO Date = Tool Date (existing) | 2023-10-09 22:00 | 2023-10-16 22:00 | 2023-11-27 23:00 | null | null | null | null | null | null | null | null | null | null | null | null
09.10.2020 1st dwg
Confirmed existing tooling, AMM
0 | 412 | null |  | 412 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-08-08 11:56 | 2023-11-08 11:49 | 12 | 116 | 8 | FALSE | fa97ae2c-028f-45a1-83e4-771266839f8e | null | FCSR-LTECH | KA70769040 | Slidegate Assy. | 124089 | GV DO BRASIL | Brazil | South America | SR | 58 | α – Alpha | Pieces on Site | {"type":"thumbnail","fileName":"ca3d44e6-b224-4b13-8f29-70c6c4d3a1a7.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/ca3d44e6-b224-4b13-8f29-70c6c4d3a1a7.jpeg","id":"96f30867-7ac7-4bba-8243-c5032b870a18"} | planned arrival 05.08.2024? | 2023-03-15 23:00 | 2023-11-05 23:00 | 2024-04-02 22:00 | 2024-06-06 22:00 | null | 2024-08-04 22:00 | null | null | null | null | null | null | null | null | null
24.06.2024 shipment
04.06.2024 58pcsd packed HU 3000037322
22.04.2024 kilning
11.04.2024 curing
11.04.2024 pressing 369pcs
03.04.2024 mixing
9th kiln (after Launch)
03.04.2024 RM
18.01.2024 production planned for week 5/6 - beginning of February
next kiln in 2024
06.11.2023 PO 4800013847 43 pcs / 100 pcs with alternative RM
16.03.2023 1st dwg
0 | 413 | null |  | 413 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 09:54 | 2023-11-13 11:00 | 12 | 12 | 9 | FALSE | ba02d274-b4de-47bc-b551-9b8201569995 | null | FCVI-DURAFLEX5L | BC49140 | Viso | 121090 | CMC Steel Florida | USA | NAFTA | MY | 20 | α – Alpha | Pieces on Site | {"type":"thumbnail","fileName":"43be4119-5d8e-454b-aff7-85ad9ea2aaa1.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/43be4119-5d8e-454b-aff7-85ad9ea2aaa1.jpeg","id":"be363a6d-e30e-4445-8910-787c9277bba5"} | 06.03.2024 CMC have stopped using the LS due to operational challenges and will resume in April. | 2023-08-03 22:00 | 2023-08-22 22:00 | 2023-11-29 23:00 | 2024-04-03 22:00 | null | 2024-05-08 22:00 | null | null | null | null | null | null | null | null | null
XX.01.2024 few pieces trial with successful cold re-start
04.08.2023 1st dwg
12.12.2023 No tooling order received.
0 | 414 | null |  | 414 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-03-06 13:53 | 2023-11-13 11:23 | 12 | 259 | 4 | FALSE | 6ecf52a6-bb7d-4372-a0fe-1462dc0c9657 | null | FCVI-DURAFLEX1000H | BD75911 | Viso | 115842 | Tata Scunthorpe Bos Plant | United Kingdom | Europe | SR | 20 | α – Alpha | PO | {"type":"thumbnail","fileName":"d66d3d1b-5e4d-4e4c-9e61-48d39b352a42.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/d66d3d1b-5e4d-4e4c-9e61-48d39b352a42.jpeg","id":"28f33217-24aa-44fd-b31f-c9722e5a7755"} | 06.03.24: 1334= tooling on site, cans on stock, waiting for thermite | 2023-06-11 22:00 | 2023-11-05 23:00 | null | null | null | null | null | null | null | null | null | null | null | null | null
February 24: 1334=tooling ready, to be pressed this week only to check dimensions, waiting for new delivery of 1334, dwg to change to 11204 + integrated mix layer
January 24: 1334=waiting for tooling
06.11.2023 will be split only between 1334 and 1335
12.06.2023 1st dwg
0 | 415 | null |  | 415 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-12-12 19:13 | 2023-11-14 12:34 | 12 | 38 | 5 | FALSE | a342d85c-28f9-4f4b-ac69-c7b213d207b5 | null | FCVI-CURVEDSWIRL | BW13610 | Viso | 100982 | Georgsmarienhuette | Germany | Europe | SR | 42 | α – Alpha | Tool | {"type":"thumbnail","fileName":"cf3b158f-f7ac-40c7-9481-2d88057418ee.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/cf3b158f-f7ac-40c7-9481-2d88057418ee.jpeg","id":"fb501e93-6a87-4f20-8b3b-39d9a9818702"} | 12.04.2023 - PO Date - checked (Ilona) | 2022-05-24 22:00 | 2023-04-11 22:00 | 2023-11-29 23:00 | null | null | null | null | null | null | null | null | null | null | null | null
25.05.2022 1st dwg
(** Tooling order received 30/06/2022 ** AMM)
(** Tooling available 05/07/2023 ** AMM)
0 | 416 | null |  | 416 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 09:34 | 2023-11-14 12:51 | 12 | 12 | 3 | FALSE | bdfb3933-e2e0-4c5e-8dbb-452f90fb4954 | null | FCVI-CISOEMEA | BP76243 | Viso | 100533 | Dillingen Huettenwerk | Germany | Europe | SR | 10 | α – Alpha | RFQ | {"type":"thumbnail","fileName":"61719a18-b6ac-4f46-aa0b-084deec783fa.png","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/61719a18-b6ac-4f46-aa0b-084deec783fa.png","id":"fab3cc53-374d-4cca-a35c-7045a3dfdb19"} | PO Date - to check (Ilona) | 2023-03-14 23:00 | null | null | null | null | null | null | null | null | null | null | null | null | null | null
15.03.2023 1st dwg
0 | 417 | null |  | 417 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-24 13:42 | 2023-11-24 13:39 | 12 | 12 | 3 | FALSE | 4b8fbaa9-ec6d-4c0e-97e2-493f42059d57 | null | FCSR-LTECH | KA74639045 | Slidegate Assy. | 165194 | Suez Steel | Egypt | Europe | SR | 72 | α – Alpha | Complete | {"type":"thumbnail","fileName":"6e266866-14bb-4975-98b5-ff92d1e9fe10.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/6e266866-14bb-4975-98b5-ff92d1e9fe10.jpeg","id":"ef44cf40-7987-46de-a7c7-38c574648a16"} | 11.05.2023 - Trial report | 2022-07-25 22:00 | 2022-10-10 22:00 | 2023-02-19 23:00 | 2023-04-02 22:00 | null | 2023-04-20 22:00 | 2023-04-25 22:00 | 2023-05-10 22:00 | null | null | null | null | null | null | null
21.04.2023 - pieces on site
03.04.2023 - ready for shipment?
11.10.2022 - start pressing?
20.02.2022 PO date? - to check
26.07.2022 1st dwg
0 | 418 | null |  | 418 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-24 16:29 | 2023-11-24 16:29 | 12 | 12 | 2 | FALSE | 20275893-38ca-4c7e-84a7-d7791ff41a5d | null | FCPS-OPTICLEAN+ | QF08804 | Purge Plugs | 145569 | TEMIRTAU LITEYNY ZAVOD | Kazakhstan | Europe | SR | 40 | α – Alpha | Complete | {"type":"thumbnail","fileName":"a71fd00d-c718-422a-9399-9ede8be3de56.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/a71fd00d-c718-422a-9399-9ede8be3de56.jpeg","id":"e1aa32b9-58fb-478b-9623-53f1afd06712"} | 21.07.2023 – 18.9.2023 - Trial | 2023-03-08 23:00 | 2023-03-15 23:00 | 2023-05-04 22:00 | 2023-05-25 22:00 | null | null | 2023-07-20 22:00 | 2023-09-17 22:00 | null | null | null | null | null | null | null
26.05.2023 shipping
30.12.2021 1st dwg
0 | 419 | null |  | 419 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-24 16:39 | 2023-11-24 16:39 | 12 | 12 | 2 | FALSE | 0169787c-c937-4d77-a1c4-5eb5d48ea0fe | null | FCPS-OPTICLEAN+ | QF09562 | Purge Plugs | 131166 | EZDK-Flat | Egypt | Europe | SR | 20 | α – Alpha | Manufacturing | {"type":"thumbnail","fileName":"53b24ed9-9abd-48e9-8f1e-23ade3792b7a.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/53b24ed9-9abd-48e9-8f1e-23ade3792b7a.jpeg","id":"1b9bee48-3976-4c86-a750-41e9ad6c8082"} | PO & RM Date to check with Krzysztof | 2023-08-27 22:00 | 2023-09-13 22:00 | 2023-10-12 22:00 | 2023-11-23 23:00 | null | null | null | null | null | null | null | null | null | null | null
Qty to check
28.08.2023 1st dwg
0 | 420 | null |  | 420 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-24 16:45 | 2023-11-24 16:45 | 12 | 12 | 2 | FALSE | f4defc2f-4b43-4d4b-a399-38c4e940754f | null | FCPS-OPTICLEAN+ | QF09554 | Purge Plugs | 146609 | EZZ STEEL COMPANY | Egypt | Europe | SR | 20 | α – Alpha | PO | {"type":"thumbnail","fileName":"34a7a597-c06a-4154-b99b-290902f98271.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/34a7a597-c06a-4154-b99b-290902f98271.jpeg","id":"c1b4e488-3c07-45c4-83a8-87ff15191dab"} | RM / Mfg date to check with Krzysztof | 2023-03-15 23:00 | 2023-09-04 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null
05.09.2023 WK 36 PO date
16.03.2023 1st dwg
0 | 421 | null |  | 421 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-24 16:54 | 2023-11-24 16:52 | 12 | 12 | 3 | FALSE | ee36b2bd-f99f-465b-9d38-b3d6f25f81a2 | null | FCPS-OPTICLEAN+ | QF09695 | Purge Plugs | 126582 | DNEPROSTEEL | Ukraine | Europe | SR | 20 | α – Alpha | Trial | {"type":"thumbnail","fileName":"e3449fde-0483-4c6e-9701-6511f90ba7fa.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/e3449fde-0483-4c6e-9701-6511f90ba7fa.jpeg","id":"741c922c-093f-455a-ad3a-e6b7ca925138"} | Trial to chek with Dima | 2023-05-11 22:00 | 2023-07-27 22:00 | 2023-08-23 22:00 | 2023-09-13 22:00 | null | 2023-10-18 22:00 | 2023-11-02 23:00 | null | null | null | null | null | null | null | null
RM / Mfg date - to check with Krzysztof
28.07.2023 PO
12.05.2023 1st dwg
0 | 422 | null |  | 422 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-24 16:59 | 2023-11-24 16:59 | 12 | 12 | 2 | FALSE | e04baf6b-16b3-4853-86ed-8b3fa7dcc93f | null | FCPS-OPTICLEAN+ | QF09604 | Purge Plugs | 114088 | FREITAL | Germany | Europe | SR | 20 | α – Alpha | Pieces on Site | {"type":"thumbnail","fileName":"0735d98d-35b8-488f-8828-14c990deadc6.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/0735d98d-35b8-488f-8828-14c990deadc6.jpeg","id":"e964146c-8ae7-48e9-bc86-9a79c30b661e"} | RM / Mfg date to check with Krzysztof | 2023-04-02 22:00 | 2023-06-29 22:00 | 2023-07-27 22:00 | 2023-08-24 22:00 | null | 2023-08-31 22:00 | null | null | null | null | null | null | null | null | null
01.09.2023 WK35 - pcs on site
30.06.2023 PO
12.09.2023 2nd dwg revision
03.04.2023 1st wg
0 | 423 | null |  | 423 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-30 15:14 | 2023-11-24 17:06 | 12 | 12 | 3 | FALSE | 8bcefc29-07e1-4528-84a5-69689c64a0af | null | FCPS-OPTICLEAN+ | QF08937 | Purge Plugs | 135579 | Liberty Ostrava | Czechia | Europe | SR | 20 | α – Alpha | Complete | {"type":"thumbnail","fileName":"79123412-ec5c-4848-82e4-b8b1c699b28f.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/79123412-ec5c-4848-82e4-b8b1c699b28f.jpeg","id":"ca4ffba4-a00d-4507-af40-32208590939c"} | 25.05.2023 trial report | 2022-05-29 22:00 | 2022-10-20 22:00 | 2023-02-01 23:00 | 2023-03-08 23:00 | null | 2023-03-15 23:00 | 2023-04-27 22:00 | 2023-05-24 22:00 | null | null | null | null | null | null | null
PO / RM / Mfg date - to check with Krzysztof
13.10.2023 2nd dwg revision
30.05.2022 1st dwg
0 | 424 | null |  | 424 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-24 17:12 | 2023-11-24 17:12 | 12 | 12 | 2 | FALSE | d066a2d7-1ba7-4e29-86a5-9560db727754 | null | FCPS-OPTICLEAN+ | QF09133 | Purge Plugs | 115583 | Buderus | Germany | Europe | SR | 20 | α – Alpha | Trial | {"type":"thumbnail","fileName":"ff1d40a0-62cf-4d8b-95bb-086e4ae62a6d.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/ff1d40a0-62cf-4d8b-95bb-086e4ae62a6d.jpeg","id":"aada7ddb-162e-49d8-94aa-a8499bc1339a"} | 08.2023 trial start | 2022-09-21 22:00 | 2023-03-09 23:00 | 2023-04-26 22:00 | 2023-05-30 22:00 | null | 2023-06-07 22:00 | 2023-08-24 22:00 | null | null | null | null | null | null | null | null
RM / Mfg date to check with Krzysztpof
10.03.2023 PO
13.10.2023 2nd dwg revision
20.09.2022 1st dwg
0 | 425 | null |  | 425 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-04-25 08:54 | 2023-11-29 11:31 | 12 | 12 | 8 | FALSE | 986af9ab-b1f8-4227-904d-daf84852fc37 | null | FCSR-LTECH | KA77392050 | Slidegate Assy. | 200099 | Gerdau Whitby - USD | Canada | NAFTA | SR | 50 | β – Beta | Pieces on Site | {"type":"thumbnail","fileName":"9f8ad7c1-c613-497a-bfdd-ca4ac360252a.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/9f8ad7c1-c613-497a-bfdd-ca4ac360252a.jpeg","id":"121f70f7-9cd0-4092-8413-135462eccb4e"} | 04.2024 pcs on site date - to check | 2023-04-06 22:00 | 2023-11-28 23:00 | 2023-12-17 23:00 | 2024-01-15 23:00 | null | 2024-04-01 22:00 | null | null | null | null | null | null | null | null | null
16.01.2024 53pcs packed HU 3000005017
07.12.2023 packing planned for week 3
07.12.2023 to press beginning od December 8th kiln - week 50
12.2023 Mix ready for pressing - pressing week 50
29.11.2023 information from Rony to change order 50pcs from DVB0272000 to SK05482000
07.04.2023 1st dwg
raw plate SK05482000
0 | 426 | null |  | 426 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-30 15:07 | 2023-11-30 15:07 | 12 | 12 | 2 | FALSE | b5619049-924c-467c-ba17-b7e7c6dfc666 | null | FCPS-OPTICLEAN+ | QF09745-FI | Purge Plugs | 431078 | Cleveland-Cliffs Plate LLC (Coatesville) | USA | NAFTA | SR | 20 | α – Alpha | PO | {"type":"thumbnail","fileName":"1563d421-5e90-4fba-b28e-9ebb1535551c.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/1563d421-5e90-4fba-b28e-9ebb1535551c.jpeg","id":"c8d5d1c1-a012-43d8-9118-2aba2a49ca09"} | PATTERN!!! QF0911 Lunch Code HSC | 2023-05-17 22:00 | 2023-09-21 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null
18.05.2023 1st dwg
0 | 427 | null |  | 427 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-03-06 13:52 | 2023-11-30 15:39 | 12 | 259 | 3 | FALSE | ab645bb2-f67f-4b27-97ad-822bb9f0f200 | null | FCVI-DURAFLEX20H | BD76711 | Viso | 182042 | FHS | Vietnam | South East Asia | SR | 20 | α – Alpha | PO | {"type":"thumbnail","fileName":"9d03a0a4-e309-48e5-97d0-cda577de8064.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/9d03a0a4-e309-48e5-97d0-cda577de8064.jpeg","id":"fa1d74c1-5d43-47de-82d7-70545ebd80f3"} | 06.03.24: 1334 and 1335 = thermite validation pending (transportation 5th of march) | 2023-08-10 22:00 | 2023-11-28 23:00 | null | null | null | null | null | null | null | null | null | null | null | null | null
February 24: 1334 and 1335 = tooling availability wk 7, cans week 8, waiting for mix
January 24: 1334 and 1335 = waiting for tooling expected wk5
29.11.2023 PO of BD76711 we are dealing with system issue
Similar patterns that I have found produced are: BD73072, BD61242, BD60434
11.08.2023 1st dwg
0 | 428 | null |  | 428 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-30 15:47 | 2023-11-30 15:47 | 12 | 12 | 2 | FALSE | f1e7b3cf-2e2b-4137-b7db-41ac798e4ab9 | null | FCPS-OPTIFLOW+ | PS-OPTIFLOWP | Purge Plugs | 168556 | Gerdau Fort Smith | USA | NAFTA | SR | 20 | α – Alpha | Pieces on Site | {"type":"thumbnail","fileName":"bf83454f-0c29-4c27-8953-da2721ffa52b.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/bf83454f-0c29-4c27-8953-da2721ffa52b.jpeg","id":"9aa14409-b771-4bdf-b0ec-f55fd8becda8"} | PATTERN !!! PH09221 | 2023-04-20 22:00 | 2023-05-08 22:00 | 2023-07-06 22:00 | 2023-07-31 22:00 | null | 2023-09-28 22:00 | null | null | null | null | null | null | null | null | null
29.09.2023 delivery Date
01.08.2023 ship from SR
09.05.2023 PO
21.04.2023 1st dwg
0 | 429 | null |  | 429 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-12-11 14:21 | 2023-11-30 16:01 | 12 | 12 | 3 | FALSE | b42009dd-11c4-48dc-984e-d83e1608c045 | null | FCPS-HSC | PL13901 | Purge Plugs | 126487 | Gerdau Jackson | USA | NAFTA | SR | 20 | α – Alpha | Trial | {"type":"thumbnail","fileName":"3046780f-a4ac-4efe-a091-3a76318e2991.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/3046780f-a4ac-4efe-a091-3a76318e2991.jpeg","id":"24d9b7c5-45c6-4b2e-b758-88a2c23f47b9"} | PATTERN !!! PL13901 | 2023-04-05 22:00 | 2023-04-12 22:00 | 2023-06-22 22:00 | 2023-07-31 22:00 | null | 2023-10-01 22:00 | 2023-11-23 23:00 | null | null | null | null | null | null | null | null
Launch Code: FCPS-HSC
02.10.2023 Delivery Date
01.08.2023 ship Date
13.04.2023 PO Date ~ RFQ Date
15.06.2023 2nd dwg revision
11.07.2022 1st dwg
0 | 430 | null |  | 430 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-30 16:09 | 2023-11-30 16:09 | 12 | 12 | 2 | FALSE | 216b9428-2b10-4521-91f9-f5c65d347ded | null | FCPS-OPTIFLOW+ | PS-OPTIFLOWP | Purge Plugs | 113250 | Nucor Tuscaloosa | USA | NAFTA | SR | 20 | α – Alpha | PO | {"type":"thumbnail","fileName":"06867ae6-d254-438e-8fb6-0d395b4a0c68.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/06867ae6-d254-438e-8fb6-0d395b4a0c68.jpeg","id":"7cf648b4-7729-4f7d-9a6e-0eb6990e6391"} | PATTERN !!! PL14594 | 2023-04-12 22:00 | 2023-10-02 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null
Launch Code: FCPS-HSC
03.10.2023 PO
13.04.2023 1st dwg
0 | 431 | null |  | 431 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-11-30 16:16 | 2023-11-30 16:16 | 12 | 12 | 2 | FALSE | 3b99c7f8-675c-4ada-a577-0a9cddf6a726 | null | FCPS-OPTIFLOW+ | PS-OPTIFLOWP | Purge Plugs | 101245 | Nucor Plymouth | USA | NAFTA | SR | 20 | α – Alpha | PO | {"type":"thumbnail","fileName":"b6f72d0e-899f-4283-a156-4764d5b40d41.jpeg","fieldName":"Drawing Image","serverUrl":"https://vesuvius.sharepoint.com","serverRelativeUrl":"/sites/NPIAcceleration/SiteAssets/Lists/49d4b27d-8528-4ed0-884f-b2bf5f336950/b6f72d0e-899f-4283-a156-4764d5b40d41.jpeg","id":"97697500-a383-4ddb-a6e4-ddae6237387a"} | PATTERN !!! PL14958 | 2023-08-21 22:00 | 2023-09-25 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null
Launch Code: FCPS-HSC
26.09.2023 PO
22.08.2023 1st dwg
0 | 432 | null |  | 432 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 09:41 | 2023-12-01 11:13 | 12 | 12 | 2 | FALSE | b65f8466-5ffb-4237-a0bd-70cdfd7b4df8 | null | FCPS-OPTIFLOW+ | PL14628 | Purge Plugs | 165320 | Rustavi Steel | Georgia | Europe | SR | 20 | α – Alpha | RFQ | null | PO pending | 2023-11-14 23:00 | null | null | null | null | null | null | null | null | null | null | null | null | null | null
1st dwg - to check the date
0 | 433 | null |  | 433 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-08-08 11:57 | 2023-12-07 11:24 | 12 | 116 | 9 | TRUE | 93c22595-8e1c-449e-abe4-9bfec1d1fa2d | null | FCSR-LTECH | KA74647050 | Slidegate Assy. | 136799 | TAIWAN OTHER CUSTOMERS | Taiwan | North Asia | SR | 50 | α – Alpha | Pieces on Site | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[ec027b7b-ba27-42d0-a702-99669df5ecb3][1]_[1].jpeg"} | planned arrival 29.08.2024? | 2023-11-23 23:00 | 2023-11-30 23:00 | 2024-04-02 22:00 | 2024-06-14 22:00 | null | 2024-08-28 22:00 | null | null | null | null | null | null | null | null | null
04.07.2024 shipment HU 3000040933
15.06.2024 packing HU 3000040933
22.04.2024 kilning
16.04.2024 curing
12.04.2024 pressing 60pcs
03.04.2024 mixing
9th kiln (after Launch)
03.04.2024 RM
18.01.2024 production planned for week 5 - beginning of February
expected lead time March 2024
CUSTOMER Name - to check (KAOHSIUNG)
PO Date 01.12.2023
RFQ Date 24.11.2023
03.03.2022 1st dwg
0 | 434 | null |  | 434 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2023-12-11 12:37 | 2023-12-11 12:37 | 40 | 40 | 1 | FALSE | f4e68de3-8323-4e9c-ac30-b702ad1f0bd1 | null | FCPS-IP00094 | QF09703 | Purge Plugs | 101763 | GERDAU PINDAMONHANGABA | Brazil | South America | RJ | 30 | β – Beta | Manufacturing | null | null | 2023-08-06 22:00 | 2023-09-03 22:00 | null | 2023-11-12 23:00 | null | null | null | null | null | null | null | null | null | null | null
0 | 435 | null |  | 435 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-07-04 10:23 | 2024-01-25 12:05 | 12 | 12 | 13 | TRUE | dd68e05b-fb81-4da2-ae10-57311de11a86 | null | FCSR-LTECH | KA74365 | Slidegate Assy. | 163559 | Baku Steel | Azerbaijan | Europe | SR | 30 | α – Alpha | Pieces on Site | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[8a815078-bf91-4e74-a1f4-c0f74ac0daf0][1]_[4].jpeg"} | crate nr HE3000038828 | 2023-11-15 23:00 | 2023-11-22 23:00 | 2024-04-02 22:00 | 2024-06-06 22:00 | null | 2024-06-17 22:00 | null | null | null | null | null | null | null | null | null
18.06.2024 shipping
07.06.2024 packing
22.04.2024 kilning
16.04.2024 curing
12.04.2024 pressing 175pcs
03.04.2024 mixing
9th kiln (after Launch)
03.04.2024 RM
25.01.2023 to arrange pressing
23.11.2023 new order placed for 60pcs (Customer VESUVIUS ISTANBUL 900136)
semifinished SK00426
PATTTERN !!! KA76345030 (LV10/LG20 DP D30 3182/3420)
07.09.2022 - 1st dwg
0 | 436 | null |  | 436 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-07-04 10:12 | 2024-01-25 12:12 | 12 | 12 | 9 | TRUE | 36efa97b-ea16-4c19-bd37-b5abc343a15a | null | FCSR-LTECH | KA74977045 | Slidegate Assy. | 900084 | VESUVIUS CALCUTTA | India | India | SR | 40 | α – Alpha | Pieces on Site | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[636840eb-0643-4926-87bd-3a554bc9c486][1]_[3].jpeg"} | Customer Name to be checked - Sudip | 2023-12-05 23:00 | 2023-12-12 23:00 | 2024-04-02 22:00 | 2024-06-06 22:00 | null | 2024-09-18 22:00 | null | null | null | null | null | null | null | null | null
19.09 - to confirm trial start
01.07.2024 shipped
07.06.2024 packed
22.04.2024 kilning
16.04.2024 curing
12.04.2024 pressing 175pcs
03.04.2024 mixing
9th kiln (after Launch)
03.04.2024 RM
25.01.2024 to arrange pressing
SK00418000 - semifinished SK00426
13.12.2023 - PO Date
27.04.2022 - 1st dwg
0 | 437 | null |  | 437 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-07-04 10:34 | 2024-01-25 12:17 | 12 | 12 | 12 | TRUE | 6eac67e3-4d5c-40ba-bc68-d3a17476dba6 | null | FCSR-LTECH | KK33070040 | Slidegate Assy. | 900090 | VESUVIUS MONTERREY | Mexico | NAFTA | SR | 49 | α – Alpha | Pieces on Site | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[c3026dde-1a10-4e16-93b2-f328e9bbdd77][1]_[3].jpeg"} | crate nr HU3000040318 | 2023-10-29 23:00 | 2024-03-19 23:00 | 2024-04-02 22:00 | 2024-06-12 22:00 | null | 2024-07-04 22:00 | null | null | null | null | null | null | null | null | null
05.07.2024 loading
13.06.2024 packing
04.06.2024 klin
split Drayton L-TECH / F-TECH G2
16.04.2024 curing
15.04.2024 pressing 50pcs
03.04.2024 mixing
9th klin (after Launch)
20.03.2024 PO Date (renew 40pcs)
25.01.2024 to arrange pressing
PATTERN !!! Customer Name!!
SK08353000 - KK33070XXX - (LV80 GT 3378/3444/3171)
02.11.2023 - PO Date / cancelled
30.10.2023 - 1st dwg
0 | 438 | null |  | 438 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-07-04 10:37 | 2024-01-25 12:18 | 12 | 12 | 10 | TRUE | 11cded2d-8ea6-4e79-87c5-37ceb0522fc1 | null | FCSR-LTECH | KA78630040 | Slidegate Assy. | 900090 | VESUVIUS MONTERREY | Mexico | NAFTA | SR | 49 | α – Alpha | Pieces on Site | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[46c804d7-cc8c-442d-ae83-e61c10131b1b][1]_[4].jpeg"} | crate nr HU3000040314 | 2023-10-29 23:00 | 2024-03-19 23:00 | 2024-04-02 22:00 | 2024-06-12 22:00 | null | 2024-07-04 22:00 | null | null | null | null | null | null | null | null | null
in transit
05.07.2024 loading
13.06.2024 packing
04.06.2024 kiln
split Drayton L-TECH / F-TECH G2
17.04.2024 curing
16.04.2024 pressing 50pcs
03.04.2024 mixing
9th kiln (after Launch)
20.03.2024 - PO (renew)
25.01.2024 to arrange pressing
Customer RFQ - 200109 // MITTAL CANADA
SK08346000
02.11.2023 - PO Date
30.10.2023 - 1st dwg (cancelled)
0 | 439 | null |  | 439 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-07-04 10:25 | 2024-01-26 11:51 | 12 | 12 | 8 | TRUE | c8f8bc69-4f5d-4e3d-9020-71ce964149fb | null | FCSR-LTECH | KK32197 | Slidegate Assy. | 163559 | Baku Steel | Azerbaijan | Europe | SR | 30 | α – Alpha | Pieces on Site | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[1cf10622-c706-4b6b-b6d2-ae8cba8d25bc][1]_[1].jpeg"} | crate nr HE3000038828 | 2023-11-15 23:00 | 2023-11-22 23:00 | 2024-04-02 22:00 | 2024-06-06 22:00 | null | 2024-06-17 22:00 | null | null | null | null | null | null | null | null | null
18.06.2024 loading
07.06.2024 packing
22.04.2024 kilning
16.04.2024 curing
12.04.2024 pressing 175pcs
03.04.2024 mixing
9th kiln (after Launch)
03.04.2024 RM
25.01.2023 to arrange pressing
23.11.2023 new order placed for 60pcs (Customer VESUVIUS ISTANBUL 900136)
semifinished SK00426
PATTTERN !!!! KK32171 (LG20 GT D30 3182/3420/3025)
27.09.2022 - 1st dwg
0 | 440 | null |  | 440 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-02-21 11:50 | 2024-02-12 14:34 | 77 | 12 | 21 | TRUE | 3ba4f122-05dc-4f10-b6df-5e7f54475b88 | null | FCVI-VFIT | VI-VFIT | Viso | 200075 | Nucor Jackson | USA | NAFTA | MY | 20 | α – Alpha | Trial | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[8cb1902c-2782-43ae-98df-31e98c841f41][2]_[19].jpeg"} | PATTERN !!! BC49330 - Launch Code 1324 VFIT | 2023-10-02 22:00 | 2023-10-23 22:00 | 2023-11-30 23:00 | 2024-01-18 23:00 | 2024-02-08 23:00 | 2024-02-22 23:00 | 2024-02-29 23:00 | null | null | null | null | null | null | null | null
Customer : Nucor Jackson
12.02.2024 The trial will be planning on #wk8 [Ozan]
03.10.2023 - 1st dwg
0 | 441 | null |  | 441 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-02-21 11:58 | 2024-02-12 14:36 | 77 | 12 | 19 | TRUE | 325ddebe-70b5-4d50-b191-475efd4de452 | null | FCVI-DURASLEEVE-FLAT | BZ50889 | Viso | 113250 | Nucor Tuscaloosa | USA | NAFTA | MY | 20 | α – Alpha | Pieces on Site | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[53732b99-6df7-4c35-af50-46a47db7f1f0][2]_[17].jpeg"} | 12.02.2024 - pieces on site [Ozan] | 2023-07-31 22:00 | 2023-08-21 22:00 | 2023-10-26 22:00 | 2024-01-04 23:00 | 2024-02-08 23:00 | 2024-02-11 23:00 | null | null | null | null | null | null | null | null | null
01.08.2024 - 1st dwg
0 | 443 | null |  | 443 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 09:48 | 2024-03-06 14:03 | 259 | 12 | 3 | FALSE | a3d1812e-eeca-4093-b111-2137cfbecab1 | null | FCVI-DURAFLEXHP+ | BC49704 | Viso | 126717 | ArcelorMittal France | France | Europe | TC | 9 | α – Alpha | Complete | null | Feb 24: 8 pcs in OS, 1 piece to be shipped from TC to OS to complete full crate and then send to customer | 2023-11-01 23:00 | 2023-12-01 23:00 | 2024-01-09 23:00 | 2024-02-21 23:00 | null | 2024-03-06 23:00 | 2024-04-08 22:00 | 2024-04-17 22:00 | null | null | null | null | null | null | null
Jan 2024: 8 pieces ready. 1 in production to complete 9, but waiting for Sales reply if ok to ship 8 and not 9
Mfg Date
PO Date
Date - 1st dwg
0 | 444 | null |  | 444 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 09:45 | 2024-03-06 14:08 | 259 | 12 | 3 | FALSE | b6e313ec-4e1c-4d11-a555-bbcaa567d4e3 | null | FCVI-DURAFLEXHF | BC45429 | Viso | 166041 | Arcellor Mittal Poland | Poland | Europe | TC | 175 | β – Beta | Complete | null | February 24: inconsistent cold reuse (1pcs did well, the second failed) | 2023-05-31 22:00 | 2023-08-02 22:00 | 2023-09-06 22:00 | 2023-11-01 23:00 | null | 2023-11-22 23:00 | 2023-11-24 23:00 | 2023-11-29 23:00 | null | null | null | null | null | null | null
Average performance was around 7-8 heats, meaning long sequenced (this customer does a lot of single shot heat, 1,4-1,7 ht in average) amcustomer wants to order more
Nov-23: pieces on site. Continuing trial, but slowly
Mfg Date
PO Date
Date - 1st dwg
0 | 446 | null |  | 446 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 09:56 | 2024-03-06 14:12 | 259 | 12 | 3 | FALSE | 8227c492-2ea6-4932-8ba4-0c8846fff330 | null | FCVI-DURAFLEXHP+ | BD73510 | Viso | 104094 | SIDENOR BASAURI | Spain | Europe | TC | 20 | α – Alpha | Pieces on Site | null | To check the plant | 2023-12-06 23:00 | 2024-01-16 23:00 | 2024-03-12 23:00 | 2024-04-10 22:00 | null | 2024-05-15 22:00 | null | null | null | null | null | null | null | null | null
Date - 1st dwg
PO Date
Mfg Date
0 | 448 | null |  | 448 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 10:03 | 2024-03-06 14:20 | 259 | 12 | 7 | FALSE | db258c16-69cc-4694-a771-3c5f9180c33d | null | FCVI-DURAFLEXHP | BD73858 | Viso | 100486 | DALMINE ACCIAIERIE SPA | Italy | Europe | TC | 20 | β – Beta | Complete | null | 06.03.24: for beta-trial= wk7 delay, waiting for thermite results, dry mix from Rio, needed to be rejuvenated 2 times, T2 and PP OK | 2024-01-23 23:00 | 2024-02-06 23:00 | 2024-02-21 23:00 | 2024-02-28 23:00 | null | 2024-03-03 23:00 | 2024-03-05 23:00 | 2024-03-13 23:00 | null | null | null | null | null | null | null
First trial run in January 2023. Sales ordered 60 pcs to have something going on (std LS BD54502 has had various failures and its supply has been stopped), but high price will be a challenge.
Options for mix: used the 1283 from RJMX that is now in GH or make 1-1283 rev 6 (revision with lower lamination problem) in OSMX"
Mfg Date
PO Date
Date - 1st dwg
0 | 449 | null |  | 449 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 10:04 | 2024-03-06 14:30 | 259 | 12 | 5 | FALSE | f6d84a9f-442d-4b13-92f1-75161b3fab4a | null | FCVI-DURAFLEXHF | BC47995 | Viso | 113334 | FERROSTAL | Poland | Europe | TC | null | α – Alpha | Complete | null | 06.03.24 : pcs found in TC, will be shipped to SR this week, additionally make pcs from 1301 | 2024-01-01 23:00 | 2024-01-10 23:00 | 2024-01-31 23:00 | 2024-03-05 23:00 | null | 2024-04-09 22:00 | 2024-05-15 22:00 | 2024-05-22 22:00 | null | null | null | null | null | null | null
Feb 24:Visible in TC S&amp;OP, but demand in 0 pcs, crate pressed half a year ago
Jan 24: Delay in trial because of unstable production (new EAF commissioning). Now production is more stable. Will try to arrange delivery of pieces in week 3
Mfg Date
PO Date
Date - 1st dwg
0 | 452 | null |  | 452 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 11:10 | 2024-03-06 14:45 | 259 | 12 | 6 | FALSE | 4d8916eb-72aa-4fe0-b15b-6fbd6a0f9a4f | null | FCVI-DURAFLEXHF | BC44620 | Viso | 126599 | NPSS | Egypt | Europe | TC | 200 | α – Alpha | PO | null | no order in S&OP, only mail | 2024-03-06 23:00 | 2024-03-13 23:00 | null | null | null | null | null | null | null | null | null | null | null | null | null
1st dwg
0 | 453 | null |  | 453 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 11:19 | 2024-03-06 14:45 | 259 | 12 | 3 | FALSE | 900dec6a-abd1-4038-8d2e-f644babd985c | null | FCVI-DURAFLEXHP | BC49603 | Viso | 113303 | QATAR STEEL COMPANY QSC | Qatar | Europe | TC | 20 | α – Alpha | PO | null | S&OP week 19 | 2024-04-30 22:00 | 2024-05-07 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null
to check Plant
1st dwg !!!
0 | 454 | null |  | 454 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 11:25 | 2024-03-06 14:45 | 259 | 12 | 5 | FALSE | b7ad2549-adb5-441c-8588-77d207eebf5f | null | FCVI-DURAFLEXHP | BD75721 | Viso | 135774 | Calarasi-Silcotub | Romania | Europe | TC | 29 | α – Alpha | Complete | null | trial successful, up to 24heats, beta trial planned | 2024-01-01 23:00 | 2024-01-03 23:00 | 2024-01-10 23:00 | 2024-02-28 23:00 | null | 2024-03-06 23:00 | 2024-03-13 23:00 | 2024-03-20 23:00 | null | null | null | null | null | null | null
PO date
1st dwg !!
0 | 455 | null |  | 455 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 11:30 | 2024-03-06 14:45 | 259 | 12 | 5 | FALSE | 94b4acf3-ecec-4be8-80b2-3125f32a4cb0 | null | FCVI-DURAFLEXHF | BC48308 | Viso | 165194 | Suez Steel Company S.A.E | Egypt | Europe | TC | 20 | α – Alpha | Complete | null | "06.03.24: Trials probably not started yet | 2023-12-19 23:00 | 2023-12-21 23:00 | 2024-01-10 23:00 | 2024-02-07 23:00 | null | 2024-02-14 23:00 | 2024-03-05 23:00 | 2024-03-14 23:00 | null | null | null | null | null | null | null
Feb 24: shipped"
0 | 456 | null |  | 456 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 11:32 | 2024-03-06 14:45 | 259 | 12 | 5 | FALSE | 3e0722db-b3b2-44a1-ae81-5385d53d4449 | null | FCVI-DURAFLEXHP+ | BC49694 | Viso | 116493 | TKS Beekerwerth | Germany | Europe | TC | 2 | α – Alpha | Complete | null | 06.03.24: shipped, no casting will be done, test to be made by customer | 2024-01-10 23:00 | 2024-02-07 23:00 | 2024-02-14 23:00 | 2024-03-05 23:00 | null | 2024-03-13 23:00 | 2024-04-03 22:00 | 2024-04-10 22:00 | null | null | null | null | null | null | null
0 | 457 | null |  | 457 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 11:43 | 2024-03-06 14:45 | 259 | 12 | 5 | FALSE | 9bd8665d-70d0-4856-a9dc-3c84092281de | null | FCVI-DURAFLEXHP+ | BC49702 | Viso | 116493 | TKS Beekerwerth | Germany | Europe | TC | 2 | α – Alpha | Complete | null | 06.03.24:shipped, no casting will be done, test to be made by customer | 2024-01-17 23:00 | 2024-01-31 23:00 | 2024-02-07 23:00 | 2024-03-05 23:00 | null | 2024-03-31 22:00 | 2024-04-07 22:00 | 2024-04-11 22:00 | null | null | null | null | null | null | null
PO Date
1st dwg !!!
0 | 458 | null |  | 458 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 11:44 | 2024-03-06 14:45 | 259 | 12 | 5 | FALSE | 808fde83-e7ec-49fd-ac3d-50aaeca57d28 | null | FCVI-DURAFLEXHP | BD76091 | Viso | 169867 | Beiman Special Steel | China | China | SZ | 5 | α – Alpha | Complete | null | 06.03.24:on site + trial has begun | 2023-12-21 23:00 | 2024-01-04 23:00 | 2024-01-11 23:00 | 2024-02-22 23:00 | null | 2024-02-29 23:00 | 2024-03-05 23:00 | 2024-03-11 23:00 | null | null | null | null | null | null | null
need to get a TOT to China as fast as possible as they are going to be ramping up presenting to customers 1301
0 | 459 | null |  | 459 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 11:46 | 2024-03-06 14:45 | 259 | 12 | 5 | FALSE | 4961c247-c6d2-4fb4-a9b5-474b2aee16bf | null | FCVI-DURAFLEXHP | BD67983 | Viso | 162011 | Shin Kansai Steel Hoshida | Japan | North Asia | SZ | 16 | α – Alpha | Complete | null | Trial date ?? | 2023-11-30 23:00 | 2024-01-18 23:00 | 2024-02-15 23:00 | 2024-03-06 23:00 | null | 2024-04-03 22:00 | 2024-05-23 22:00 | 2024-05-30 22:00 | null | null | null | null | null | null | null
06.03.24: To follow in terms of production of mix in SZ, i.e. within the validation of mix production with CS premix in SZMX
PO Date
1st dwg !!!
0 | 460 | null |  | 460 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 11:48 | 2024-03-06 14:45 | 259 | 12 | 6 | FALSE | 3174c70c-b6ad-4d48-a48b-792b6ce91906 | null | FCVI-DURAFLEXHF | BD76695 | Viso | 104961 | ISMT | India | India | CL | 40 | α – Alpha | Manufacturing | null | 18.03.24: mix 1301 rejuvenated in CL. Waiting for fired properties and thermite after rejuvenation. | 2024-02-07 23:00 | 2024-02-21 23:00 | 2024-03-13 23:00 | 2024-03-17 23:00 | null | null | null | null | null | null | null | null | null | null | null
same blend for ISMT, Tata Steel Long, and Vardhaman)
0 | 461 | null |  | 461 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 11:56 | 2024-03-06 14:45 | 259 | 12 | 6 | FALSE | b28e4d52-8566-4c84-85ad-e14b005aefbb | null | FCVI-DURAFLEXHP | BD75671 | Viso | 140955 | Tata Steel Long - APOB | India | India | CL | 40 | α – Alpha | Manufacturing | null | 18.03.24: mix 1301 rejuvenated in CL. Waiting for fired properties and thermite after rejuvenation. | 2024-02-01 23:00 | 2024-02-29 23:00 | 2024-03-06 23:00 | 2024-03-17 23:00 | null | null | null | null | null | null | null | null | null | null | null
same blend for ISMT, Tata Steel Long, and Vardhaman)
0 | 462 | null |  | 462 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 11:58 | 2024-03-06 14:45 | 259 | 12 | 8 | FALSE | 0c4d464e-f014-4ce1-87ee-e1fc1c2d0fdb | null | FCVI-DURAFLEXHP | BD70870 | Viso | 107383 | Vardhaman | India | India | CL | 20 | α – Alpha | Manufacturing | null | BD60681 under concession | 2024-01-17 23:00 | 2024-01-31 23:00 | 2024-03-06 23:00 | 2024-03-17 23:00 | null | null | null | null | null | null | null | null | null | null | null
18.03.24: mix 1301 rejuvenated in CL. Waiting for fired properties and thermite after rejuvenation.
same blend for ISMT, Tata Steel Long, and Vardhaman)
0 | 463 | null |  | 463 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 12:03 | 2024-03-06 14:45 | 259 | 12 | 4 | FALSE | e1712131-4f9b-4f8e-a6fa-b1b5d1ba8098 | null | FCVI-DURAFLEXHP+ | BD74401 | Viso | 430519 | CSP | Brazil | South America | SZ | null | α – Alpha | Manufacturing | null | BD74559 under concession | 2024-01-01 23:00 | 2024-01-03 23:00 | 2024-01-31 23:00 | 2024-02-21 23:00 | null | null | null | null | null | null | null | null | null | null | null
mix arrived in RJ. Production will start only in February
0 | 464 | null |  | 464 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 12:11 | 2024-03-06 14:45 | 259 | 12 | 3 | FALSE | 16200142-8374-473f-9f9c-2b40532898d5 | null | FCVI-DURAFLEXHF | BC49447 | Viso | 103871 | GERDAU CHARQUEADAS | Brazil | South America | RJ | null | α – Alpha | Complete | null | Pieces on site. Trail not before February | 2024-01-04 23:00 | 2024-01-10 23:00 | 2024-01-24 23:00 | 2024-02-14 23:00 | null | 2024-02-28 23:00 | 2024-03-06 23:00 | 2024-03-13 23:00 | null | null | null | null | null | null | null
0 | 465 | null |  | 465 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 12:13 | 2024-03-06 14:45 | 259 | 12 | 3 | FALSE | 1d7b1c34-e3ac-4379-ad32-584cf01fc547 | null | FCVI-DURAFLEXHF | BD77925 | Viso | 101763 | GERDAU PINDAMONHANGABA | Brazil | South America | RJ | null | α – Alpha | Complete | null | BD77776 under concession 1301 | 2024-01-17 23:00 | 2024-01-31 23:00 | 2024-02-07 23:00 | 2024-02-21 23:00 | null | 2024-03-13 23:00 | 2024-03-17 23:00 | 2024-03-21 23:00 | null | null | null | null | null | null | null
trial in progress
PO date
1st dwg!!!
0 | 466 | null |  | 466 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 12:09 | 2024-03-06 14:45 | 259 | 12 | 2 | FALSE | a680a3c1-62de-41ee-913e-89145d177343 | null | FCVI-DURAFLEXHF | BD77271 | Viso | 101763 | GERDAU PINDAMONHANGABA | Brazil | South America | RJ | null | α – Alpha | RFQ | null | PO DATE | 2024-06-05 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null | null
1st dwg!!!
0 | 467 | null |  | 467 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 12:16 | 2024-03-06 14:45 | 259 | 12 | 9 | FALSE | 2ae9e0e2-84fc-4b74-ad72-a524001a586e | null | FCVI-DURAFLEXHP | BC49439 | Viso | 101497 | ArcelorMittal Juiz de Fora | Brazil | South America | RJ | 48 | α – Alpha | Manufacturing | null | BC49454 under concession | 2024-01-24 23:00 | 2024-02-07 23:00 | 2024-02-28 23:00 | 2024-03-24 23:00 | null | null | null | null | null | null | null | null | null | null | null
25.03.24: RJ x ray to be commissioned end on april
22.03.24: (Thiago Pereira) first pieces to be made"
mix arrived in RJ. Production will start only in February
PO Date
1st dwg !!!
0 | 468 | null |  | 468 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 12:14 | 2024-03-06 14:45 | 259 | 12 | 8 | FALSE | ef8a4748-0f46-44e4-82ac-68a60f265e88 | null | FCVI-DURAFLEXHP | BC49439 | Viso | 156457 | AM RESENDE | Brazil | South America | RJ | 30 | α – Alpha | Complete | null | BC49439 produced as BC44885 under concession | 2024-01-10 23:00 | 2024-02-07 23:00 | 2024-03-13 23:00 | 2024-03-24 23:00 | null | 2024-05-01 22:00 | 2024-05-09 22:00 | 2024-05-16 22:00 | null | null | null | null | null | null | null
25.03.24: RJ x ray to be commissioned end on april
22.03.24: (Thiago Pereira) first pieces to be made"
mix arrived in RJ. Production will start only in February
PO Date
1st dwg !!!
0 | 469 | null |  | 469 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 12:16 | 2024-03-06 14:45 | 259 | 12 | 10 | FALSE | d5efad96-d9c1-4675-a34a-8e6dc326ae89 | null | FCVI-DURAFLEXHP+ | BC49470 | Viso | 156474 | TERNIUM BRASIL | Brazil | South America | RJ | 9 | α – Alpha | Manufacturing | null | produced as BC47672 under concession | 2024-01-10 23:00 | 2024-01-17 23:00 | 2024-01-24 23:00 | 2024-02-14 23:00 | null | null | null | null | null | null | null | null | null | null | null
mix arrived in RJ. Production will start only in February
0 | 470 | null |  | 470 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 12:18 | 2024-03-06 14:46 | 259 | 12 | 4 | FALSE | b1e581cb-6ea9-4607-aeaf-b97cd6c80369 | null | FCVI-DURAFLEXHP+ | BC47268 | Viso | 164080 | USIMINAS | Brazil | South America | RJ | 20 | α – Alpha | Complete | null | BC44521 | 2024-01-03 23:00 | 2024-01-10 23:00 | 2024-01-31 23:00 | 2024-02-07 23:00 | null | 2024-02-21 23:00 | 2024-03-03 23:00 | 2024-03-06 23:00 | null | null | null | null | null | null | null
trial in progress
PO date
1st dwg !!!
0 | 471 | null |  | 471 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 11:41 | 2024-03-06 14:46 | 259 | 12 | 5 | FALSE | b080bf6b-2764-4b40-a5b1-b48feacacc1c | null | FCVI-DURAFLEXHF | BC49256 | Viso | 104569 | Charter Steel Saukville | USA | NAFTA | MY | 10 | α – Alpha | Manufacturing | null | 02/29. Waiting for 1301 mix approval (thermite pots) | 2024-01-11 23:00 | 2024-01-18 23:00 | 2024-02-11 23:00 | 2024-02-28 23:00 | null | null | null | null | null | null | null | null | null | null | null
12-02-24 : pieces with cans in RJ
15-02-24: Rejection of the 10 pieces per detail in base
PO date
1st dwg !!!
0 | 472 | null |  | 472 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 11:38 | 2024-03-06 14:46 | 259 | 12 | 5 | FALSE | 01aa024c-342d-4cbd-9829-e56e45d353b6 | null | FCVI-DURAFLEXHF | BC47045 | Viso | 104569 | Charter Steel Saukville | USA | NAFTA | MY | 20 | α – Alpha | Complete | null | "trial in 2022: 4 LS tested and 16 unused LS sent to PI for analysis to explain failure (pinholes observed) | 2022-09-21 22:00 | 2022-10-06 22:00 | 2022-10-13 22:00 | 2022-11-09 23:00 | null | 2022-11-30 23:00 | 2022-12-07 23:00 | 2022-12-14 23:00 | null | null | null | null | null | null | null
average : 2,75 hts (RHI = 2,5 hts, max 5 hts) but competitor is less expensive"
PO date
1st dwg !!!
0 | 473 | null |  | 473 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 11:34 | 2024-03-06 14:46 | 259 | 12 | 5 | FALSE | 62f0e020-9f8f-457f-bc9b-a6e6ddef9911 | null | FCVI-DURAFLEXHF | BC48621 | Viso | 152564 | CMC Steel Arizona | USA | NAFTA | MY | 20 | β – Beta | Complete | null | 15-02-24: pending for production | 2023-11-15 23:00 | 2023-11-22 23:00 | 2023-11-29 23:00 | 2024-01-04 23:00 | null | 2024-01-09 23:00 | 2024-01-16 23:00 | 2024-01-23 23:00 | null | null | null | null | null | null | null
Jan 24: Bionic sleeve. 20 pcs tested customer happy with the perfo, more order to cme
PO date
1st dwg !!!
0 | 474 | null |  | 474 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 10:00 | 2024-03-06 14:46 | 259 | 12 | 6 | FALSE | 5c466952-63db-4fff-b10e-63917c0622bd | null | FCVI-DURAFLEXHF | BC49348 | Viso | 101357 | Gerdau Jackson, MI | USA | NAFTA | MYV | 50 | α – Alpha | Manufacturing | null | 02/28. Base diameter out of specification, 10 pieces out of 23 with this condition, pending concession | 2024-01-17 23:00 | 2024-01-31 23:00 | 2024-02-07 23:00 | 2024-02-27 23:00 | null | null | null | null | null | null | null | null | null | null | null
06-02-24: 45 pieces waiting for production
13-02-24: pressing
0 | 476 | null |  | 476 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 12:26 | 2024-03-06 14:46 | 259 | 12 | 4 | FALSE | c869381a-ca18-4c76-bc12-0120754de171 | null | FCVI-DURAFLEXHF | BD75283 | Viso | 121232 | Cleveland Cliff Indiana Harbor East | USA | NAFTA | CH | 27 | α – Alpha | RFQ | null | PO Date | 2024-06-26 22:00 | null | null | null | null | null | null | null | null | null | null | null | null | null | null
1st dwg!!!
0 | 477 | null |  | 477 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 09:49 | 2024-03-06 14:46 | 259 | 12 | 6 | FALSE | 64894480-2bab-4e01-831a-c2bdd8dff566 | null | FCVI-DURAFLEXHP | BC49215 | Viso | 182085 | Nucor Berkeley | Others | Others | CH | 23 | α – Alpha | Complete | null | 22.03.24: Trials at Nucor Berkeley are on hold for now, customer focus is on other projects. | 2023-12-27 23:00 | 2024-01-03 23:00 | 2024-01-17 23:00 | 2024-02-14 23:00 | null | 2024-03-06 23:00 | 2024-03-21 23:00 | 2024-04-03 22:00 | null | null | null | null | null | null | null
- Customer very interested in the bionic version and will be a Duraflex, waiting for drawing (Martin Kreierhoff) and will RFQ next week.
- Currently: gained 100% of the business due to EIC not performing, and this is the opportunity to introduce Duraflex there faster.
January 24: Pieces on site. Trail not before February
0 | 479 | null |  | 479 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 09:59 | 2024-03-06 14:46 | 259 | 12 | 2 | FALSE | 2cab871a-7f40-45e1-83b3-6df47e4599b0 | null | FCVI-DURAFLEXHP+ | BC49470 | Viso | 101397 | Steel Dynamics Roanoke Bar Div | USA | NAFTA | MY | 20 | α – Alpha | Pieces on Site | null | BC49165 | 2024-02-05 23:00 | 2024-02-21 23:00 | 2024-04-10 22:00 | 2024-05-16 22:00 | null | 2024-06-05 22:00 | null | null | null | null | null | null | null | null | null
Mfg Date
PO Date
Date - 1st dwg
0 | 481 | null |  | 481 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 09:52 | 2024-03-06 15:06 | 259 | 12 | 2 | FALSE | 22b3d376-8400-48b5-99ea-f9e53cbd67ac | null | FCVI-DURAFLEXHF | BC49710 | Viso | 991034 | Roanoke Electric Steel 101397-Cons | USA | NAFTA | MYV | 20 | α – Alpha | Pieces on Site | null | BC49639 Under concession | 2024-01-08 23:00 | 2024-02-13 23:00 | 2024-03-17 23:00 | 2024-04-17 22:00 | null | 2024-05-15 22:00 | null | null | null | null | null | null | null | null | null
account manager will fill in regarding conversion there
Date - 1st dwg
PO Date
Mfg Date
0 | 482 | null |  | 482 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 09:31 | 2024-03-18 15:00 | 259 | 12 | 2 | FALSE | bbd79a10-30f5-4a05-9248-9da03d6bb6dc | null | FCVI-DURAFLEXHF | BC47029 | Viso | 121232 | Cleveland Cliff Indiana Harbor East | USA | NAFTA | MY | 20 | α – Alpha | Manufacturing | null | PATTERN !!! | 2024-01-03 23:00 | 2024-01-31 23:00 | 2024-03-13 23:00 | 2024-05-06 22:00 | null | null | null | null | null | null | null | null | null | null | null
To check Plant
Ready for shipment Date
PO Date
Date - 1st dwg
0 | 483 | null |  | 483 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 09:32 | 2024-03-18 15:04 | 259 | 12 | 3 | FALSE | 2f10e4c0-bdd9-46df-bab5-3be566409dab | null | FCVI-DURAFLEXHF | BC47029 | Viso | 103871 | GERDAU CHARQUEADAS | Brazil | South America | RJ | 0 | α – Alpha | Manufacturing | null | PATTERN !!! | 2024-01-07 23:00 | 2024-02-14 23:00 | 2024-03-06 23:00 | 2024-03-24 23:00 | null | null | null | null | null | null | null | null | null | null | null
"25.03.24: RJ x ray to be commissioned end on april
22.03.24: (Thiago Pereira) first pieces to be made"
To check Plant
Ready for shipment Date
PO Date
Date - 1st dwg
0 | 484 | null |  | 484 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 09:34 | 2024-03-18 15:18 | 259 | 12 | 3 | FALSE | 97201d38-1db6-4a4d-a5e6-f31880f7a2bf | null | FCVI-DURAFLEXHP+ | BC47268 | Viso | 105010 | BlueScope Port Kembla | Australia | Australia - New Zealand | MY | 20 | α – Alpha | Pieces on Site | null | 1301 mix | 2024-01-09 23:00 | 2024-02-06 23:00 | 2024-03-06 23:00 | 2024-04-03 22:00 | null | 2024-04-24 22:00 | null | null | null | null | null | null | null | null | null
To check Plant
Ready for shipment Date
PO Date
Date - 1st dwg
0 | 485 | null |  | 485 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 09:35 | 2024-03-18 15:19 | 259 | 12 | 3 | FALSE | 460f1424-509d-4aaf-9648-29eaa7797db4 | null | FCVI-DURAFLEXHP+ | BC47268 | Viso | 114324 | Mitsubishi Muroran | Japan | North Asia | SZ | 20 | α – Alpha | Pieces on Site | null | PATTERN!!! | 2024-01-31 23:00 | 2024-02-07 23:00 | 2024-04-01 22:00 | 2024-05-08 22:00 | null | 2024-06-04 22:00 | null | null | null | null | null | null | null | null | null
1301 mix
To check Plant
Ready for shipment Date
PO Date
Date - 1st dwg
0 | 486 | null |  | 486 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 12:34 | 2024-03-18 15:19 | 259 | 12 | 4 | FALSE | 70815509-052c-4894-b62f-ac15c96a07f9 | null | FCVI-DURAFLEXHP | BC46765 | Viso | 164812 | Qian'an | China | China | SZ | 20 | α – Alpha | Pieces on Site | null | PATTERN !!! | 2024-01-03 23:00 | 2024-02-07 23:00 | 2024-03-06 23:00 | 2024-05-08 22:00 | null | 2024-06-05 22:00 | null | null | null | null | null | null | null | null | null
LTC Ladle Shroud
1301 mix
Ready for shipment Date
PO Date
Date - 1st dwg
0 | 487 | null |  | 487 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 12:20 | 2024-03-18 15:19 | 259 | 12 | 4 | FALSE | 910f70bf-2c35-4721-9ec7-a9add14992bb | null | FCVI-DURAFLEXHP | BC46765 | Viso | 136417 | WISCO | China | China | SZ | 20 | α – Alpha | Manufacturing | null | PATTERN !!! | 2024-01-31 23:00 | 2024-03-06 23:00 | 2024-05-01 22:00 | 2024-06-05 22:00 | null | null | null | null | null | null | null | null | null | null | null
LTC Ladel Shroud
1301 mix
To check Plant
Ready for shipment Date
PO Date
Date - 1st dwg
0 | 488 | null |  | 488 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-06-27 09:27 | 2024-04-15 11:43 | 54 | 12 | 2 | FALSE | c5e0f864-a6e1-459c-9e51-6d60556638f6 | null | FCVI-DURASLEEVECS | BZ51564 | Viso | 113212 | KOSICE/TUNDISH PARTS | Slovakia | Europe | SR | 20 | α – Alpha | Pieces on Site | null | To check Plant | 2024-01-03 23:00 | 2024-01-10 23:00 | 2024-03-06 23:00 | 2024-04-03 22:00 | null | 2024-05-22 22:00 | null | null | null | null | null | null | null | null | null
Ready for shipment Date
PO Date
Date - 1st dwg
0 | 489 | null |  | 489 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-07-04 10:44 | 2024-04-25 07:48 | 12 | 12 | 7 | TRUE | 53457551-8e61-4e5f-badf-2f6b8478c0e3 | null | FCSR-LTECH | TKA70769045 | Slidegate Assy. | 169250 | Gerdau Corsa Sahagun | Mexico | NAFTA | SR | 60 | β – Beta | Pieces on Site | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[6bb21ee1-cfcd-4be4-a7ab-4db4a2e23a90][1]_[4].jpeg"} | DVB0255000 semifinished | 2024-03-03 23:00 | 2024-03-10 23:00 | 2024-03-10 23:00 | 2024-05-24 22:00 | null | 2024-06-20 22:00 | null | null | null | null | null | null | null | null | null
crate nr HU3000035598
21.06.2024loading
25.05.2024 packing
22.04.2024 kilning
11.04.2024 curing
11.04.2024 pressing 369pcs
03.04.2024 mixing
9th kiln (after Launch)
11.03.2024 PO
30.01.2020 - 1st dwg
0 | 490 | null |  | 490 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-07-04 10:46 | 2024-04-25 07:54 | 12 | 12 | 9 | TRUE | a1381123-4808-4f88-bfa4-8d114eacb556 | null | FCSR-LTECH | KA74977050 | Slidegate Assy. | 200336 | Ternium Mexico, SA de DV (Puebla) | Mexico | NAFTA | SR | 60 | β – Beta | Pieces on Site | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[16741aec-6ddc-4561-adc4-eac3f14f3eee][1]_[5].jpeg"} | in transit | 2024-03-07 23:00 | 2024-03-10 23:00 | 2024-04-02 22:00 | 2024-06-06 22:00 | null | 2024-08-06 22:00 | null | null | null | null | null | null | null | null | null
crate nr HU3000037828
07.06.2024 loading
05.06.2024 packing
22.04.2024 kilning
16.04.2024 curing
12.04.2024 pressing 175pcs
03.04.2024 mixing
9th kiln (after Launch)
SK00426
11.03.2024 PO Date
03.04.2024 - WK14 - RM Date
2704.2022 - 1st dwg
0 | 491 | null |  | 491 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-07-04 10:40 | 2024-04-25 08:07 | 12 | 12 | 6 | TRUE | 61f53215-4d37-4a47-9525-90320292b6a1 | null | FCSR-LTECH | KK32619050 | Slidegate Assy. | 200099 | Gerdau Whitby - USD | Canada | NAFTA | SR | 43 | β – Beta | Pieces on Site | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[09b8f302-07ec-4211-9871-3c54c4ceffd0][1]_[3].jpeg"} | SK03487000 | 2024-03-05 23:00 | 2024-03-19 23:00 | 2024-04-02 22:00 | 2024-05-12 22:00 | null | 2024-07-24 22:00 | null | null | null | null | null | null | null | null | null
in transit
crate nr HU3000032060
24.05.2024 loading
13.05.2024 packing
22.04.2024 kilning
12.04.2024 curing
11.04.2024 pressing 44pcs
03.04.2024 mixing
9th klin (after Launch)
20.03.2024 PO
03.04.2024 RM
17.04.2023 - 1st dwg
0 | 492 | null |  | 492 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-07-04 10:41 | 2024-04-25 08:10 | 12 | 12 | 7 | TRUE | 8fbbc817-24cb-48b9-83ee-c1796e1c3aa4 | null | FCSR-LTECH | KA77392050 | Slidegate Assy. | 200099 | Gerdau Whitby - USD | Canada | NAFTA | SR | 40 | β – Beta | Pieces on Site | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[1e6f9f11-a1b2-4087-958c-0632224cef31][1]_[3].jpeg"} | in transit | 2024-03-05 23:00 | 2024-03-19 23:00 | 2024-04-02 22:00 | 2024-06-20 22:00 | null | 2024-07-02 22:00 | null | null | null | null | null | null | null | null | null
crate nr HU3000042703
03.07.2024 loading
21.06.2024 packing
12.04.2024 curing
11.04.2024 pressing 50pcs
03.04.2024 mixing
9th kiln (after Launch)
to double check Pattern & Customer !!!
DVB0272000
20.03.2024 PO Date
03.04.2024 RM
0704.2023 - 1st dwg
0 | 493 | null |  | 493 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-08-08 11:58 | 2024-04-25 08:13 | 12 | 116 | 8 | TRUE | 700732f5-5eeb-4f99-baee-975c1a64c12e | null | FCSR-LTECH | TKA70801080 | Slidegate Assy. | 104251 | British Steel Scunthorpe | United Kingdom | Europe | SR | 60 | α – Alpha | Pieces on Site | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[584d0460-02a3-4d70-91ee-43b4d7b4746d][1]_[3].jpeg"} | planned arrival 23.07.2024? | 2024-01-31 23:00 | 2024-03-20 23:00 | 2024-04-02 22:00 | 2024-07-01 22:00 | null | 2024-07-22 22:00 | null | null | null | null | null | null | null | null | null
09.07.2024 shipment
crate nr HU3000045303
loading date
02.07.2024 packing
DWB0074000
21.03.2024 PO date
03.04.2024 RM
21.02.2020 - 1st dwg
0 | 494 | null |  | 494 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-08-08 11:59 | 2024-04-25 08:37 | 12 | 116 | 9 | TRUE | c03a3d6a-3f60-43f1-8fbd-025dc50e43bb | null | FCSR-LTECH | TKA70769055 | Slidegate Assy. | 101015 | Corporacion Aceros Arequipa S.A. | Peru | South America | SR | 150 | β – Beta | Pieces on Site | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[85456f19-05e5-4ea1-9cef-7c9febc51f7a][1]_[3].jpeg"} | planned arrival 18.09.2024? | 2024-01-31 23:00 | 2024-03-25 23:00 | 2024-04-02 22:00 | 2024-07-21 22:00 | null | 2024-09-17 22:00 | null | null | null | null | null | null | null | null | null
07.08.2024 shipment
22.07.2024 packing HU 3000049454
12.07.2024 packing
assembling on going 50 pcs packed together with G2
26.06.2024 kiln Drayton
24.06.2024 pressing with G2 campaigne
06.06.2024 100 pcs packed
22.04.2024 kilning
11.04.2024 curing
11.04.2024 pressing 369pcs
03.04.2024 mixing
9th kiln (after Launch)
15.04.2024 PO confirmation
03.04.2024 RM
26.03.2024 PO
30.01.2020 - 1st dwg
0 | 495 | null |  | 495 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-07-04 10:15 | 2024-04-25 08:44 | 12 | 12 | 6 | TRUE | 11768eec-56a6-49e4-aed9-f5c2da367b99 | null | FCSR-LTECH | KA70769060 | Slidegate Assy. | 135667 | JSW STEEL - Dolvi Works | India | India | SR | 52 | α – Alpha | Pieces on Site | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[c2208e4b-42ba-467e-a7e2-5ba6e2dc448c][1]_[3].jpeg"} | crate nr HU3000034471 | 2024-02-29 23:00 | 2024-04-02 22:00 | 2024-04-07 22:00 | 2024-05-20 22:00 | null | 2024-09-18 22:00 | null | null | null | null | null | null | null | null | null
19.09.2024 trial date to confirm with Sudip
01.07.2024 shipped
21.05.2024 packed
22.04.2024 kilning
11.04.2024 curing
11.04.2024 pressing 369pcs
03.04.2024 mixing
9th kiln (after Launch)
08.04.2024 PO
03.04.2024 RM
16.03.2023 - 1st dwg
semifinished DVB0255000
0 | 496 | null |  | 496 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-09-12 10:20 | 2024-06-27 10:11 | 12 | 116 | 10 | TRUE | 604de2b4-7bc6-409a-8d13-fbad837f02ab | null | FCSR-LTECH | KA70769038 | Slidegate Assy. | 170680 | MIDDLE EAST BUSINESS | Lebanon | Europe | SR | 100 | α – Alpha | Pieces on Site | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[e3616c0b-1475-45d7-a2ca-92aaf3cedcd6][1]_[2].jpeg"} | PATTERN !!! | 2024-06-05 22:00 | 2024-06-10 22:00 | 2024-06-20 22:00 | 2024-08-21 22:00 | null | 2024-09-26 22:00 | null | null | null | null | null | null | null | null | null
Customer !!! 900237
estimated pieces on site 27.09.2024
05.09.2024 crate shipped
22.08.2024 SK10839 packed 100 pcs HU 3000055646
08.08.2024 pending impregnation, assembly week 38
SK10839 - semi finished
27.09.2024 shipment confirmation
01.08.2024 pending impregnation
21.06.2024 pressed
11.06.2024 PO (no notification, Customer Order directly to SAP) SOP
16.03.2023 - 1st dwg !!!
0 | 497 | null |  | 497 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-10-03 10:11 | 2024-06-27 10:17 | 12 | 116 | 10 | TRUE | bf45017e-7280-4d4f-96c2-65e2db329867 | null | FCSR-LTECH | KA78853 | Slidegate Assy. | 128904 | TATA STEEL- NINL | India | India | SR | 20 | α – Alpha | Tool | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[72ed770c-c8b3-4940-a8f6-051afa561356][1]_[3].jpeg"} | SK0887400 (for KA78853 – L-tech) - Tata Steel NINL | 2023-11-30 23:00 | 2024-06-11 22:00 | 2024-08-08 22:00 | null | null | null | null | null | null | null | null | null | null | null | null
03.10.2024 mixing wk41, pressing planned for wk42
08.08.2024 waiting for mould to be prepared - Tooling Department to confirm, not ready for 07.08, next campaign to plan
12.06.2024 - PO
29-30WK shut down
22.07.2024 ? ETA for stepms
24.06.2024 - dwg of modified mold published (3 weeks for stamps) >> WK32
No tooling, existing mold to be used, water cut
28.02.2024 - SK08874 - raw plate - IC Price (Subir / Magda Addario)
01.12.2023 - 1st dwg
0 | 498 | null |  | 498 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-08-08 12:03 | 2024-06-27 10:25 | 12 | 116 | 8 | TRUE | 9a4c4f39-c86a-4786-a64a-cffee986c9f7 | null | FCSR-LTECH | KA76188055 | Slidegate Assy. | 480062 | CELSA HUTA OSTROWIEC | Poland | Europe | SR | 80 | β – Beta | Pieces on Site | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[060950eb-d74f-4b1f-92c1-3bbcf6f73227][1]_[2].jpeg"} | planned arrival 09.08.2024? | 2024-05-02 22:00 | 2024-05-09 22:00 | 2024-05-19 22:00 | 2024-07-15 22:00 | null | 2024-08-08 22:00 | null | null | null | null | null | null | null | null | null
26.07.2024 shipment
18.07.2024 packing 3000048584
16.07.2024 - shipment confirmation ?
12.07.2024 packing (Oliwia)
assembling on going
WK29-30 shut down
23.05.2024 - pressed
20.05.2024 - mixes, exiting tooling
10.05.2024 - PO
31.08.2022 - 1st dwg !!
0 | 499 | null |  | 499 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-08-08 10:39 | 2024-06-27 10:34 | 12 | 116 | 4 | FALSE | 56cdc746-a964-4606-ac05-835bdd508acd | null | FCSR-SANDCDT | KA79158 | Slidegate Assy. | 114088 | FREITAL | Germany | Europe | SR | 10 | α – Alpha | Pieces on Site | null | PATTERN !!! KA79158 | 2024-01-17 23:00 | 2024-02-01 23:00 | 2024-05-23 22:00 | 2024-07-16 22:00 | null | 2024-08-11 22:00 | null | null | null | null | null | null | null | null | null
02.08.2024 shipped
17.07.2024 packed 10pcs, HU 3000048145
WK29-30 shut down
12.07.2024 pending assembly, to be packed 12.07
12.07.2024 - shipment confirmation, delayed 1wk - 19.07.2024
31.05.2024 - pressed
24.05.2024 - mixes, existing tooling
02.02.2024 - PO
1st dwg !!!
0 | 500 | null |  | 500 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-10-03 10:07 | 2024-06-27 10:38 | 12 | 116 | 9 | FALSE | 53561cb3-8bec-40a3-9a45-aa7ed346feec | null | FCSR-SANDCDT | KA79422 | Slidegate Assy. | 117732 | Buderus Wetzlar | Germany | Europe | SR | 20 | α – Alpha | Manufacturing | null | KA79422 | 2024-04-24 22:00 | 2024-05-28 22:00 | 2024-05-30 22:00 | 2024-08-23 22:00 | null | null | null | null | null | null | null | null | null | null | null
03.10.2024 not shipped yet, awaiting in warehouse
WK29-30
13.09.2024 - shipment confirmation, delivery not planned yet
24.08.2024 packed 20pcs HU 3000056270
14.08.2024 pending assembly
12.07.2024 production on assembly in wk36
15.06 carbonization
12.06.2024 impregnation
02.06.2024 fired
01.06.2024 cured
31.05.2024 - pressed
29.05.2024 - PO
1st dwg !!!!
0 | 501 | null |  | 501 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-08-28 12:32 | 2024-06-27 10:42 | 12 | 116 | 6 | FALSE | db90147c-30b8-4a68-850c-7e2438b51e1c | null | FCSR-SANDCDT | KA79224060 | Slidegate Assy. | 116011 | Deutsche Edelstahlwerke Gmbh | Germany | Europe | SR | 10 | α – Alpha | Pieces on Site | null | KA79224060 set YD03214 | 2024-04-09 22:00 | 2024-04-16 22:00 | 2024-05-23 22:00 | 2024-07-21 22:00 | null | 2024-08-29 22:00 | null | null | null | null | null | null | null | null | null
estimated time on site 30.08.2024
16.08.2024 shipped
14.08.2024 not shipped yet
22.07.2024 packed 10pcs HU 3000049453
WK29-30 shut down
12.07.2024 pending assembly, to be packed 12.07.2024
28.06.2024 - shipment confirmation - delayed 2wks - 19.07.2024
27.06.2024 - not packed yet
31.05.2024 - pressed
24.05.2024 - mixes
17.04.2024 - PO
1st dwg !!!
0 | 502 | null |  | 502 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-08-08 11:45 | 2024-06-27 10:50 | 12 | 116 | 13 | TRUE | 64562121-d523-46a6-aca3-54c9c37462da | null | FCSR-FTECHG2 | KA79653070 | Slidegate Assy. | 168871 | ArcelorMittal Lazaro Cardenas | Mexico | NAFTA | SR | 50 | α – Alpha | Pieces on Site | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[110b9ea1-fa68-411f-ac15-a49739b7e27d][1]_[4].jpeg"} | KA79653070 | 2024-05-06 22:00 | 2024-05-29 22:00 | 2024-06-11 22:00 | 2024-07-09 22:00 | null | 2024-09-17 22:00 | null | null | null | null | null | null | null | null | null
planned arrival 18.09.2024
shipped 07.08.2024
WK29-30 shut down
mixes
12.07.2024 - shipment confirmation ?
10.07.2024 packing HU 3000047159
08.07.2024 assembling
26-28.06.2024 firing
21.06.2024 curing
19.06.2024 pressed
10-12.06.2024 - mixes
PO pending
07.05.2024 - 1st dwg!!!
0 | 503 | null |  | 503 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-08-14 10:16 | 2024-06-27 10:55 | 12 | 116 | 11 | TRUE | ca49f94c-87f6-4769-9bc6-d9bb2e52eba0 | null | FCSR-FTECHG2 | KA79950070 | Slidegate Assy. | 135578 | USS - Kosice | Slovakia | Europe | SR | 50 | α – Alpha | Trial | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[6868c3a4-c424-481d-95a7-47492dab959b][1]_[2].jpeg"} | KA79950070 | 2024-06-13 22:00 | 2024-06-16 22:00 | 2024-06-20 22:00 | 2024-07-08 22:00 | null | 2024-07-31 22:00 | 2024-08-06 22:00 | null | null | null | null | null | null | null | null
Trial date 07.08.2024
planned arrival 01.08.2024
Customer - to check
WK29-30 shut down
18.07.2024 shipment
09.07.2024 - packing HU3000046863
08.07.2024 - assembling
26-28.06.2024 - firing
21.06.2024 - curing
21.06.2024 - pressed
11-12.06.2024 - mixes
26.06.2024 - PO
14.06.2024 - 1st dwg
0 | 504 | null |  | 504 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-08-08 11:45 | 2024-06-27 10:56 | 12 | 116 | 8 | TRUE | 7f3a84f8-f751-447e-8f0e-567843ce124a | null | FCSR-FTECHG2 | KA79885 | Slidegate Assy. | 104951 | Cleveland-Cliffs Middletown Works | USA | NAFTA | SR | 50 | α – Alpha | Pieces on Site | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[24a7d406-7df2-40d0-a5fc-cf70a277983b][1]_[2].jpeg"} | KA79885 | 2024-05-27 22:00 | 2024-06-05 22:00 | 2024-06-11 22:00 | 2024-08-05 22:00 | null | 2024-09-17 22:00 | null | null | null | null | null | null | null | null | null
planned arrival 18.09.2024
07.08.2024 shipped
06.08.2024 50pcs packed HU 3000052606
crate should be packed till 09.08.2024
01.08.2024 delivery of gaskets, finishing assembly
WK29-30 shut down
08.07.2024 - assembling
26-28.06.2024 - firing
21.06.2024 - curing
21.06.2024 - pressed
11-12.06.2024 - mixes
pending - PO
28.05.2024 - 1st dwg !!!
0 | 505 | null |  | 505 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-09-12 10:18 | 2024-06-27 11:02 | 12 | 116 | 12 | TRUE | 22ea97db-90ae-482e-be93-dddf6e70de57 | null | FCSR-FTECHG2 | KA78564080 | Slidegate Assy. | 110296 | ARCELORMITTAL BRASIL S/A - TUBARÃO | Brazil | South America | SR | 44 | α – Alpha | Pieces on Site | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[f5f13502-d6a7-4358-9ccd-d87be928b413][1]_[2].jpeg"} | KA78564080 | 2024-05-29 22:00 | 2024-06-04 22:00 | 2024-06-11 22:00 | 2024-07-11 22:00 | null | 2024-10-24 22:00 | null | null | null | null | null | null | null | null | null
estimated pieces on site 25.10.2024
28.08.2024 crate shipped
14.08.2024 order received, awaiting shipment
08.08.2024 still no order, crate not shipped, waiting in warehouse
WK29-30 shut down
12.07.2024 - shipment confirmation
11.07.2024 - packing 44pcs HU 3000047241
08.07.2024 - assembling
26-28.06.2024 - firing
21.06.2024 - curing
19.06.2024 - pressed
11-12.06.2024 - mixes
pending - PO
03.10.2023 - 1st dwg !!!
0 | 506 | null |  | 506 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-10-10 10:35 | 2024-06-27 11:05 | 12 | 12 | 7 | TRUE | 2ffba710-feed-47a3-a291-b7ec4a5394ea | null | FCSR-FTECHG2 | KA79521065 | Slidegate Assy. | 135663 | Tata Steel Meramandli | India | India | SR | 40 | α – Alpha | Tool | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[735cb048-3ee7-4743-bfc1-9f7a0b5ddaa8][1]_[2].jpeg"} | KA79521065 | 2024-04-18 22:00 | 2024-05-25 22:00 | 2024-12-18 23:00 | null | null | null | null | null | null | null | null | null | null | null | null
10.10.2024 campaign planned for December 2024
not started yet (no mix available)
WK29-30 shut down
26.05.2024 - PO
19.04.2024 - 1st dwg !!!
0 | 507 | null |  | 507 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-07-04 11:18 | 2024-07-04 10:55 | 12 | 12 | 2 | FALSE | 0295c7fb-d941-4896-ba09-dc768c980a93 | null | FCSR-FTECHG2 | KA78564090 | Slidegate Assy. | 123629 | Hyundai Steel Dangjin Billet caster | South Korea | North Asia | SR | 30 | α – Alpha | Pieces on Site | null | in transit | 2023-10-03 22:00 | 2023-10-17 22:00 | 2024-02-11 23:00 | 2024-03-04 23:00 | null | 2024-07-10 22:00 | null | null | null | null | null | null | null | null | null
09.05.2024, HU 3000016546
05.03.2024 packing
PO 18.10.2023,
first order 18.10.2023 for KA78564090-> then decision 04.01 about producing these two items
pressing 12.02.2024?
29.11.2023 pending assembly (40pcs agreed by Technology and R&D)
51pcs fetling 27.11.2023
83pcs carbonization 24.11.2023
83pcs impregnated 21.11.2023
100pcs cooked 19.11.2023
100pcs cured 15.11.2023
105pcs pressed 26.10.2023
PO date 18.10.2023
03.10.2023 1st dwg
0 | 508 | null |  | 508 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-07-04 11:19 | 2024-07-04 11:01 | 12 | 12 | 2 | FALSE | d4ee0908-1d84-4839-b238-a0e48b5601d8 | null | FCSR-FTECHG2 | KA78606 | Slidegate Assy. | 123629 | Hyundai Steel Dangjin Billet caster | South Korea | North Asia | SR | 20 | α – Alpha | Pieces on Site | null | in transit | 2023-10-04 22:00 | 2023-10-17 22:00 | 2024-02-04 23:00 | 2024-05-08 22:00 | null | 2024-07-11 22:00 | null | null | null | null | null | null | null | null | null
09.05.2024, HU 3000016547
05.03.2024 packing
12.02.2024 pressing
05.02.2024 mixing
PO 18.10.2023, first order 18.10.2023 for KA78564090-> then decision 04.01 about producing these two items
SK08072000
29.11.2023 pending assembly (40pcs agreed by Technology and R&D)
51pcs fetling 27.11.2023
83pcs carbonization 24.11.2023
83pcs impregnated 21.11.2023
100pcs cooked 19.11.2023
100pcs cured 15.11.2023
105pcs pressed 26.10.2023
PO date 18.10.2023
03.10.2023 1st dwg
0 | 509 | null |  | 509 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-07-04 11:16 | 2024-07-04 11:05 | 12 | 12 | 2 | FALSE | b37c06be-fa15-4635-a503-5ef7902a3d93 | null | FCSR-FTECHG2 | KA79554085 | Slidegate Assy. | 840041 | ArcelorMittal Eisenhüttenstadt 11200800 | Germany | Europe | SR | 36 | α – Alpha | Trial | null | WK28 trial plan | 2024-04-03 22:00 | 2024-04-09 22:00 | 2024-04-09 22:00 | 2024-05-23 22:00 | null | 2024-06-06 22:00 | 2024-07-07 22:00 | null | null | null | null | null | null | null | null
36pcs (40) shipped 24.05.2024, HU 3000035500
24.05.2024 packing
PO 22.05.2024
17.04.2024 pressing
10.04.2024 mixing
1st dwg!!!
0 | 510 | null |  | 510 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-07-04 11:09 | 2024-07-04 11:09 | 12 | 12 | 1 | FALSE | 7267b53c-725b-40e3-87a7-950208bae29a | null | FCSR-FTECHG2 | KA79539 | Slidegate Assy. | 101769 | Voestalpine Linz (LD3) | Austria | Europe | SR | 30 | α – Alpha | Trial | null | Trial plan to confirm | 2024-04-03 22:00 | 2024-04-09 22:00 | 2024-04-09 22:00 | 2024-05-23 22:00 | null | 2024-06-05 22:00 | 2024-07-10 22:00 | null | null | null | null | null | null | null | null
30 pcs shipped 24.05.2024, HU 3000035501
24.05.2024 packing
22.05.2024 PO
17.04.2024 pressing
10.04.2024 mixing
1st dwg !!!!
0 | 511 | null |  | 511 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-08-14 10:17 | 2024-07-04 11:15 | 12 | 116 | 2 | FALSE | 57789fa3-9ee0-42d5-b420-e36a7f4e6285 | null | FCSR-FTECHG2 | KA79505 | Slidegate Assy. | 173481 | ArcelorMittal France, Site de Dunkerque | France | Europe | SR | 30 | α – Alpha | Trial | null | Trial Date: 05.08.2024 | 2024-04-03 22:00 | 2024-04-09 22:00 | 2024-04-09 22:00 | 2024-06-25 22:00 | null | 2024-07-14 22:00 | 2024-08-04 22:00 | null | null | null | null | null | null | null | null
*KA79505 - KA76923 (PO for regular scheduled qty)
under standard code KA76923 30 pcs
lack of special PO, shipping from exisiting orders KA76923
28.06.2024 - shipment, HU 3000043383
26.06.2024 - packing
17.04.2024 - pressing
10.04.2024 - mixing
1st dwg !!!
0 | 512 | null |  | 512 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-10-03 10:11 | 2024-09-12 10:22 | 12 | 116 | 3 | FALSE | 54612ea4-ad11-4df0-a8ee-e6f9883eef7f | null | FCSR-LTECH | KA74977050 | Slidegate Assy. | 142906 | Ternium Mexico, SA de DV (Puebla) | USA | NAFTA | SR | 300 | α – Alpha | Tool | null | 03.10.2024 mixing wk41, pressing planned for wk42 | 2024-07-03 22:00 | 2024-08-20 22:00 | 2024-08-20 22:00 | null | null | null | null | null | null | null | null | null | null | null | null
12.09.2024 production to arrange, not full batch for firing
semi-finished plate SK00426
PO Date - 21.08.2024
0 | 513 | null |  | 513 | 0x0100C43E332D9327E94C985ECBDE39833559000C5039B40E27B743A5631E0719F0CA5D | null | 2024-10-10 10:21 | 2024-10-10 10:21 | 12 | 12 | 3 | TRUE | d6cbb273-5a7b-4287-88fe-f027b9e6bc3d | null | FCSR-LTECH | KA76188060 | Slidegate Assy. | 104019 | BRAZIL | Brazil | South America | SR | 30 | α – Alpha | Tool | {"fileName":"Reserved_ImageAttachment_[12]_[DrawingImage][36]_[5e8c9832-e15a-418e-9ef6-c076cdd34ee3][1]_[1].jpeg"} | To check Customer! with Vini | 2024-09-03 22:00 | 2024-09-22 22:00 | 2024-10-09 22:00 | null | null | null | null | null | null | null | null | null | null | null | null
10.2024 - RM Date - to confirm
23.09.2024 - PO Date